## Slide 1
RTC+B Task Force
Update
Matt Mereness
RTCBTF
November 13, 2025

## Slide 2: Outline
Discussion today:
  Update on RTCBTF Issues List
  Scope of RTC+B Program
  Market Trials Update
  Market Notices walk-through
  Rest of Today’s Agenda

## Slide 3: RTCBTF Remaining Items for Go-Live
RTCBTF- Completed market trials and transition plan details
Market Trials
COMPLETED

## Slide 4: RTC+B Scope
Final 2025 Refinements for Go-Live
Related NPRRs
within Program

## Slide 5
Sequence and Dates for Market Trials to Go-Live
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
RTC QSE Telemetry Check-out (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added Prod EMS model.
COMPLETED

## Slide 6: Sep/Oct Market Trials in-flight
Trials & Transition meetings in-flight every Monday 10-10:30am until December 1-5 (then daily)
  Standalone calendar page each week with WebEx
    RTCBTF Home Page houses all market trials documentation
  Averaging 150-175 participants
  Weekly presentation walk-through with Q&A
    Heavy use of RTCB@ercot.com email -> FAQ
  Link to this Monday’s Trials meeting

## Slide 7: Market Trials and Transition through Go-Live
We are here….
NCLR s/provide = NCLR can use self-provision in SCED
DST Nov 2

## Slide 8: Market Notices sent last week
30-day Market Notices sent November 5 across usual channels:
  RTC+B Program Readiness
  RTC+B Protocol Changes
  RTC+B Settlement
  RTC+B Credit
  RTC+B Market Facing changes
Two other Notices
  API End-Point Changes (affects all entities accessing ERCOT XML/API Dec 4/5 impacts)
  QSE without Resources Acknowledgement

## Slide 9: Market Notices sent last week
  RTC+B Program Readiness

## Slide 10: Market Notices sent last week
  RTC+B Protocol Revision Request Changes

## Slide 11: Market Notices sent last week
  RTC+B Settlement

## Slide 12: Market Notices sent last week
  RTC+B Credit

## Slide 13: Market Notices sent last week
  RTC+B Market Facing changes

## Slide 14: Market Notices sent last week
  RTC+B Market Facing changes

## Slide 15: Market Notices sent last week
  API End-Point Changes (affects all entities accessing ERCOT XML/API Dec 4/5 impacts)

## Slide 16: Market Notices sent last week
  QSE without Resources Acknowledgement

## Slide 17: November/December
Week 2 RTCBTF Workshops for December go-live Cutover
Weeks 2 & 3 Continue Trial Activity
Currently minimal plans week of Thanksgiving

## Slide 18: Other Updates
Later today:
  Transition/Cutover Meeting for QSEs (1-3pm)
  Transition/Cutover Meeting for TDSPs (3:30-4:30pm)
TWG meeting Nov 20 for more detailed technical discussions
Next 3 weeks:
  Weekly Market Trials/Transition meetings continue
First week of December
  Daily Cutover Meetings 10am-11am
Next RTCBTF Dec 12 (on the other side of go-live)

## Slide 19: Focus for remainder of RTCBTF Agenda today:
3. Closed-Loop LFC Update Whitepaper (posted Nov 7)
4. Follow-up from RUC Capacity Short Education (posted Nov 10)
5. AS Deployment Factors Discussion (posted Nov 7)
Market Feedback- Shams/HEN
Questions before moving on?
(Lunch arriving around noon)