## Slide 1
Current MOTE Transition to RTC+B
Sreenivas Badri
November 20, 2025

## Slide 2: Current MOTE Transition to RTC+B – Cutover Plan
Current MOTE (UIs/APIs) will be down from November 28, 2025, 5:30 PM in preparation for cutover to RTC+B.
Current MOTE (UIs/APIs) will be updated with RTC+B code and configurations and will be up with following new API URLs by 12:00 Noon on December 1, 2025.
  New MOTE API URLs:
  Internet API URL: https://testmisapi.ercot.com/NodalAPI/EWS/
  WAN API URL: https://testmisapi.wan.ercot.com/NodalAPI/EWS/
*ERCOT is not making any changes to current MOTE digital certs and API public key
This means MOTE will be down from November 28, 2025, 5:30 PM until December 1,2025 12:00 noon
Market Participants are expected to complete any planned market and outage submissions communication and qualification testing for current system by November 28, 2025, 5:00 PM, as MOTE system will not be available for current production market and outage submissions testing from December 1-4, 2025.

## Slide 3: Current MOTE Transition to RTC+B – Cutover Plan
MOTE Market Manager UI and Outage Scheduler UI URLs will remain same as current URLs after MOTE transition to RTC+B. Below are current MOTE Market Manager UI and Outage Scheduler UI URLs:
  Market Manager UI: https://testmis.ercot.com/mmsui/mmsui/displayTradesLanding.action
  Outage Scheduler (OS) UI: https://testmis.ercot.com/osrui/osrui/Summary.action
Same current MOTE system Notification Listener URLs will be used to send notifications to Market Participants after the MOTE transition to RTC+B.
MOTE MPIM is NOT impacted due to RTC+B upgrade, so Market Participants will be using same MPIM applications.
ERCOT will open a Secure Webex Call from 1:00 PM till 3:00 PM on December 1,2025 to support QSEs/TSPs MOTE API URLs transition to new MOTE API URLs.
ERCOT will send out Secure Webex Conference call information this week to QSEs/TSPs AR & BAR.
Market Notice will be sent out today with details on current MOTE transition to RTC+B.

## Slide 4: MOTE Cutover Plan - Timelines
Note - Market Participants are expected to complete any planned market and outage submissions communication and qualification testing for current system by November 28, 2025, 5:00 PM, as MOTE system will not be available for current production market and outage submissions testing from December 1-4, 2025.
 | Effective Dates | Digital Certificate | MMSUI/ OSUI | API/WAN URL
Current MOTE | Till 11/28/2025 5:30 PM | Current MOTE | testmis.ercot.com/mmsui testmis.ercot.com/osui | https://testmisapi.ercot.com /2007-08/Nodal/eEDS/EWS/ https://testmisapi.wan.ercot.com:9443/2007-08/Nodal/eEDS/EWS/
RTC+B MOTE | From 12/1/2025 12:00 noon | Current MOTE (no change) | No change: testmis.ercot.com/mmsui testmis.ercot.com/osui | New MOTE URLs: https://testmisapi.ercot.com/NodalAPI/EWS/ https://testmisapi.wan.ercot.com/NodalAPI/EWS/

## Slide 5: Current MOTE Transition to RTC+B – Cutover Plan
Questions?
Any concerns/questions, please contact us at rtcb@ercot.com