## Slide 1
RTC+B Update
for TWG
Matt Mereness
November 20, 2025

## Slide 2
Sequence and Dates for Market Trials to Go-Live
#1 RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
#3 Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
#5 Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
#2 RTC QSE Telemetry Checkout (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
#6 Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
#4 QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added Prod EMS model.
Market trials are a progression of activities to mitigate the risk for Go-Live on new systems and processes for both the Market Participants & ERCOT.

## Slide 3: Market Trials and Transition through Go-Live
We are here….
Currently minimal plans during Thanksgiving week (ERCOT system will be online)

## Slide 4: Market Notices sent last week
30-day Market Notices sent November 5 across usual channels:
  RTC+B Program Readiness
  RTC+B Protocol Changes
  RTC+B Settlement
  RTC+B Credit
  RTC+B Market Facing changes
Two other Notices
  API End-Point Changes (affects all entities accessing ERCOT XML/API Dec 4/5 impacts)
  QSE without Resources Acknowledgement

## Slide 5: Market Notices sent last week
  RTC+B Program Readiness

## Slide 6: Market Notices sent last week
  RTC+B Protocol Changes

## Slide 7: Market Notices sent last week
  RTC+B Settlement

## Slide 8: Market Notices sent last week
  RTC+B Credit

## Slide 9: Market Notices sent last week
  RTC+B Market Facing changes

## Slide 10: Market Notices sent last week
  RTC+B Market Facing changes

## Slide 11: Market Notices sent last week
  API End-Point Changes (affects all entities accessing ERCOT XML/API Dec 4/5 impacts)

## Slide 12: Market Notices sent last week
  QSE without Resources Acknowledgement

## Slide 13: RTC+B Task Force & Workshops Links to Cutover Workshops Last Week and key materials
RTC+B Cutover Workshop for QSEs
  Review RTCB Transition/Cutover Handbook
  QSE Dual Entry Expectations
  Detailed Cutover Plan
RTC+B Cutover Workshop for TDSPs
  Outage Scheduler API URL changes
  Outage Scheduler Cutover Plan
  SOTE Studies

## Slide 14: Cutover Discussion Highlights
Next Week normal weekly call with focus on transition/cutover
Added to ERCOT Calendar:
Daily RTC+B Cutover Calls Mon-Fri Dec 1-5 10am-11am

## Slide 15: Cutover Discussion Highlights
Link to Cutover Handbook on RTCBTF Homepage
Timing and Dual Entry Requirements

## Slide 16: Cutover Discussion Highlights
Link to Cutover Strategy for Dual Submissions spreadsheet on RTCBTF Homepage
Granular Timing and Dual Entry Requirements

## Slide 17: Cutover Discussion Highlights
No dual submission requirements for Day-Ahead Market purposes
  DAM executions performed Dec 1 – Dec 4 are same pre-RTC system
  First “changed DAM” in RTC+B is executed on Dec 5, for OD Dec 6
Dual submissions limited to certain transactions on certain days as described in spreadsheet (prior slide) and explained at a high level in next slide…..

## Slide 18
Pre-RTC System
RTC System
Dec 1
Dec 2
Dec 3
Dec 4
Dec 6
Dec 5
Dec 1
Dec 2
Dec 3
Dec 4
Dec 6
Dec 5
QSE Submitting during timeframe of
Dec 1-3
Market Submissions December 1-3
Overlapping / Dual Submissions

## Slide 19
Pre-RTC System
RTC System
Dec 1
Dec 2
Dec 3
Dec 4
Dec 6
Dec 5
Dec 1
Dec 2
Dec 3
Dec 4
Dec 6
Dec 5
QSE Submitting during timeframe of
Dec 4
Example, RUC Snapshots after 1800 Dec 4 (balance of 12/4 and OD 12/5) needs items maintained by QSEs for settlement if any RUCs for Dec 5:
COP
AS Offers
QSE-Trades
After pre-RTC DAM on 12/4 for OD 12/5 is executed:
ERCOT will copy DAM Awards and Self-Arranged AS into RTC tables by 1800
Market Submissions December 4

## Slide 20
Pre-RTC System
RTC System
Dec 1
Dec 2
Dec 3
Dec 4
Dec 6
Dec 5
Dec 1
Dec 2
Dec 3
Dec 4
Dec 6
Dec 5
QSE Submitting during timeframe of
Dec 5
Midnight cutoff pre-RTC system
Energy Trades only*
Market Submissions December 5
* Energy Trades can be put in for prior OD (back to 1430)

## Slide 21: Cutover Step-by-Step Timeline Graphic
Link to Cutover Detail Plan Draft Presentation on RTCBTF Homepage

## Slide 22: Cutover Step-by-Step Timeline Spreadsheet
Link to Go-Live Cutover Plan External Spreadsheet on RTCBTF

## Slide 23: Market Notice for MOTE transition Dec 1

## Slide 24: Current MOTE Transition to RTC+B – Cutover Plan
Current MOTE (UIs/APIs) will be down from November 28, 2025, 5:30 PM in preparation for cutover to RTC+B.
Current MOTE (UIs/APIs) will be updated with RTC+B code and configurations and will be up with following new API URLs by 12:00 Noon on December 1, 2025.
  New MOTE API URLs:
  Internet API URL: https://testmisapi.ercot.com/NodalAPI/EWS/
  WAN API URL: https://testmisapi.wan.ercot.com/NodalAPI/EWS/
*ERCOT is not making any changes to current MOTE digital certs and API public key
This means MOTE will be down from November 28, 2025, 5:30 PM until December 1,2025 12:00 noon
Market Participants are expected to complete any planned market and outage submissions communication and qualification testing for current system by November 28, 2025, 5:00 PM, as MOTE system will not be available for current production market and outage submissions testing from December 1-4, 2025.

## Slide 25: Current MOTE Transition to RTC+B – Cutover Plan
MOTE Market Manager UI and Outage Scheduler UI URLs will remain same as current URLs after MOTE transition to RTC+B. Below are current MOTE Market Manager UI and Outage Scheduler UI URLs:
  Market Manager UI: https://testmis.ercot.com/mmsui/mmsui/displayTradesLanding.action
  Outage Scheduler (OS) UI: https://testmis.ercot.com/osrui/osrui/Summary.action
Same current MOTE system Notification Listener URLs will be used to send notifications to Market Participants after the MOTE transition to RTC+B.
MOTE MPIM is NOT impacted due to RTC+B upgrade, so Market Participants will be using same MPIM applications.
ERCOT will open a Secure Webex Call from 1:00 PM till 3:00 PM on December 1,2025 to support QSEs/TSPs MOTE API URLs transition to new MOTE API URLs.
ERCOT will send out Secure Webex Conference call information this week to QSEs/TSPs AR & BAR.
Market Notice will be sent out today with details on current MOTE transition to RTC+B.

## Slide 26: Wrap-Up and Questions
QSEs should be reviewing Cutover plans and considering staffing and system needs for Dec 1-5
  MOTE transition activities end of next week
  ERCOT will be asking for Cutover night contacts