## Slide 1
Weekly
RTC+B Market Trials Update
ERCOT Staff
December 1, 2025

## Slide 2: Outline
Antitrust Admonition
Where we are at
Cutover Workshop highlights
MOTE transition
Walk-through other postings/details
Q&A
Appendix- Supporting Materials:
  Summary of SCED Functionality
  SCED Analysis/Results for prior week
  DAM and AS Self-Provision Education
  Telemetry Screening
  New RTC Pricing Reports location
  NPRR1290 Validation Changes
  Links to Handbooks
  FAQ Updated
  Connectivity and Configuration (digital certs)

## Slide 3
WebEx Meeting reminders (same as other ERCOT forums):
Please keep line muted
If you have a question, please use the chat feature to either:
  Type in your question, or
  Type in “Question” and wait to be recognized to state question

## Slide 4
Sequence and Dates for Market Trials to Go-Live
#1 RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
#3 Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
#5 Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
#2 RTC QSE Telemetry Checkout (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
#6 Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
#4 QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added Prod EMS model.
Market trials are a progression of activities to mitigate the risk for Go-Live on new systems and processes for both the Market Participants & ERCOT.

## Slide 5: Market Trials and Transition through Go-Live
We are here….
RTC+B Systems are now Production for od December 5 and onward….

## Slide 6: Market Notices sent
30-day Market Notices sent November 5 across usual channels:
10-day Market Notices sent November 21 across usual channels
https://www.ercot.com/services/comm/mkt_notices/archives

## Slide 7: Market Notices sent
  RTC+B Market Facing changes

## Slide 8: Market Notices sent
  RTC+B Market Facing changes

## Slide 9: Market Notices
  API End-Point Changes (affects all entities accessing ERCOT XML/API Dec 4/5 impacts)

## Slide 10: Market Notices
  QSE without Resources Acknowledgement (not re-sent, performing ERCOT outreach)

## Slide 11: RTC+B Task Force & Workshop References Links to Cutover Workshops (Nov 13) and TWG (Nov 20) materials
RTC+B Cutover Workshop for QSEs
  Review RTCB Transition/Cutover Handbook
  QSE Dual Entry Expectations
  Detailed Cutover Plan
RTC+B Cutover Workshop for TDSPs
  Outage Scheduler API URL changes
  Outage Scheduler Cutover Plan
  SOTE Studies
TWG Meeting Nov 20
  More Details
  Dual Submissions
  etc

## Slide 12: ESR Single- Model Qualification
Special Note about ESR Qualification:
  If ERCOT does not receive updated tests in NDCRC, the RRS-PFR qualification for RTCB go-live will be removed.
  The RRSPFR qualification will be re-instated upon submitting the test.

## Slide 13: Cutover Discussion Highlights
Link to Cutover Handbook on RTCBTF Homepage
Timing and Dual Entry Requirements

## Slide 14: Cutover Discussion Highlights
Link to Cutover Strategy for Dual Submissions spreadsheet on RTCBTF Homepage
Granular Timing and Dual Entry Requirements

## Slide 15: Cutover Discussion Highlights
No dual submission requirements for Day-Ahead Market purposes
  DAM executions performed Dec 1 – Dec 4 are same pre-RTC system
  First “changed DAM” in RTC+B is executed on Dec 5, for OD Dec 6
Dual submissions limited to certain transactions on certain days as described in spreadsheet (prior slide) and explained at a high level in next slide…..

## Slide 16
Pre-RTC System
RTC System
Dec 1
Dec 2
Dec 3
Dec 4
Dec 6
Dec 5
Dec 1
Dec 2
Dec 3
Dec 4
Dec 6
Dec 5
QSE Submitting during timeframe of
Dec 1-3
Market Submissions December 1-3
Overlapping / Dual Submissions

## Slide 17
Pre-RTC System
RTC System
Dec 1
Dec 2
Dec 3
Dec 4
Dec 6
Dec 5
Dec 1
Dec 2
Dec 3
Dec 4
Dec 6
Dec 5
QSE Submitting during timeframe of
Dec 4
Example, RUC Snapshots after 1800 Dec 4 (balance of 12/4 and OD 12/5) needs items maintained by QSEs for settlement if any RUCs for Dec 5:
COP
AS Offers
QSE-Trades
After pre-RTC DAM on 12/4 for OD 12/5 is executed:
ERCOT will copy DAM Awards and Self-Arranged AS into RTC tables by 1800
Market Submissions December 4
Real-Time Market Submissions – Submit for all Operating Hours for OD 12/04/2025 HE 1800 and Beyond
AS Offers
TPO Output Schedules

## Slide 18
Pre-RTC System
RTC System
Dec 1
Dec 2
Dec 3
Dec 4
Dec 6
Dec 5
Dec 1
Dec 2
Dec 3
Dec 4
Dec 6
Dec 5
QSE Submitting during timeframe of
Dec 5
Midnight cutoff pre-RTC system
Energy Trades only*
Market Submissions December 5
* Energy Trades can be put in for prior OD (back to 1430)

## Slide 19: Cutover Step-by-Step Timeline Graphic
Link to Cutover Detail Plan Presentation on RTCBTF Homepage

## Slide 20: Cutover Step-by-Step Timeline Spreadsheet
Link to Go-Live Cutover Plan External Spreadsheet on RTCBTF

## Slide 21: Market Notice for MOTE transition Dec 1

## Slide 22: Current MOTE Transition to RTC+B – Cutover Plan
Current MOTE (UIs/APIs) is updated with RTC+B code and configurations
  New MOTE API URLs:
  Internet API URL: https://testmisapi.ercot.com/NodalAPI/EWS/
  WAN API URL: https://testmisapi.wan.ercot.com/NodalAPI/EWS/
*ERCOT is not making any changes to current MOTE digital certs and API public key
  Market Manager UI: https://testmis.ercot.com/mmsui/mmsui/displayTradesLanding.action
  Outage Scheduler (OS) UI: https://testmis.ercot.com/osrui/osrui/Summary.action
  Same current MOTE system Notification Listener URLs will be used to send notifications to Market Participants after the MOTE transition to RTC+B.
  MOTE MPIM is NOT impacted due to RTC+B upgrade, so Market Participants will be using same MPIM applications.
ERCOT support call today from 1:00 PM till 3:00 PM on December 1,2025 to support QSEs/TSPs MOTE API URLs transition to new MOTE API URLs.
  https://www.ercot.com/calendar/12012025-RTC_B-MOTE-Support-Call

## Slide 23: Wrap-Up and Questions
Extra support beyond Daily Calls:
  Public MOTE WebEx today
    Connectivity support
  Secure WebEx Thursday night cutover for QSE with Resources (similar to LFC Test)
    Mailing WebEx info later today to AuthRep and BackupAuthRep
    Also confirm if same QSE contact list as used for LFC Closed Loop Tests
  Public QSE WebEx for Friday morning
    Connectivity/submission support for Day-Ahead Market
QSEs should be reviewing Cutover plans and considering staffing and system needs for Dec 1-5
Go to more details and then finish Wrap-Up
RTC+B FAQ is a great resource for support (on RTCBTF home page):
    https://www.ercot.com/files/docs/2025/05/12/RTCB-FAQ-Questions-and-Answers-111925.xlsx
Remainder of meeting for Q&A
  Can always email the RTC+B Program mailbox: RTCB@ercot.com

## Slide 24: APPENDIX- Supporting Materials from Market Trials
Summary of SCED Functionality
SCED Analysis/Results for prior week
DAM and AS Self-Provision Education
Telemetry Screening
New RTC Pricing Reports location
NPRR1290 Validation Changes
Links to Handbooks
FAQ Updated
Connectivity and Configuration (digital certs)

## Slide 25: Summary of SCED functionality
What is RTC SCED using to solve in trials?
  Production Network model from NMMS
  QSE submitted offers (energy and A/S)
  QSE production telemetry
    ERCOT performs some overrides for stale data from QSE sites- improving each week
  Outages in prod telemetry would be outage in RTC SCED
  July 31 improvements implemented:
    NPRR1268/1269 ASDC and Proxies logic implemented
    AS Plan improved and now same as Prod
  Aug 4 improvements implemented:
    IRR Forecast synchronization has been manual, but now automated
  Aug 18 improvements implemented :
    Active constraints flag being manually copied (automation planned for Aug 18)
    Load Forecasts being fed into RTC, but ERCOT manually aligns which forecast is being used based on operator selection in Prod (automation planned for Aug 18)

## Slide 26: Day-Ahead Market

## Slide 27: DAM Operating Day (OD) Test
Testing strongly encouraged, but not required for all QSEs
  Handbook #6 Day-Ahead Market
  The DAM will run on Tuesdays
  DAM submission window closes at noon.
By 0600 QSEs can validate and confirm report posting:
  Advisory AS Obligation: Available on Market Trials MMSUI (5 significant digits after decimal point)
  ASDCs: Available on Production MIS
  Load Ratio Share and PSS/e files will change with RTC cutover, but will not be visible for OD 9/17
For successful DAM completion, and meaningful results, market participants are strongly encouraged to submit various submission types, and not only submission types listed above (E.g., PTPs, EOOs, EBs, AS Self-Arrangement, non-ESR AS and non-ESR TPO submissions).

## Slide 28: DAM Operating Day (OD) Test – Pre DAM
Key DAM Submission Changes
  AS Obligation – no self-arrangement will be allowed over QSE’s Advisory AS Obligation.
    Example: RRS Advisory AS Obligation = 2.18368 -> maximum Self-AS submission = 2.1
  COP – can submit negative LSL/HSL for ESR. Can submit values for AS Capability within the existing AS fields.
  TPO (EB/OC) – negative MW quantity reflects ESR EB/OC. ESR startup and minimum energy costs are not allowed and ESRs are considered self-committed.
  Resource-Specific AS Offers – FRRSUP and FRRSDN offers not allowed. Offers must be between $0 and DAM SWCAP. For ESRs, RRSUFR and ECRSM offers not allowed. All AS offers from ESRs are inclusive of EB/OCs.
  AS Only Offers – Offers must be between $0 and DAM SWCAP. REGUP, REGDN, RRSPFR, Online NSPIN, and Online ECRS are allowed. Other AS types are not allowed. Multi-hour and fixed blocks are not allowed.

## Slide 29: DAM Operating Day (OD) Test – Post DAM
Post Publish Report Verification
  AS-Only Awards
  ESR Resource-Specific AS awards
  TPO(EB/OC) awards
  QSEs with Advisory AS Obligations and AS awards can download/review their Final AS Obligations and ensure observe/handle values with up to 5 significant digits after the decimal
  DAM LMPs
  DAM MCPCs
  DAM Constraint Shadow Prices
  Other DAM Awards

## Slide 30: DAM ASDC Price Setting Example
OD 9/17/2025 HE 21
NSPIN MCPC : $38.52
  AS Award stack intersected the ASDC @ 2536.6 MW
  NSPIN AS Plan @ HE 21 : 2339 MW

## Slide 31: DAM ASDC Price Setting Example
OD 9/17/2025 HE 18
ECRS MCPC : $80.51
  AS Award stack intersected the ASDC @ 1888.6 MW
  ECRS AS Plan @ HE 18 : 2877 MW

## Slide 32: NCLR Self-Provision Reminder: AS Self-Provision is a special design to allow Non-Controllable Load Resources to self-provide their AS Responsibilities into/through SCED/Real-Time Market

## Slide 33: NCLR Resource Status Codes
Pre-RTC
  Resource Status Codes (RST)
  OUTL = 260
  ONRL = 259
  ONECL = 264
RTC+B
  Updated Resource Status Codes (RSTR)
  OUTL = 258
  ONL = 257

## Slide 34: Ramp Rates and Capabilities
Pre-RTC
  AS Responsibility and Schedule
  RRRS
  RRSC
  ECRS
  ECSC
  NSRS
  NSSC
RTC+B
  Ramp Rates & Awards
  UFRC (UFR Capability)
  UFRA (UFR Award)
  ECRR (ECRS RR Capability *10 Min)
  ECRA (ECRS Award)
  NSRR (NSPIN RR Capability *30 Min)
  NSRA (NSPIN Award)
QSE to ERCOT Telemetry
ERCOT to QSE ICCP

## Slide 35: Self-Provision Achieved via Telemetry Points for NCLRs
QSEs will be able to self-provide in real-time via telemetered ICCP points
LEGEND
ICCP Change Request Example RTC+B V1.4 on RTC ERCOT webpage

## Slide 36: The Self-Provision Checklist
Scenario: My Load Resource was awarded 15 MW in the DAM, and I purchased 5 MW via a trade.
My total RRS AS Position is 20 MW.
How to correctly self-provide 20 MW:
    Is my resource qualified?
    Telemetry Points
      RSTR set to ONL (257)
      UFR must be Armed
      Can I cover my obligation?
        Qualified MW Amount ≥ Self-provided amount
        NPF - LPC ≥ Self-provided amount
        Capability to Provide AS ≥ Self-provided amount
      Final Step: Telemeter Self-provision
      “your offers explain your extra”

## Slide 37: Scenario 1
Scenario ** Assume AS qualified for All Headroom (NPF-LPC) | Max Power Cons. | Net Power Flow | Low Power Cons. | Resource Status | Under Freq. Relay | Self-provided RRS UFR (MW) | Self-provided ECRS (MW) | Current Capability to provide UFR (MW) | ECRS (10min) Ramp Rate (MW/min) | RRS UFR AS Award | ECRS AS Award | Notes
 | MPC | NPF | LPC | RSTR | UFR | SPUF | SPEC | UFRC | ECRR | UFRA | ECRA | 
NCLR_1 is qualified to provide 20 MW. DAM awards NCLR_1 with 15MW RRS. QSE also has additional 5MW RRS Position via RRS Trades. | 20 | 20 | 0 | ONL | Arm | 20 | 0 | 20 | 0 | 20 | 0 | NCLR_1 Telemetry needs to show: Status = ONL, MPC >= NPF >= 20 MW, NPF-LPC >= 20 MW, RRS capability >= 20 MW, RRS self-provided telemetry = 20 MW SCED will respect the 20 MW self-provided RRS and award the resource 20 MW RRS UFR.
QSE to ERCOT Telemetry
ERCOT to QSE ICCP
NCLR_1 has a 20 MW RRS AS Position, 15 MW from DAM award and 5 MW from RRS Trade

## Slide 38: Telemetry Screening for Scorecard 3B for Handbook 3 Acceptable Telemetry Point values received by ERCOT for active resources.
Key points for Telemetry scorecard check
  Device types checked - Units, CLRs, NCLRs, ESRs for each QSE
  RTCB Telemetry status should be “Good” quality
  RTCB Units / CLRs / NCLRs Telemetry values should be within “Expected Range” or an expected value. Details are provided in next few slides.
  Expected values are derived from equivalent analogs in current production, based on defined criteria.
  RTCB ESR telemetry values are checked against corresponding combo model Battery Unit / CLR counterparts in production.
Scoring:

## Slide 39: RTC+B Telemetry points screening/validation

## Slide 40: RTC+B New Reports Posted to the ERCOT Website
Links to the available RTC+B versions of Real-Time reports posted on Real-Time Market Information page.

## Slide 41: Submission validation update - PROD vs RTC+B
NPRR1290 :
  cleaned up protocol language around submitting offer curves and bid curves
  disallows having more than 2 price/quantity points in a flat/vertical segment of the curve.
Impacts to QSEs during dual-submission – some submissions accepted in Production will be rejected in Market Trials environment:
RTM Energy bids – protocol requiring “increasing quantities” now enforced.
  Reverted this change to validation. Further discussion highlighted protocol should be brought in line to long-standing practice, not validation.
  Example: Bid with Q1=0mw, Q2=10mw, Q3=10mw will be rejected as Q3 does not increase from Q2.
TPO & RTM Bid – more than 2 price/quantity pairs with same price or quantity will be rejected
Market Submission Validation
Rules document updated.

## Slide 42: Submission validation update - PROD vs RTC+B
TPO – EB/OC - EOC
RTM EB
RTM EB

## Slide 43: Market Trials Framework:
TAC Approved the Market Trials Plan in October 2024
Discussions with RTC+B Task Force have shaped the Handbooks
Handbook #1- QSE Submission Testing
Handbook #2- QSE Telemetry Tests
Handbook #3- Open Loop SCED
Handbook #4- QSE Telemetry Tests
Handbook #5- Close-Loop LFC Tests
Handbook #6- Day-Ahead Market Tests
All are posted on the
RTCBTF Homepage
under Market Trials banner

## Slide 44: Market Trials Technical Details
Detailed discussions with TWG have provided technical content details
Digital Certificate details
Connectivity/URL details to User Interfaces and APIs
Reminder of how to submit new ICCP requests
RTC and Production Telemetry connectivity
Network Model Load Schedule
All are posted on the
RTCBTF Homepage
under Technical Details banner

## Slide 45: Reminder of RTC+B FAQ
Worksheets for categories
Posted on RTCBTF Home Page under Key Documents
Common questions/responses in Excel Workbook (target weekly updates)
Search workbook for Key Words

## Slide 46
RTC+B Market Submissions - Systems configurations
RTC QSE
Submission Testing
Open-loop
RTC SCED
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
Start
03/2025
Start
05/2025
Start
09/2025
Go-Live
12/5/25*
Apr 2025
Mar 2025
Feb 2025
Optional: RTC QSE/Vendor Developer
Submission Testing
Start
07/2025
Certificate: Current MOTE
Env: ERCOT RTC Market Trial
URL: RTC MIS MOTE URL
Certificate: Current Production
Env: ERCOT RTC Market Trial
URL: RTC MIS Market Trial
Cert: Production
Env: Prod
URL: MIS Prod
QSE/Vendor developer can use MOTE certificates & RTC MIS MOTE API URL to test the submissions until end of submission testing phase (end of June) as needed. At the start of the Open Loop testing, RTC MOTE MIS URLs will be disabled.
URL links: RTC MOTE and Market Trial URL links to be used for MMSUI, OSUI and API submissions. Actual links are provided in next slide.
For notifications/responses to MPs from RTC Market Trials environment, MP will need to provide the listener URL to ERCOT

## Slide 47: RTC+B Market Submissions - Systems configurations (Updated with URLs)
RTC+B Market Trials and Go-live
RTC Phase | Digital Certificate | MMSUI / OSUI URL | API / WAN URL
Vendor/QSE Submissions Testing | Current MOTE | RTC MOTE MIS URLs https://testmarkettrials.ercot.com/mmsui/mmsui/displayTradesLanding.action https://testmarkettrials.ercot.com/osrui/osrui/Summary.action | RTC MOTE API/WAN URL https://testmarkettrialsapi.ercot.com/NodalAPI/EWS/ https://testmarkettrialsapi.wan.ercot.com/NodalAPI/EWS/
Open Loop and Closed Loop Testing | Current Production | RTC Market Trial URL https://markettrials.ercot.com/mmsui/mmsui/displayTradesLanding.action https://markettrials.ercot.com/osrui/osrui/Summary.action | RTC Market Trial API/WAN URL https://markettrialsapi.ercot.com/NodalAPI/EWS/ https://markettrialsapi.wan.ercot.com/NodalAPI/EWS/
From RTC Go-live onwards | Current Production | Current Prod MIS URL mis.ercot.com/mmsui mis.ercot.com/osui | New Production API/WAN URL

## Slide 48: RTC+B Market Submissions - Systems configurations Public Key Update for WAN/API submissions
For API/WAN submissions into Market Trials environments, need to download public keys and place into the keystore location in system being used for RTC+B submissions.
No change to digital user certificates – continue to use existing MOTE and Production Certificates
Market Trial API Public key location: https://www.ercot.com/services/mdt/webservices