## Slide 1
NOGRR282 Impacts on Large Load Interconnection Process
LLWG, December 11, 2025
Jeff Billo

## Slide 2: Existing Process (With PGRR115 Implemented)
There are currently no approved voltage/frequency ride through requirements.
Prior to requesting Initial Energization, all LELs:
  Must complete the DWG Large Load Data Survey.
  Be included in a QSA where ERCOT will perform a Large Electronic Load Voltage Ride-Through (LEL-VRT) assessment to identify impacts of LEL trips and establish SOL/IROL if needed.
If there are no SOL/IROL constraints identified in the QSA, the LEL may proceed to energization.
If one or more SOL/IROL constraints are identified, the LEL may energize once ERCOT updates control room monitoring and procedures.

## Slide 3: VRT Process: Before the approval of NOGRR282
11/14/2025
V/F RT Exempted
Voltage/Freq Ride-Through Required
Non-exempt LEL Energization Request after 11/14/2025
Until NOGRR282 is approved, ERCOT will accept energization requests from loads that do not meet the VRT requirements in NOGRR282 and do not meet the proposed exemption requirements.
ERCOT will perform the LEL-VRT assessment as described on slide 2.
  If lack of VRT causes SOL/IROL exceedance, the LEL may be energized after ERCOT updates the SOL/IROL control room and TO procedures*.
  If lack of VRT does not cause SOL/IROL exceedance, LEL may be energized as scheduled.
If NOGRR282 is approved with the currently proposed exemption criteria, this LEL will be required to comply VRT/FRT requirements.
*See: https://www.ercot.com/files/docs/2025/11/19/LLWG-LL-Operating-Limit-Implementation-v2.pptx

## Slide 4: VRT Process: After approval of NOGRR282 for Exempt LELs
11/14/2025
V/F RT Exempted
Voltage/Freq Ride-Through Required
Exempt LEL Energization Request after 11/14/2025
After NOGRR282 is approved, there will still be LELs that are exempt from the requirements that will request energization.
ERCOT will perform the LEL-VRT assessment as described on slide 2.
  If lack of VRT causes SOL/IROL exceedance, the LEL may be energized after ERCOT updates the SOL/IROL control room and TO procedures*.
  If lack of VRT does not cause SOL/IROL exceedance, LEL may be energized as scheduled.
If NOGRR282 is approved with the currently proposed exemption criteria, this LEL will not be required to comply VRT/FRT requirements but may be subject to curtailment if lack of VRT causes SOL/IROL exceedance.
*See: https://www.ercot.com/files/docs/2025/11/19/LLWG-LL-Operating-Limit-Implementation-v2.pptx

## Slide 5: VRT Process: After approval of NOGRR282
11/14/2025
V/F RT Exempted
Voltage/Freq Ride-Through Required
Non-exempt LEL Energization Request
After NOGRR282 is approved, a LEL that is not exempt and that cannot meet the VRT standard will not be granted approval to energize.
ERCOT plans to submit a PGRR in Q1 2026 to establish a model quality test process that includes VRT verification. This model quality verification will be required as a condition for granting approval to energize.
NOGRR 282 Becomes Effective

## Slide 6: Questions?