## Slide 1
RTC+B Update
Matt Mereness
TWG
December 18, 2025

## Slide 2: Outline
Discussion today:
  Update on Overall RTCBTF Issues List
  Summary of Defects and emergency fix later this week
  Follow-up on Reports
  Rest of Today’s Agenda

## Slide 3: RTCBTF Remaining Items for Go-Live
RTCBTF- Completed market trials and transition plan details
Market Trials
COMPLETED

## Slide 4: RTC+B Scope
Final 2025 Refinements for Go-Live
Related NPRRs
within Program

## Slide 5
Sequence and Dates for Market Trials to Go-Live
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
RTC QSE Telemetry Check-out (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added Prod EMS model.
COMPLETED

## Slide 6: Stabilization release this week
ERCOT is deploying a final package of emergency releases this week prior to the holidays
  Competitive Constraint Test logic fix
  Pricing during Load Shed – NPRR1131
  AS Trades (market notice on next slide)
  AS Manager deployment/recall messages issue

## Slide 7: Market Notice regarding AS Trades

## Slide 8: RTC Cutover Information: Missed Reports
EMIL_ID | RPT_ID | Product Name
np3-157-cd | 13446 | Consolidated Transmission Outage Report
NP3-233-CD | 13103 | Hourly Resource Outage Capacity
np4-738-cd | 13484 | Solar Power Production - Actual 5-Minute Averaged Values
np4-746-cd | 21810 | Solar Power Production - Actual 5-Minute Averaged Values by Geographical Region
np5-649-cd | 12352 | Temporarily Removed Contingencies
np4-733-cd | 13071 | Wind Power Production - Actual 5-Minute Averaged Values
np4-743-cd | 14788 | Wind Power Production - Actual 5-Minute Averaged Values by Geographical Region
NP6-329-CD | 24889 | RTD Indicative Real-Time MCPC
NP6-330-CD | 24890 | RTD Indicative Ancillary Service Awards by Resource
NP6-328-CD | 24887 | Total Capability of Resources Available to Provide Ancillary Service
NP6-332-CD | 24891 | Real-Time Clearing Prices for Capacity by SCED Interval
The following reports have the highest probability of being missed during cutover activities. ERCOT will not be able to repost these reports.
Additionally, NP3-763-CD Short Term System Adequacy (Rpt ID 12315) was missed and RERUN for the first hourly interval of the day on 12/5.

## Slide 9: RTC Cutover Information: Expired Reports
EMIL_ID | RPT_ID | Product Name
np5-758-cd | 13079 | Deselected Hourly RUC Recommendations
NP8-143-CD | 11025 | QSE Ancillary Services Capacity Monitor
np6-291-cd | 12309 | Topology Consistency
np6-619-cd | 12308 | State Estimator Real-Time Transmission Line Flows
NP6-327-CD | 21114 | LMP By SOG Including Price Adders
np6-787-cd | 11485 | LMPs by Electrical Bus
np6-788-cd | 12300 | LMPs by Resource Nodes, Load Zones and Trading Hubs
np6-914-cd | 12351 | Manual Overriding of HDLs and LDLs
NP6-323-CD | 13221 | Real-Time Price Adders by SCED Interval
np6-322-cd | 13114 | SCED System Lambda
np6-915-cd | 13081 | Summary Report of HDL and LDL
np12-218-cd | 23995 | ERCOT System Limit Exceedances
np6-6-cd | 12305 | NSA Active Constraints
np5-911-cd | 12345 | NSA Inactive Constraints
NP6-324-CD | 13220 | Real-Time Price Adders for 15-Minute Settlement Interval
np6-326-cd | 21115 | Real-Time Price for SOG
np6-905-cd | 12301 | Settlement Point Prices at Resource Nodes, Hubs and Load Zones
eia-930-cd | 13457 | Hourly Balancing Authority Operations Report
sys-608-cd | 12354 | SCED Resource Shift Factors
np6-607-cd | 16013 | SCED Settlement Point Shift Factors
np6-86-cd | 12302 | SCED Shadow Prices and Binding Transmission Constraints
np6-235-cd | 12340 | System-Wide Demand
np6-346-cd | 14836 | Actual System Load by Forecast Zone
np6-344-cd | 15954 | Actual System Load by Study Area
np6-345-cd | 13101 | Actual System Load by Weather Zone
np5-757-cd | 13080 | Deselected Daily RUC Recommendations
The reports listed here, for the first 12/5 posting interval, will be EXPIRED due to inaccurate data.

## Slide 10: RTC Cutover Information: Stabilization Issues
The following products are being tracked for stabilization issues:

## Slide 11: RTCBTF Discussion: