## Slide 1: DRRS Proposed Timeline (NPRRs 1309/1310)
Workshop 1 – Jan 7
ERCOT review of NPRRs 1309 and 1310
Workshop 2 – Feb 4
Review of ERCOT/Stakeholder comments
Board Update – Feb 9-10
Workshop 3- March 4
Workshop 4 – April 1
Finalize NPRR schedule - determine whether extra PRS/TAC meetings will be needed
PRS Meeting – April 15
Board Update – April 20-21
Special TAC Meeting – May 6
May change to Workshop if PRS does not vote at April 15 meeting
PRS Meeting – May 13th
Possible Vote on NPRR1309 or NPRR1310
TAC Meeting – May 20th
Board Meeting – June 1-2
Assign “Homework” to ERCOT/Stakeholders for review at Workshop 2
Direction for TAC Update to February Board
Determine whether extra voting meetings will be needed and schedule
  Board Vote on NPRR1309 or NPRR1310
  Final Meeting for PRS to Vote on NPRR1309 or NPRR1310
  Final Meeting for TAC to Vote on NPRR1309 or NPRR1310
  Review of ERCOT/Stakeholder comments