## Slide 1
Flight Testing Update
David Michelsen
Manager Retail Operations
Retail Market Subcommittee
01/13/2025

## Slide 2: Flight 1025 Details
7 New CRs have successfully tested in Flight 1025 including 4 DUNS+4 CRs
30 Existing CRs have successfully tested in Flight 1025
Of the 30 Existing CRs, 30 tested for Service Provider Change and 5 added Territories
1 Existing CR withdrew their registration from Flight 1025
One of the New CRs had one outstanding banking transaction with one TDSP. The TDSP continued working with the CR and the task was completed on 11/6/25.
Retail Market Subcommittee
01/13/26

## Slide 3: Flight 0226 Preview
Market Notice for Flight 0226 was sent on 12/03/25
Market Notice first reminder for Flight 0226 was sent on 01/07/26
Market Notice final reminder for Flight 0226 will be sent on 01/21/26
Flight 0226 application deadline is 01/14/26
Flight 0226 signup deadline is 01/28/26
Connectivity testing begins on 02/04/26
Day 1 transactions begin on 02/23/26
Flight 0226 is scheduled to complete on 03/06/26
Contingency period is scheduled to conclude 03/13/26
Retail Market Subcommittee
01/13/26