## Slide 1: Large Load Batch Study Process
TAC
January 21, 2026

## Slide 2: Batch Study Process Overview
RPG Project 1
Batch Study
Developer Request
Developer Commitment
Planning Forecast
RPG Project 2
Load Limits and Required Projects
At the December 18, 2025 PUCT Open Meeting, ERCOT explained the need to replace the individualized Large Load Interconnection (LLI) study approach in PGRR115 with a Batch Study process:
  Currently, LLI requests are studied individually
  This approach has resulted in the need to restudy some LLI requests one or more times due to outdated study assumptions as other requests in the area meet milestones to be considered “must-study” loads. Restudies have created uncertainty and risk for developers and have slowed the process to interconnect
The outcomes of a Batch Study will be:
  The amount of requested Load that can reliably be served by year for each LLI request; and
  The transmission upgrades needed to serve the full requested Load level
The Batch Study process is envisioned to be ongoing, but a “Batch Zero Study” will likely be necessary to transition from the current process. To facilitate this study, ERCOT will need to categorize current LLI requests as one of the following:
  LLI requests that do not need to be restudied;
  LLI requests that have attained certain milestones but are subject to restudy and will be restudied in Batch Zero; or
  LLI requests that are early in the process and will be studied in a subsequent Batch

## Slide 3: Batch Study Stakeholder Engagement Plan
Meeting | Discussion Purpose
January 22 LLWG | Overview
January 29 PUC Open Meeting | Update
February 3 Workshop | Draft Framework
February 6 PUCT Open Meeting | Update
February 9-10 Board of Directors | Overview
February 12 Workshop (tentative) | Final Draft Framework
February 20 PUCT Open Meeting | Proposed Batch Study Framework
ERCOT has engaged the McKinsey Group to help gather stakeholder feedback on the challenges with the current process and solicit input regarding a future Batch Study process
For at least the Batch Zero study, ERCOT would anticipate requesting from the PUCT a good cause exception from PGRR115 in order to conduct the studies
For ongoing the Batch Study process, ERCOT will work with PUCT Staff to determine whether any enabling language is necessary as part of PUCT Project No. 58481, Large Load Interconnection Standards under PURA 37.0561. Further, after gathering any feedback from PUCT, ERCOT would expect to file revision requests to codify the Batch Study process

## Slide 4
Questions?