## Slide 1
Project Update
January 14, 2026
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  2025 Release Targets
  2026 Release Targets
  Priority/Rank Recommendations for Revision Requests with Impacts
    PGRR127 – Addition of Proposed Generation to the Planning Models
  Technology Working Group (TWG)
    Next meeting is 1/22/2026
  Prioritization Update
    Status Notes
    2026 Project Planning
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: 2025 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/30 | February 2/27 | March 3/27 | April 4/24 | May 5/29 | June 6/26
NPRR945 NPRR1219 | NPRR1254 RTC+B Market Trials Sandbox Deployed | NPRR1145 | RTC+B Market Trials begin on 5/5/2025 | NPRR1253 | 
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R4
R5
R6
July 7/31 | August 8/28 | September 9/25 | October 10/23 |  | December 12/18
NPRR1234(a) |  |  | NOGRR245 |  | PGRR091 NPRR1234(b) PGRR115(a) SCR828
R7
R8
R10
R11
R3
R9
NPRR1007-1013
RTC+B Market Trials
Closed-loop SCED/LFC
Day-Ahead Market
Open-loop RTC SCED
QSE Telemetry Tests
RTC QSE Submission Testing
RTC QSE Telemetry Check-out
RTC+B Stabilization
RTC+B
12/5
NPRR963(a)
NPRR1000
NPRR1014
NPRR1029(a)
NPRR1054
NPRR1058
NPRR1172
NPRR1204
NPRR1216(a)
NPRR1236
NPRR1245
NPRR1246
NPRR1268
NPRR1269
NPRR1270
NPRR1282
NOGRR211
NOGRR268
NOGRR277
OBDRR020
OBDRR052
PGRR118
NPRR963(a) – Portion of NPRR
NPRR1029(a) – Market suspension of ESRs portion
NPRR1216(a) – Invoice workaround
NPRR1234(a) – Section 3.10.7.2, paragraphs 14-19
NPRR1234(b) – See market notice
PGRR115(a) – All except Sect. 5.2.10
ü
ü
1/1
3/1
ü
3/7
ü
ü
ü
RTC+B Stabilization begins
7/21
ü
ü
ü
ü
ü
ü
ü

## Slide 4: 2026 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/28-1/29 | February 2/25-2/26 | March 3/25-3/26 | April 4/29-4/30 | May 5/27-5/28 | June 6/24-6/25
NPRR1234(c) PGRR131 | NPRR1299 |  |  |  | SCR820
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R4
R5
R6
July 7/29-7/30 | August 8/26-8/27 | September 9/30-10/1 | October 10/28-10/29 | December 12/16-12/17 | 
R7
R8
R10
R11
R3
R9
E
RTC+B Stabilization
E
E
NS
NPRR1234(c) – RIOO changes for End-Use
Industry Classification to Loads
Numerous projects are initiating in 2026
and will eventually have go-live targets

## Slide 5: Priority / Rank Recommendations for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1214 | Reliability Deployment Price Adder Fix to Provide Locational Price Signals, Reduce Uplift and Risk | TBD | TBD | $800k-$1.2M, 12-18 months Impacted Systems: MMS, Settlements, Reporting ERCOT requests a continued table at PRS due to RTC+B resource constraints and design concerns
PGRR127 | Addition of Proposed Generation to the Planning Models | 2026 | 430 | $20k-$4k, 3-4 months Impacted System: RIOO Regulatory
Recommendations for…
PPL Rank Information
Next 2025 Rank in Business Strategy = 4580 Next 2028 Rank in Business Strategy = 5110
Next 2026 Rank in Business Strategy = 4820 Next 2029 Rank in Business Strategy = 5300
Next 2027 Rank in Business Strategy = 4910 Next Rank in Regulatory = 430

## Slide 6: Technology Working Group (TWG)
Agenda for TWG meeting held on 12/18/2025:
Next TWG scheduled for 1/xx/2026

## Slide 7: 2026 Project Planning
ERCOT understands that Market Participants need lead time to implement changes in their systems for many Revision Requests
Approved Revision Request Project Starts
  NPRR936 – CRR Account Holder Limits
  NPRR1188 – Implement Nodal Dispatch and Energy Settlement for Controllable Load Resources
  NPRR1238 – Voluntary Registration of Loads with Curtailable Load Capabilities
  NPRR1244 – Clarification of CLR Primary Frequency Response Responsibilities
  NPRR1277 – Revisions to EAL Formula
  NPRR1281 – Improvements to Alternate FFSS Resource Designation
  NPRR1288 – Remove Multiple Month Transactions in CRR Auctions
Revision Request Projects with Potential for 2026 Implementation
  NPRR1198 – Congestion Mitigation Using Topology Reconfigurations
  NPRR1201 – Limitations on Resettlement Timeline & Default Uplift Exposure Adj
  NPRR1290 Phase 2 – Gap Resolutions and Clarifications for RTC+B
  SCR818 Phase 2 – Changes to Incorporate GIC Modeling Data into Existing Modeling Applications
  SCR829 – API for the NDCRC Application
  SCR831 – Short Circuit Model Integration
Other priority Review Request projects may start in 2026 with a future year Go-Live
  DRRS (NPRR1309, NPRR1310), Residential Demand, Firming
Green Text: Deemed “High Priority” at Prioritization Workshop