## Slide 1
RTC+B Update
Stabilization and Lessons Learned
TWG
January 22, 2026

## Slide 2: Outline
RTC+B Stabilization and Upcoming releases/discussions
  Emergency/Off-cycle releases
  2026 R1 release
  Future discussions/releases
RTC+B Lessons Learned

## Slide 3: RTC+B – Stabilization and Upcoming Releases
December emergency/off-cycle releases
1. Software Issue Impacting certain Ancillary Service Trades considerations
    Emergency fix deployed to Production on December 10, 2025 10 AM
    Fixed the AS trades data post-process for the impacted ODs 12/5/2025 – 12/10/2025
    Reran the RUC capacity short calculations for the impacted RUC runs with commitments for OD 12/8/2025
    Market notice with details - M-A121225-01 Software Issue Identified Impacting Ancillary Service Trades
2. December off-cycle release
    MP facing - NCLR COP capability validation rule updated for RRS and ECRS
    Fix deployed to Production on December 17, 2025, 3:30 PM

## Slide 4: RTC+B – Stabilization and Upcoming Releases
3. SCED optimization parameters tuning in the Stabilization Period
  RTC SCED is modeled as a Mixed-Integer Quadratic Programming problem and solved using IBM CPLEX optimization solver
  Based on the analysis of SCED results, the CPLEX solver parameters were adjusted further to enhance the optimality of the SCED solution
    Relative MIP Gap tolerance was changed from “1e-4” to “1e-7”
    The CPLEX solver algorithm was switched from Barrier (Interior Point method) to Primal Simplex.
  Further details can be found in the RTCBTF presentation – Tuning of Optimization Solver Configurations for SCED under RTC+B
  The changes were deployed to Production on January 8, 2026, 1:30 PM

## Slide 5: RTC+B – Stabilization and Upcoming Releases
2026 R1 release
  MMS submission related fixes as discussed in previous TWG meeting
    R1 Release Market Submissions Changes
  MOTE deployment completed on January 16, 2026
  Production deployment planned for January 29, 2026
    M-C011626-01 Implementation of Market-facing changes for January 29, 2026

## Slide 6: RTC+B Next Steps
RTC+B Task Force to continue to prioritize pending discussions
  Inventory of RTCBTF Issues to Consider in 2026
NPRR1290 Phase 2 implementation
  Change to MMS SCED Electrical Bus LMP capping logic
  1 report impact – ERCOT to publish both the capped and uncapped Electrical Bus LMP
  Timelines and XSD changes details at next TWG Meeting – Feb 19, 2026.
Deferred/pending fixes – remaining issues that will be fixed over the next few releases (2026 R2 to R4).
  1 known MP impact fix: MMS UI Generator Parameter submission checks for min/max SOC and roundtrip efficiency for non-ESR resources. QSE should be able to submit/update generator parameters with SOC and roundtrip efficiency values being null/empty for non-ESR resources.

## Slide 7: RTC+B Lessons Learned
ERCOT is in the process of gathering RTC+B project Lessons Learned
For example, early and continuous QSE/TSP and their vendor outreach will be improved upon and carried into other projects.
  TWG workshops in 2024 to discuss design/implementation details along with training videos/material published online helped with QSE/vendor engagement in preparation for an earlier than initially planned RTC+B go-live date.
  Open Loop and Closed Loop testing takeaways
    Opening the market trials environment for vendor testing helped identify issues early, and allowed for early resolution of access related issues
    Requesting Production quality telemetry and submissions helped identify issues on both the vendor and ERCOT side related to systems set up and data validation rules
    Extended period of open loop testing with apps running helped ERCOT evaluate system performance and results with production quality telemetry and submission data
We encourage MPs to provide additional lessons learned and feedback to following contacts:
    Sreenivas.Badri@ercot.com
    Sruthi.Hariharan@ercot.com