## Sheet1
Item | Description | Initial Assignment Thoughts | Initial Priority Thoughts | Initial Timing Thoughts | Additional ERCOT Notes
1 | ASDC review:
1a | General performance of curves and impacts on prices | WMS/TAC | High | On-going throughout the year | Although a high priority, analysis expected be on-going throughout the year. Likely part of 2026 biennial "ORDC" report
1b | Evaluating the impacts of the ASDC floors | WMS/TAC with assignment to WMWG should a deeper dive be desired/warranted | High | On-going throughout the year | Although a high priority, analysis expected be on-going throughout the year. Likely part of 2026 biennial "ORDC" report
2 | Evaluating the impacts of the Ancillary Service proxy offer floor values, including how frequently the proxy block comes into play | WMS/TAC with assignment to WMWG should a deeper dive be desired/warranted | High | On-going throughout the year | Although a high priority, analysis expected be on-going throughout the year. Likely part of 2026 biennial "ORDC" report
3 | Analyzing the RUC Ancillary Service deployment factors | CMWG as part of on-going analysis of RUC drivers | Medium | Include as part of existing RUC discussions | None
4 | Analyzing the Real-Time Ancillary Service duration parameters | TAC/WMS/ROS | High | Discussion along with 2027 Ancillary Service methodolgy discussions | High with link to DRRS and 2027 Ancillary Service methodology discussions
5 | Impacts of capping System Lambda and evaluating alternatives to what is including in NPRR1290 | WMS/WMWG | Medium | After other related discussions on this list (e.g., ASDCs and Real-Time offer caps) | Likely to be affected by other discussions on this list (e.g., ASDCs and Real-Time offer caps). Considering waiting for those other topics to at least start
6 | Discussion regarding the $2,000/MWh offer caps for Real-Time, either exclusively for ESRs or more generally | See ERCOT note | See ERCOT note | See ERCOT note | Expected to be discussed at PUCT, as per 25.509(d). Discussions should happen there prior to further ERCOT stakeholder meeting activity
7 | Evaluating if there are any concerns with Ancillary Service deliverability | CMWG | Medium | Later part of 2026 | Unless issues are identified, wait until more RTC+B history is collected
8 | Investigate the impact of not having an indifference payment for the post-RTC, pre-1214 RDPA process | WMWG | Medium | Later part of 2026 | Unless issues are identified, wait until more RTC+B history is collected
9 | Evaluating the transmission constraint shadow price caps and how they interact with the ASDCs and PBPP | CMWG | Low | After other related discussions on this list (e.g., ASDCs and Real-Time offer caps) | No issues have yet been identified and other discussions affecting this topic are on-going or expected
10 | Updates to the Off-Line Non-Spin Deployment and Recall procedure | WMWG | Medium | Already on-going | Revision request language already being developed by ERCOT staff. Language anticipated being avalable in 2026 Q1.
11 | Discussions with stakeholders to identify potential gaps in reporting post-RTC+B implementation, specifically related to Real-Time Ancillary Service (e.g., aggregate awards or additional elements for extracts) | WMWG | Medium | As soon as stakeholders like | Although a medium priority, discussions can begin immediately. Stakeholder discussion on this topic not expected be a signficant effort for ERCOT staff (e.g., conflict with other efforts).