## Slide 1
Project Prioritization Update
Technical Advisory Committee (TAC)
Troy Anderson
ERCOT Portfolio Management
February 25, 2026

## Slide 2: Aging Revision Request Project Status
Prioritization Workshop held in August 2025 to set priorities for 2026
10 Revision Request projects were deemed “High Priority”
Status | High Priority Revision Request Projects
Complete | None
In-Flight | NPRR1188 – Implement Nodal Dispatch and Energy Settlement for CLRs NPRR1234 – Interconnection Requirements for Large Loads and Modeling Standards for Loads >=25MW NPRR1238 – Registration of Loads with Curtailable Load Capabilities NPRR1244 – Clarification of CLR Primary Frequency Response Responsibilities NPRR1277 – Revisions to EAL Formula (scheduled to go-live on 3/2/2027) NPRR1281 – Improvements to Alternate FFSS Resource Designation
Approved to Start | NPRR1198 – Congestion Mitigation Using Topology Reconfigurations (April 2026 start)
Pending RDPA Analysis | NPRR1091 – Changes to Address Market Impacts of Additional Non-Spin Procurement
TBD | NPRR1004 – Load Distribution Factor Process Update
Workaround in Place | NPRR1216 – Implementation of Emergency Pricing Program

## Slide 3: Aging Revision Request Project Status
“Medium Priority” Revision Request projects in progress
Status | Revision Request
In-Flight | NOGRR226 – Addition of Supplemental UFLS Stages NOGRR247 – Change UFLS Stages and Load Relief Amounts NPRR936 – CRR Account Holder Limits
Approved to Start | SCR818 Ph2 – Changes to Incorporate GIC Modeling Data into Existing Modeling Applications (April 2026 start)
Pending Start Approval | NPRR1201 – Limitations on Resettlement Timeline and Default Uplift Exposure Adjustments
Other Revision Request projects in progress
Status | Revision Request
In-Flight | NOGRR245 – Inverter-Based Resource (IBR) Ride-Through Requirements NPRR1288 – Remove Multiple Month Transactions in CRR Auctions NPRR1303 – Modernize Submission of Declarations of Natural Gas Pipeline Coordination SCR820 – Operator Real-Time Messaging During Emergency
Approved to Start | SCR831 – Short Circuit Model Integration (April 2026 start – bundled with SCR818 Phase 2)

## Slide 4: Aging Revision Request Project History
Key Takeaway: Aging backlog has remained relatively steady since 2021
Population: Aging Revision Requests as of 8/2020 plus any new approved RRs with related projects since 8/2020

## Slide 5: Aging Revision Request Project History
Key Takeaway: “Not Started” and “On Hold” items will be discussed at PRS in April
Current “Not Started” Details
6 approved in the last 6 months
26 “Medium Priority”
8 deemed “No Action” at this time
5 candidates for removal
4 “High Priority” (see slide 2)
2 approved to start

## Slide 6: Appendix
Additional slides from PRS project update

## Slide 7: 2026 Project Planning
ERCOT understands that Market Participants need lead time to implement changes in their systems for many Revision Requests
Approved Revision Request Project Starts
  NPRR936 – CRR Account Holder Limits
  NPRR1188 – Implement Nodal Dispatch and Energy Settlement for Controllable Load Resources
  NPRR1238 – Voluntary Registration of Loads with Curtailable Load Capabilities
  NPRR1244 – Clarification of CLR Primary Frequency Response Responsibilities
  NPRR1277 – Revisions to EAL Formula
  NPRR1281 – Improvements to Alternate FFSS Resource Designation
  NPRR1288 – Remove Multiple Month Transactions in CRR Auctions
  NPRR1290 Phase 2 – Gap Resolutions and Clarifications for RTC+B
Revision Request Projects with Potential for 2026 Implementation
  NPRR1198 – Congestion Mitigation Using Topology Reconfigurations
  NPRR1201 – Limitations on Resettlement Timeline & Default Uplift Exposure Adj
  SCR818 Phase 2 – Changes to Incorporate GIC Modeling Data into Existing Modeling Applications
  SCR829 – API for the NDCRC Application
  SCR831 – Short Circuit Model Integration
Other priority Review Request projects may start in 2026 with a future year Go-Live
  DRRS (NPRR1309, NPRR1310), Residential Demand (NPRR1296), Firming
Green Text: Deemed “High Priority” at 2025 Prioritization Workshop

## Slide 8: Select Project Updates
NPRR1290 Phase 2 – Gap Resolutions and Clarifications for RTC+B
  The team was ready to kick this off as part of RTC+B stabilization
  Discovered an issue with the language – ERCOT will file an urgent NPRR to resolve
  Path forward is now TBD – may require a stand-alone project
NPRR1198 – Congestion Mitigation Using Topology Reconfigurations
  Targeting April 2026 start – expecting late Q3 / early Q4 go-live
  This is one of the “high priority” items identified in last year’s prioritization workshop
NPRR1201 – Limitations on Resettlement Timeline & Default Uplift Exposure Adjustments
  Targeting July 2026 start with go-live in late 2026
NPRR1238 – Voluntary Registration of Loads with Curtailable Load Capabilities
  Part of Large Load Curtailment Manager project (Initiated in February 2026)
  Targeting partial implementation by summer 2026 with full scope delivered by end of 2026
  ERCOT expecting to file an NPRR to codify SB6-related curtailments in the Protocols
Targeting April 2026 for the next prioritization discussion at PRS
  Plans for 2026 will largely be in place (and in motion) by that time