## Slide 1
Resource Integration Topics
Jenifer Fernandes
ERCOT
Resource Integration Working Group
February 23rd, 2026

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.3.5
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.3.5, Quarterly Stability Assessment
Issue’s seen in previous QSA’s
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic/PSCAD Model Review
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline
PSSE Model Quality Test Required
PSCAD Model Quality Test, Unit Model Validation and Template is required. PSCAD template is required starting August 1st QSA.
TSAT Model Required – If PSSE model is UDM, then TSAT model should be UDM and should include MQT

## Slide 4: QSA 45 day deadline
FIS studies finalized and posted in RIOO-IS 45 days prior to quarterly stability assessment deadline.
Dynamic models (PSEE, PSCAD, TSAT (UDM)) and MQT report submitted in RIOO-IS.
From Planning guide Section 5.3.5 (2): Last Day for an IE to meet prerequisites as listed in paragraph (4) below | 45 day deadline
Prior August 1 | June 17
Prior November 1 | September 17
Prior February 1 | December 18
Prior May 1 | March 17

## Slide 5: Active RR’s
PGRR132: Update to Standard Generation Interconnection Agreement (SGIA) Requirement
NPRR1272: Voltage Support at Private Use Networks
PGRR124: ESR Maintenance Exception to Modifications

## Slide 6: Generation Interconnection Requests
2,008 active generation interconnection requests totaling 450 GW as of January 31st, 2026 (Solar 162 GW, Wind 48 GW, Gas 57 GW, Battery 179 GW / 375 GWh, and Other 4 GW) (Excludes capacity associated with projects designated as Inactive per Planning Guide Section 5.7.6)
Chart: Large Generator Monthly Capacity by GIM Milestone plus Project Count, 13-Month Rolling Basis
| Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26
# Signed Interconnect Agreement | 445 | 460 | 491 | 507 | 511 | 510 | 517 | 535 | 532 | 530 | 528 | 539 | 574
# Completed Full Study | 133 | 121 | 112 | 105 | 106 | 114 | 119 | 111 | 117 | 116 | 122 | 121 | 121
# in Full Study | 1163 | 1200 | 1207 | 1212 | 1223 | 1237 | 1242 | 1201 | 1196 | 1164 | 1159 | 1150 | 1136
# Screening Study Complete | 119 | 113 | 113 | 102 | 89 | 88 | 86 | 82 | 94 | 94 | 91 | 90 | 79
# Initial Screening study | 16 | 19 | 19 | 29 | 21 | 27 | 27 | 33 | 20 | 11 | 9 | 5 | 17
GW Capacity | 388.6158 | 399.0073 | 404.457 | 410.8736 | 408.9081 | 419.6478 | 432.1004 | 427.4415 | 431.1647 | 431.2039 | 434.4146 | 440.2987 | 449.5541

## Slide 7: Generation Interconnection Requests
Small Gen- 31 projects Not Model Ready, 50 projects Model Ready
Chart: Small Generator Monthly Capacity by GIM Milestone plus Project Count, 13-Month Rolling Basis
| Nov-24 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25
# Not Model Ready | 33 | 32 | 30 | 24 | 26 | 32 | 31 | 28 | 23 | 23 | 29 | 28 | 28
# Model Ready | 48 | 46 | 46 | 50 | 50 | 50 | 50 | 50 | 52 | 56 | 54 | 56 | 57
MW Capacity | 755.62 | 726.03 | 701.78 | 682.08 | 706.9 | 767.07 | 762.84 | 733.06 | 703.44 | 741.48 | 770.99 | 780.98 | 790.97
Chart: Small Generator Monthly Capacity by GIM Milestone plus Project Count, 13-Month Rolling Basis
| Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26
# Not Model Ready | 30 | 24 | 26 | 32 | 31 | 28 | 23 | 23 | 29 | 28 | 28 | 25 | 31
# Model Ready | 46 | 50 | 50 | 50 | 50 | 50 | 52 | 56 | 54 | 56 | 57 | 54 | 50
MW Capacity | 701.78 | 682.08 | 706.9 | 767.07 | 762.84 | 733.06 | 703.44 | 741.48 | 770.99 | 780.98 | 790.97 | 732.45 | 752.12

## Slide 8: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department
Mailing List
  RESOURCE_INTEGRATION@LISTS.ERCOT.COM

## Slide 9: Questions?
Thank you!