## Slide 1
Market Participant Service Portal with new Identity & Access Management Method ERCOT Staff Protocol Revision Subcommittee 3/11/2026

## Slide 2: MP Service Portal (MPSP) Scope
MP & Client Services Communication:
Contact Client Services
Receive notices and requests for information
Request Reports
Report issues (IT, Grid, Market)
Forms Submission:
LSIPA (Section 23 Form S)
Notice of Change of Information (NCI) (section 23 Form E)
Weatherization Portal:
Move current portal into the MPSP
Identity & Access Management:
Implement new future ready B2B tooling for user logon with MFA
MPSP Objectives
Reduce manual process
Reduce work management through emails/phone calls
Centralize submission, access, and tracking for requests and forms
Automate data population and data validation
Adopt future ready modern B2B tooling for user logon with MFA
What does this mean for you?
Business to Business (B2B) Tooling: Includes Identity Provider (IdP), Access Management (AM), Identity Governance and Administration (IGA), Multi Factor Authentication (MFA) for Market Participants (MP) and other entities who work with ERCOT
2/19/26 TWG: MPSP Updates https://www.ercot.com/files/docs/2026/02/19/ERCOT-TWG-2026-02-19-Market-Participant-Service-Portal-Updates.pptx

## Slide 3: MP Timeline
Q1 2026
Q2 2026
Q3 2026
Q4 2026
2027-2028
IAM2 RFP for B2B Tooling
Data alignment with MPSP and NPRRs
Stakeholder Education and Hands On Training
Targeted October Release
Share initial plans for 2027/2028 B2B integration waves
October Go-Live Check-Point
Stabilization Period
Internal ERCOT Planning for B2B tool integration with other market-facing applications
2026
  Q1: Deloitte selected as Implementation Partner and onboarded - completed
  Q1: IAM Modernization new B2B tooling vendor selection in progress
  Q2: ERCOT testing MPSP with B2B tooling, confirm release targets
  Q2: Target Board approval of Revision Requests
  Q3: Align new data with MPSP and NPRRs, stakeholder training
  Q4: Target Release in October with ongoing stabilization support and additional education
  Q4: Apply lessons into planning for additional forms (MPSP) & B2B tooling waves (other applications)
We are here
Implementation Partner selected
June Board Meeting
Updates will continue to be provided to TWG.

## Slide 4: B2B Plan
Custom MFA (Client Certificate + password) GridGeo
Auth0 MFA via SSL proxy per individual application, i.e. RIOO, GINR, REC, FlighTrak
Client certificates with SAML token (i.e. current Weatherization portal)
NEW B2B TOOLING
MPSP Go-Live (Oct 2026)
First use of new B2B tooling
2027/2028
Full adoption of new B2B tooling
We are here
2027: Begin waves to transition applications to new B2B tooling
Share Wave Plan
B2B Tooling Starts with MPSP, followed by implementation waves starting in 2027
Digital Certificates
Key Takeaway: The MPSP is the only application that will implement the new B2B tooling in 2026.

## Slide 5: PRS Related Revision Requests
MP Service Portal | Status | Details
NPRR1302, Addition of a Market Participant Service Portal within the MIS Certified Area and Revision of Forms | Request PRS Approval | Introduces a new portal for MPs designed to automate interactions between ERCOT and MPs, currently managed via email communications and manual processes Future form submissions will go through the Portal (MPSP) rather than through email Establishes the need for a secondary email address that will feed into the new B2B tooling
NPRR1306, Removal of Digital Certificate References for Market Participants with ERCOT MIS Access | Request PRS Approval | Replaces the term “Digital Certificates” throughout the Protocols with better streamlined modern technology for both the individual Market Participant and the User Security Administrator (USA) Adoption will allow ERCOT to implement modern MFA authentication methods for logon and authentication to ERCOT’s systems by B2B users
Approvals of the NPRRs by June Board meeting support MPSP go-live in October.