## Slide 1: PRS update on Large Load Interconnection Batch Study Workshops
March 11th, 2026
Matt Mereness

## Slide 2: The batch study process increases outcome certainty and transparency while limiting restudy risk
…to the new batch study process
ERCOT action
Non-ERCOT action
Communication point
Dev. submits project to TSP
Single study
Single study (invalidating prior results)
Initial approval
Single study (invalidating prior results)
Initial approval
RPG, QSA
Energization
Dev. submits project to TSP
Dev. submits project to TSP
Dev. submits project to TSP
RPG, QSA
Energization
Batch study: ERCOT compiles applications, studies together as a batch, and allocates load
C
From the existing single study process…
A
Frequent restudies required If another project impacts the same transmission zone, all previous studies are invalidated and impacted projects which haven’t yet energized must be restudied
B
Restudy loop In the absence of capacity reservation, projects can be repeatedly pulled into restudies as new requests enter the system, delaying approvals and potentially extending timelines by years
C
Batching process Every ~6 months, all submitted requests are clustered and studied together; allocated capacity coming out of the study is “reserved” to prevent restudies
Transparent communications Along with the new batch study process, ERCOT is redesigning the study communication process to have clearly defined touchpoints and transparent information handovers
B
Source: ERCOT discussions
Dev. submits project to TSP
Dev. submits project to TSP
Single study (invalidating prior results)
Single study (invalidating prior results)
Initial approval
Initial approval
Initial approval
Dev. submits project to TSP
Dev. submits project to TSP
Dev. submits project to TSP
Dev. submits project to TSP
A
A
A
A

## Slide 3: Insights from a multi-channel stakeholder engagement effort enabled a comprehensive view of stakeholder alignment and open questions
2/3 LLI Batch Study Workshop
Written public comments
Stakeholder survey
109
Unique respondents
46
Hours spent collecting stakeholder feedback
~100
Questions received
120+
Commentary pages submitted
Stakeholder interviews (60)
Areas of strong stakeholder alignment
Key open questions requiring resolution
  How CLR/BYOG/co-located generation should be treated within the batch study
4
Source: Batch Study Process for Large Load Interconnections Workshop, ERCOT Large Load Interconnection Batch Study Process Stakeholder Survey, public written comments, stakeholder interviews
  A ~6-month batch study cadence is viewed as good balance between speed and analytical rigor
1
  More proactive, structured, and transparent communication is essential
2
  Batch Zero eligibility should also consider operational readiness and TSP submission date along with financial commitment
3
  How ERCOT will ensure consistency in timelines/study assumptions across T(D)SPs
5
  How Batch Zero will link directly to actionable RPG transmission approvals
6

## Slide 4: Batch Zero revision request timeline
Forums
Workshops and working groups
PRS (Protocols Review Subcommittee)
ROS (Reliability and Operations Subcommittee)
TAC
ERCOT Board
2026
Q1
Q2
Q3
Feb
Mar
Apr
May
Jun
Jul
Workshop #2 Feb 12
Workshop #4 Mar 10
Workshop #5 Mar 24
Workshop #6 Mar 30
PRS Update 3/11
ROS Update 3/5
ROS Vote 5/7
Board Vote 6/1
3/4 ERCOT files Batch Zero Revision Request(s)
8/1 Target effective date of protocols
Objective
Align stakeholders on direction/scope following Commission decision
Define the scope, boundaries, and intended role of Batch Zero
Preview structure/governing concepts of Batch Zero NPRR before filing
Confirm proposed protocol changes are ready for governance review
Endorse NPRR 1325 for advancement to TAC
File PGRR145 for Workshops and ROS review
Endorse PGRR145 for advancement to TAC
Review/endorse combined NPRR/PGRR package for Board approval
Consideration Batch Zero NPRR/PGRR
LLWG Feb 19
Workshop #3 Feb 26
TAC Vote 5/19-20
Close outstanding design and drafting issues, incorporate vetted stakeholder feedback, and finalize Revision Request language for committee approval
Target Board approval date
Board Meeting 4/20
Regular PRS 4/15
ROS Update 4/2
Monthly TAC updates
Workshop #7 Apr 9
Note that TAC leadership is involved in considering options to ensure successful review and approval
Special PRS 4/22
Regular TAC 4/29
Special TAC 5/13
PRS Vote 5/6
Monthly LLWG updates
Apr (TBD) ERCOT files CLR/BYOG Revision Request(s)

## Slide 5: March 10 Workshop #4 summary
1
Timeline and governance recap
Update on timeline and key workshop dates
Outline PRS/ROS/TAC pathways to June Board with key submission dates
2
Stakeholder Survey Feedback and FAQ
Review FAQs and common stakeholder questions, including ERCOT responses
Review results from the stakeholder feedback survey and key themes emerging
3
Batch Zero PGRR/NPRR Walk-though
Review February 26 slides and highlight key updates since the last version
Walk through proposed PGRR language and relevant sections for alignment
4
Market Comments filed on NPRR/PGRR (if any)
Open discussion: stakeholder comments, initial requests, and areas requiring refinement after filing
5
Discussion of CLR and BYOG concepts
Resume discussion on treatment of CLR and BYOG (note that LLWG on Mar 13th will focus on these topics)
6
Q&A
Open forum for Batch Zero concerns, comments, and suggestions