## Slide 1: ERCOT LLWG - Data Center Development Timeline
March 2026
Bharath Ravulapati - Director, Grid Strategy and Execution
Crusoe

## Slide 2: Data Center Development Executive Summary
LOI and lease negotiation, tenant requirements and fit-out, SLA agreements, move-in readiness, hyperscaler vs. colocation considerations
Data Center - Foundation and structural work, MEP installation, raised floor/white space buildout, cabling infrastructure, commissioning milestones
Project Substation - Substation construction timeline, utility coordination, transmission line work, energization schedule, interconnection agreements
Design development, engineering studies, contractor procurement, permitting submissions, geotechnical/civil surveys, cost estimating and value engineering
Land
Local Outreach
Pre-Construction
Site selection, due diligence, acquisition, zoning/entitlements, environmental assessments, utility access evaluation
Community engagement, municipal relationships, public hearings, economic impact messaging, permitting coordination with local authorities
Long Lead Equipment
Capital stack structure, debt/equity timeline, lender due diligence, financial close milestones, draw schedules tied to construction progress
Construction
Financing
Identification of critical path equipment (transformers, switchgear, UPS, generators), procurement strategy, vendor lead time management, factory acceptance testing
Grid disturbance protection requirements, low/high voltage ride-through compliance, utility interconnection standards (IEEE 1547, NERC), inverter and UPS settings, testing and validation during commissioning, ensuring uptime during grid fluctuations
GPUs
VRT
GPU procurement strategy, lead times and allocation, integration with compute infrastructure, cooling requirements for high-density racks, delivery and deployment phasing
Tenant

## Slide 3: Data Center Development - Master Timeline
Months | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Land |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Financing |  |  |  |  |  |  | Financing closed |  |  |  |  |  |  |  |  |  |  |  | 
Local Outreach |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-Con |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LLE |  |  |  |  |  |  | Procure LLE |  |  |  |  |  |  |  |  |  |  |  | 
DC Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Sub Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tenant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GPU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
VRT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
VRT Commissioning
Sub Energization
DD & option to buy, Secure Mineral Rights, Secure Mineral Rights, Geotech, Secure Easements, Secure Land
VRT Testing
VRT Commissioning
GPU Testing
GPU Integration
Procure GPUs
Lease signing
Lease negotiation
Sign LOI
Substation Construction
Factory Testing
DC Design
Sub Design
Select Contractor
Present to City Council
ERCOT Approval
Financing
Engage local planners
Procure LLE
Site Commissioning
MEP Construction
Design Racks and Cooling
Equipment Installation
Address local concerns
Energization
*Note: Timelines are illustrative, and can range between 18-24 months
Building Structure and Envelope
Site Clearing

## Slide 4: Thank you!
Q&A