## Sheet1
TDTMS Agile Enhancement List of Proposed Changes |  |  | rev 03182026
Date | System | Description of Issue /Suggestion | Submitted By | NOTES | Completed
2024-12-01 | ERCOT MIS - Find Transaction | Adding 'key dates' back which represent when the transaction was submitted | TDTMS | included in MIS Project
2024-12-01 | ERCOT MIS - Find Transaction | Providing a hyperlink to a list of reject codes | TDTMS | included in MIS Project
2024-12-01 | MarkeTrak | Addition of ESI within automated subject line of escalation email | TDTMS | Complete
2024-12-01 | MarkeTrak | alllow REPs to utilize the same Switch Hold removal reject codes as TDSPs | TDTMS | MT team will review LOE
2025-08-01 | MarkeTrak User's Guide | remove the reference to "waiting 5 days to submit" in section 4.3 - Usage & Billing - Dispute add the reference "waiting 5 days to submit" in section 4.2 Usage & Billing - Missing | Tomas Fernandez | Complete 2/23/26
2025-08-01 | MarkeTrak | Add validations to Usage & Billing - Missing submittals: invalid start/stop cycle date not scheduled | TDMTS - small group | LOE is estimated as high - project would be required
2026-02-19 | MarkeTrak | Auto assign TDU for Usage & Billing MTs | Tomas Fernandez
2026-02-19 | MarkeTrak | Label "agree" button for IAG MT from Losing REP | TDTMS