## Slide 1
Flight Testing Update
Paul Yockey
Flight Administrator
Texas SET WG Meeting
03/24/2026

## Slide 2: Flight 0226 Details
13 New CRs have successfully completed testing for Flight 0226 including 9 DUNS+4 CRs
8 Existing CRs have successfully completed testing for Flight 0226
Of the 8 Existing CRs, 7 tested for Service Provider Change and 1 added Territories
Texas Set Working Group
03/24/2026

## Slide 3: Flight 0626 Preview
Market Notice for Flight 0626 was sent on 03/18/26
Market Notice first reminder for Flight 0626 will be sent on 04/08/26
Market Notice final reminder for Flight 0626 will be sent on 04/29/26
Flight 0626 application deadline will be 04/15/26
Flight 0626 signup deadline will be 05/06/26
Connectivity testing will begin on 05/13/26
Day 1 transactions will begin on 06/08/26
Flight 0626 is scheduled to complete on 06/22/26
Contingency period is scheduled to conclude 06/26/26
Texas Set Working Group
03/24/2026