## Slide 1: Large Load Working Group March Update
Bob Wittmeyer
Chair LLWG
bob@longhornpwr.com
512 762 8895

## Slide 2: Mar 13th - LLWG Meeting
Agee Springer – ERCOT Large Load Interconnection Queue – Update - +140 GW
Bharath Ravulapati – Crusoe presented on optimistic timeline for Data Center Development
Discussion of NOGRR 282 – request for later implementation dates from DCC and TBC
Mark Henry – TRE gave an update on NERC’s activity (to be come standard update)
Discussion of CLR and Bring your own Generation
Review of LEL Frequency Limit Study – Luis Hinojosa
Discussion of PGRR 144
LL Model Quality Test – drat update to DWG - Sun Wook

## Slide 4: Data Center Development - Master Timeline
Months | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Land |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Financing |  |  |  |  |  |  | Financing closed |  |  |  |  |  |  |  |  |  |  |  | 
Local Outreach |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-Con |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LLE |  |  |  |  |  |  | Procure LLE |  |  |  |  |  |  |  |  |  |  |  | 
DC Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Sub Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tenant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GPU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
VRT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
VRT Commissioning
Sub Energization
DD & option to buy, Secure Mineral Rights, Secure Mineral Rights, Geotech, Secure Easements, Secure Land
VRT Testing
VRT Commissioning
GPU Testing
GPU Integration
Procure GPUs
Lease signing
Lease negotiation
Sign LOI
Substation Construction
Factory Testing
DC Design
Sub Design
Select Contractor
Present to City Council
ERCOT Approval
Financing
Engage local planners
Procure LLE
Site Commissioning
MEP Construction
Design Racks and Cooling
Equipment Installation
Address local concerns
Energization
*Note: Timelines are illustrative, and can range between 18-24 months
Building Structure and Envelope
Site Clearing

## Slide 5
5

## Slide 6
CLR/BYOG – Potentially feasible options exist - but time is extremely tight to have NPRR/PGRR/NOGRR in place.

## Slide 7: Modeling Challenges for Large Loads & ERCOT
Developers often do not know what the end use will be for the Large Load interconnection, today Data Centers and Hyperscalers have the $$$, tomorrow: Hydrogen? Ammonia Plants? GigaFactories?
Equipment changes as faster than your laptop computer.
ERCOT Process can take years, particularly if Transmission has to be built.
The Computer Equipment these data centers will install has not been invented yet.
The UPS Systems the integration of BTM Generation also has not been invented and won’t be until much closer to energization.
The Computers are expected to be changed out every 3-4 years
Historical Modeling approaches are not going to work
ERCOT needs assurance that the system will not crater.
Potential solution is set of phased in standards that will not require restudy and allow model updates much closer to energization. This would allow real data to be passed to ERCOT rather than outdated models that reflected something years prior.

## Slide 8: Next Meeting April 24
Expected discussion Topics
Large Load Modeling – PGRR 144
Vendor presentation on how they can do NPRR 282
Other TBD

## Slide 9
Questions