## Slide 1: Large Load Interconnection Batch Study Workshops
March 25th, 2026
TAC Update

## Slide 2: Outline
Governance: Scope and Timing
Parallel PUCT Activities
Summary of Stakeholder feedback
Options for Controllable Load Resource (CLR) and Bring your own Generation (BYOG)

## Slide 3: The batch study process increases outcome certainty and transparency while limiting restudy risk
…to the new batch study process
ERCOT action
Non-ERCOT action
Communication point
Dev. submits project to TSP
Single study
Single study (invalidating prior results)
Initial approval
Single study (invalidating prior results)
Initial approval
RPG, QSA
Energization
Dev. submits project to TSP
Dev. submits project to TSP
Dev. submits project to TSP
RPG, QSA
Energization
Batch study: ERCOT compiles applications, studies together as a batch, and allocates load
C
From the existing single study process…
A
Frequent restudies required If another project impacts the same transmission zone, all previous studies are invalidated and impacted projects which haven’t yet energized must be restudied
B
Restudy loop In the absence of capacity reservation, projects can be repeatedly pulled into restudies as new requests enter the system, delaying approvals and potentially extending timelines by years
C
Batching process Every ~6 months, all submitted requests are clustered and studied together; allocated capacity coming out of the study is “reserved” to prevent restudies
Transparent communications Along with the new batch study process, ERCOT is redesigning the study communication process to have clearly defined touchpoints and transparent information handovers
B
Source: ERCOT discussions
Dev. submits project to TSP
Dev. submits project to TSP
Single study (invalidating prior results)
Single study (invalidating prior results)
Initial approval
Initial approval
Initial approval
Dev. submits project to TSP
Dev. submits project to TSP
Dev. submits project to TSP
Dev. submits project to TSP
A
A
A
A

## Slide 4: Scope and Priorities for Workshops
March 4 filings completed for Batch Zero: ERCOT filed the Batch Zero PGRR145 and related NPRR1325 on March 4, initiating the formal governance process and aligning with the May PRS/ROS/TAC sequence and June 1 Board target reflected in the critical path timeline
  March 17 ERCOT comments filed: ERCOT submitted follow-up comments on PGRR145 (March 17) in response to stakeholder feedback on the March 4 draft, introducing targeted refinements (e.g., safe harbor for legacy LLIS, revised deadlines, alignment with PUCT PFP)
Additional filings on target (CLR and BYOG): ERCOT is advancing targeted revision requests to clarify CLR and BYOG treatment and is currently targeting an early April filing (TBD)
Out of Scope: Long-term Batch Process revisions for development of the enduring batch framework is out of scope for the current filing. ERCOT will incorporate lessons learned from Batch Zero to inform future revision requests and the design of a durable, repeatable batch study process

## Slide 5: Batch Zero Revision Request Timeline
Forums
Workshops and working groups
PRS (Protocols Review Subcommittee)
ROS (Reliability and Operations Subcommittee)
TAC
ERCOT Board
2026
Q1
Q2
Q3
Feb
Mar
Apr
May
Jun
Jul
Workshop #2 Feb 12
Workshop #4 Mar 10
Workshop #5 Mar 24
Workshop #6 Mar 30
PRS Update 3/11
ROS Update 3/5
ROS Vote 5/7
Board Vote 6/1
3/4 ERCOT files Batch Zero Revision Request(s)
8/1 Target effective date of protocols
Objective
Align stakeholders on direction/scope following Commission decision
Define the scope, boundaries, and intended role of Batch Zero
Preview structure/governing concepts of Batch Zero NPRR before filing
Confirm proposed protocol changes are ready for governance review
Endorse NPRR for advancement to TAC (contingent on technical valid.)
If accompanying PGRR filed, then ROS will be involved in review
ROS approval will be required for any PGRR(s).
Review/endorse combined NPRR/PGRR package for Board approval
Authorize implementation of Batch Zero by approval of NPRR/PGRRs
LLWG Feb 19
Workshop #3 Feb 26
TAC Vote 5/19-20
Close outstanding design and drafting issues, incorporate vetted stakeholder feedback, and finalize Revision Request language for committee approval
Target Board approval date
Board Meeting 4/20
Regular PRS 4/15
ROS Update 4/2
Monthly TAC updates
Workshop #7 Apr 9
Note that TAC/PRS/ROS leadership are actively considering options to ensure successful review and approval
Special PRS 4/22
Regular TAC 4/29
Special TAC 5/13
PRS Vote 5/6
4
Monthly LLWG updates
4/8 ERCOT files CLR/BYOG Revision Request(s)
ROS Update (special) 4/14
ROS Update (special) 4/23

## Slide 6: Revision Request Process Flow
Comments may be filed between each step of the process
Comments for NPRR1325 may be submitted using the Comments Form found here
Comments for PGRR145 may be submitted using the Comments Form found here.
NPRR Comments
PGRR Comments
Large Load Interconnection Workshops
NPRR/PGRR
Review
BOARD
PUCT
TAC
ROS
PGRR Language/IA Review
PRS
NPRR Language/IA Review

## Slide 7: Workshop #5 Discussion
Timeline and governance recap
Update on timeline and key workshop dates
Outline PRS/ROS/TAC pathways to June Board with key submission dates
Batch Zero PGRR/NPRR Walk-though
Review March 10 slides and highlight key updates since the last version
Walk through proposed ERCOT comments on PGRR language for alignment
Market Comments filed on NPRR/PGRR (21 sets)
Open discussion: stakeholder comments, initial requests, and areas requiring refinement after filing
Summary of key comments received by PGRR section
1
2
3
4
5
Discussion of CLR and BYOG concepts
Resume discussion on treatment of CLR and BYOG
Q&A
Open forum for Batch Zero concerns, comments, and suggestions

## Slide 8: Related PUCT Activities
PUC Project 58480, 16 TAC § 25.370, Large Load Forecasting Rule (Adopted & Effective March 1, 2026)
  After 2026, only Large Loads that have executed an interconnection agreement that satisfies the requirements in PUC Project 58481 will be included in the Large Load forecast. These requirements will be reflected in future revision requests.
  Establishes alternative gating criteria for Large Loads to be included in the 2026 Large Load Forecast, which is used in planning assessments until new cases are constructed in 2027 using new rule criteria.
PUC Project 58481, proposed to be 16 TAC § 25.194, Large Load Interconnection Standards (Proposal for Publication filed March 12, 2026)
  Intermediate Agreement Requirements:
    Site control (updated)
    Financial Security ($50,000/MW in current PFP; subject to final rule)
    Disclosures
    Option to pay for significant equipment or services
  Interconnection Agreement Requirements:
    Site control (updated)
    Financial security
    Interconnection fee ($50,000/MW, non-refundable)
    CIAC
  Other Provisions
    Reallocation
    Withdrawal Consequences
    Refund Eligibility and Timing
Source: PUCT Project No. 58480 (final rule) and Project No. 58481 – Proposal for Publication of 16 TAC §25.194 (filed March 12, 2026)
XXX Changes due to PUCT PFP

## Slide 9: Incorporating PUC Project 58481 into Batch Zero: Two Implementation Pathways
2026
2027
Q2
Q3
Q4
Q1
Case building
  Batch Zero Study
  Illustrative publication date of Project No. 58481
Deferred launch of Batch Zero
No need for re-alignment if adopted 58481 rule is different from published draft
Case building
Batch Zero Study
Potential re-alignment needed if adopted 58481 rule is different from published draft
Early launch of Batch Zero
Project 58481 will define readiness and financial commitment standards for Large Loads. ERCOT must determine how to align Batch Zero timing with this rulemaking
Context
  Description: embed the embed the PUCT proposal for publication (Project No. 58481) concepts directly into the PGRR language and update the PGRR with the published PFP once available
  Implications
  Enables earlier Batch Zero launch
  Uses proposed draft for intermediate agreement and interconnection agreement criteria
  Risk of misalignment if final rule differs from draft
  Description: draft PGRR to reference the final adopted 16 TAC §25.194 and begin Batch Zero a defined period (e.g., X days) after the rule becomes effective
  Implications
  Batch Zero will be aligned with final PUC rule
  May delay Batch Zero start depending on rule adoption timeline
Illustrative timeline
Option 1: Replicate the Draft 58481 PFP in the PGRR (proceed in parallel)
Option 2: Tie PGRR to Final Adopted 58481 Rule (sequential alignment)
Option
Description and implications

## Slide 10: Stakeholder feedback received to date
Source: ERCOT PGRR145 “Key Documents” section
Author
G
Date of submission
Mar 5; Mar 11; Mar 19
Mar 9; Mar 20
Mar 9; Mar 20
Mar 10
Mar 19
Mar 19
Mar 20
Mar 20
Mar 19
Mar 20
Mar 20
Schaper Energy Consulting
Reliant Energy1
Crusoe
Rose City Partners
Lancium
Skybox Datacenters
Oncor
CenterPoint Energy
IREN
Stream Datacenters2
Agentic Infrastructure1
Provident Inc.2
Mar 20
3-Waters Technical Services
Vistra
Eolic
TEBA
Satoshi Energy
Black Mountain
Sandow Lakes Energy
Emerald AI
AEP
Monarch Energy
Crow Holdings
Zero Emission Grid
Author
Date of submission
Mar 20
Mar 20
Mar 20
Mar 20
Mar 20
Mar 20
Mar 20
Mar 20
Mar 20
Mar 20
Mar 20
Mar 20
1. Agentic and Reliant filed comments together on Mar 20 | 2. Stream Datacenters and Provident filed comments together on Mar 20
Note: based on list of comments submitted as of 3/23

## Slide 11: Stakeholder feedback highlights: key themes across submissions (more details in Appendix)
Source: ERCOT PGRR145 “Key Documents” section
Recurring feedback
Description
Treatment of advanced and legacy projects
Projects that have completed legacy LLIS processes (studies, IA execution, financial commitments, construction start) are viewed as already demonstrating firm readiness: re-assessment or reclassification at this stage raises concerns around investment certainty and financing risk
1
Timing framework and transition fairness
Current cutoff dates (e.g., March–July 2026 window) are perceived as creating inconsistent outcomes for projects with similar readiness, particularly where progress depends on ERCOT/TSP processing timelines: greater alignment between readiness and eligibility timing is sought
2
Eligibility and prioritization criteria
Preference for prioritization based on objective project maturity (studies, IA, financial commitment, construction) rather than timing metrics alone. RPG-backed projects are also viewed as valid pathways given their higher level of technical review, when combined with demonstrated readiness
3
Financial requirements and regulatory alignment
Concerns on potential duplication of financial obligations (e.g., CIAC vs. new security/fees), treatment of projects with no network upgrades, and alignment with ongoing PUCT rulemaking (Project No. 58481): request for mechanisms for crediting prior commitments and ensuring consistency with final rules
4
Process clarity, governance, and implementation
Feedback highlights the need for clearer definition of roles (ERCOT vs. TSP/DSP), standardized agreements and attestations, consistent modeling inputs, and greater transparency in study scope, assumptions, and outputs to support implementation
5
Note: based on list of comments submitted as of 3/23

## Slide 12: Four different constructs were identified by ERCOT to integrate CLR and BYOG concepts into PGRR145
Construct
Description
Feasibility
1A
Load-Only CLR (Not netted with Generation and/or Batteries)
Large Load registers as a CLR at the POI. No netting allowed with co-located generation or storage.
Potentially feasible
1B
CLR with Non-Synchronous Backup Generation
Large Load registers as a CLR and utilizes behind-the-meter backup generation that is not synchronized with the ERCOT grid
Potentially feasible
2
BYOG Self-Limiting Facility (SLF)
Colocated Large Load and Generation operate behind a single POI under a defined net injection/withdrawal limit enforced at the POI
Potentially feasible
3
Netted Network
Colocated Large Load and Generation operate behind a single POI (physically similar to SLF), but are permitted to participate simultaneously on both the supply and demand sides of the ERCOT market, subject to the POI interconnection limit
Not feasible

## Slide 13: Load-Only CLR (Not netted with any Generation or Batteries)
Source: ERCOT discussions
Point of interconnection
Large Load registers entirely as a CLR without any type of netting with generation or storage
Load-Only CLR leverages the existing CLR framework as the simplest near-term option1, subject to required market/system implementation items (e.g., SCED/mitigation enhancements) before energization
Participates as dispatchable demand and must follow SCED basepoints within its registered operating range (PC/LPC/MPC)
No assurance of service above awarded firm MW; real-time consumption may be reduced below PC based on system conditions and SCED mitigation
ERCOT observes and verifies performance based on net MW at the POI and adherence to SCED dispatch instructions
Must meet existing CLR telemetry and dispatch performance requirements (subject to SCED instructions and registered operating limits)
Load may register operational capability above awarded firm MW, subject to real-time dispatch and congestion mitigation2
Illustrative example
  150 MW requested in Year 1
  ERCOT performs steady-state and stability studies and allocate phased MW (e.g., 100 MW in Years 1–2, 300 MW in Years 3-4, until transmission upgrade in Year 5)
  Operational parameters:
    PC = 0–100 MW (firm)
    LPC = 0–100 MW
    MPC = 150 MW (upper operational capability; not a planning guarantee)
    CLR quantity may be modified in later years as transmission capability increases
1. NPRR1188 later in 2026: Nodal pricing align local congestion prices. NPRR1255 mitigation methods needed (small project) | 2. Potentially subject to additional limits identified in dynamic studies
Description
Details
Load
Illustrative scheme
Chart: 
 | 100 | 100 | 300 | 300 | 1000
 | 50 | 200 | 200 | 400
50
Year 1
Year 2
Year 3
Year 4
Year 5
150
300
500
700
CLR Load
Firm Load
POTENTIALLY FEASIBLE CONFIGURATION
1A
ERCOT grid
XXX Changes/Clarification vs. Mar 10th Workshop

## Slide 14: CLR with Non-Synchronous Backup Generation
Source: ERCOT discussions
Point of interconnection
Large Load registers as a CLR and utilizes behind-the-meter backup generation that is not synchronized1 with the ERCOT grid
This construct allows internal self-supply during curtailment without parallel operation or export to the ERCOT system
To qualify under this construct, backup generation must not be synchronized with or operate in parallel with the ERCOT grid and must be incapable of exporting power at the POI
ERCOT models the facility as load only at the POI for steady-state and stability studies and observes only net load at the POI
Transmission study limits remain binding on the net load at POI
Load must follow SCED basepoints within its LPC–MPC range
Large Load may need to segment internal load into controllable tranches (e.g., 10 MW blocks) to comply with SCED
Any internal switching to backup generation is behind-the-fence and not visible to ERCOT
If backup generation fails, the load remains responsible for meeting SCED dispatch instructions
No export or generation market participation is permitted under this construct2
Description
Illustrative scheme
POTENTIALLY FEASIBLE CONFIGURATION
1B
1. Any behind-the-meter generator or storage that can operate in parallel with the ERCOT grid (i.e., can be synchronized/connected while the POI remains energized) must be registered as a GR/ESR and is not compatible with a Load-Only CLR construct | 2. No energy or ancillary service participation from the backup resource is permitted
Load
ERCOT grid
Backup Gen
Backup Gen
Details
Load
ERCOT grid
Backup Generation
Backup Generation
No AC path to ERCOT grid

## Slide 15: BYOG Self-Limiting Facility (SLF)
Source: ERCOT discussions
Point of interconnection
Colocated Large Load and Generation operate behind a single POI under a defined net injection/ withdrawal limit enforced at the POI
Facility is structured as a PUN with a Self-Limiting Feature (SLF) (consistent with NPRR1026 framework)
The SLF ensures that net real power at the POI never exceeds the approved interconnection limit, regardless of internal load or generation configuration
Load and Generation are both registered resources
Interconnection limit applies to net MW at the POI
Requires operational coordination agreement between Load and Generator
ERCOT models the facility as a net resource at the POI, subject to the self-limiting cap
Facility must ensure net injection/withdrawal does not exceed POI cap at any time (may require breaker logic and/or reverse power relay to enforce the limit)
Transmission planning does not assume simultaneous full load and full generation at the POI:
  Either supply-side (GR/ESR) or demand-side (CLR) may participate at a given time
  Simultaneous full participation on both sides is not permitted unless structured as a Netted Network (separate construct)
The largest modeled contingency depends on internal configuration (e.g., if generators share a common step-up transformer, transformer loss may be most limiting event; if generators are electrically independent, individual G-1 may apply)
Description
Illustrative scheme
Load = 1,000 MW
Gen = 5 x 250 MW
G-1 compliant (serve 1,000 MW load) or most limiting contingency
POTENTIALLY FEASIBLE CONFIGURATION
2
Load
ERCOT grid
Gen 1
Gen 2
Gen 3
Gen 4
Gen 5
Load = 1,000 MW
Gen = 2 x 500 MW
G-1 compliant (only serve 500 MW load)
Load
ERCOT grid
Gen 1
Gen 2
Details

## Slide 16: Netted Network
Source: ERCOT discussions
Point of interconnection
Colocated Large Load and Generation operate behind a single POI (physically similar to SLF), but are permitted to participate simultaneously on both the supply and demand sides of the ERCOT market, subject to the POI interconnection limit
Same physical configuration as SLF (Load and GR/ESR behind one POI)
Net injection/withdrawal at the POI remains capped by the interconnection agreement
Unlike SLF:
  Supply and demand may participate simultaneously in Energy and AS1 markets
  Enables concurrent market activity from load and generation behind the same POI
Description
UNFEASIBLE CONFIGURATION
3
Illustrative scheme
Load = 1,000 MW
Gen = 5 x 250 MW
G-1 compliant (serve 1,000 MW load) or most limiting contingency
Load
ERCOT grid
Gen 1
Gen 2
Gen 3
Gen 4
Gen 5
Load = 1,000 MW
Gen = 2 x 500 MW
G-1 compliant (only serve 500 MW load)
Load
ERCOT grid
Gen 1
Gen 2
1. Ancillary services
Details
Note:
Netted Network would still be modeled the same as PUN (ie no difference in Batch)
ERCOT Markets and Operations will continue to evolve

## Slide 17: Conceptual Batch Zero BYOG operating configurations for Large Load interconnection3
PRELIMINARY
Business as Usual (BAU)
PUN+
Batch Self-Limiting Facility (SLF)
Load and generation are connected at separate POIs (shown) or behind the same POI and interact through the transmission system under existing interconnection framework
Configurations
Description
Generation and load are studied separately
Generation is only included in the LLIS if it meets PG 6.9 criteria
Load deliverability depends on transmission capability and may be constrained through the current study process
Transmission upgrades from batch study based on G-1+N-1 analysis
Details
Load is supported by dispatchable on-site generation such that G-1 ≥ load and treated as firm, with reliability managed through ERCOT operational actions
Configuration satisfies G-1 ≥ load (loss of one generator still allows remaining units to serve the load)
Load is treated as firm
No planning or administrative limit at POI
No transmission upgrades from batch study since configuration is G-1 secure
In operations:
  ERCOT may reject generator outages or require mitigation plans
  ERCOT may RUC resources1
  In real-time, mitigation plans or local load shed may be used
3. Conceptual designs still under internal review and may change | Source: ERCOT discussions
Site operates with a fixed transmission withdrawal limit determined through batch study
Generation mix may include thermal resources, renewables, and batteries
A fixed transmission withdrawal limit is established (e.g., 100 MW grid import limit) determined in the batch study
ERCOT does not coordinate RUC1 or outage management for the facility
The load and generation owners must coordinate operations to ensure grid imports never exceed the limit
The site would be equipped with a reverse power relay or equivalent protection to enforce the limit
Transmission upgrades required if identified by the batch study to meet reliability criteria2
1. RUC (Reliability Unit Commitment): ERCOT mechanism used to commit generation outside the market to maintain system reliability | 2. Based on batch study results for the generation/load mix
No admin limit
100 MW limit ensured by reverse power relay
~
~
~
~
~
~
~
~
~
~
~
~
~
Point of interconnection (POI)

## Slide 18: Questions?
Forums
Workshops and working groups
PRS (Protocols Review Subcommittee)
ROS (Reliability and Operations Subcommittee)
TAC
ERCOT Board
2026
Q1
Q2
Q3
Feb
Mar
Apr
May
Jun
Jul
Workshop #2 Feb 12
Workshop #4 Mar 10
Workshop #5 Mar 24
Workshop #6 Mar 30
PRS Update 3/11
ROS Update 3/5
ROS Vote 5/7
Board Vote 6/1
3/4 ERCOT files Batch Zero Revision Request(s)
8/1 Target effective date of protocols
Objective
Align stakeholders on direction/scope following Commission decision
Define the scope, boundaries, and intended role of Batch Zero
Preview structure/governing concepts of Batch Zero NPRR before filing
Confirm proposed protocol changes are ready for governance review
Endorse NPRR for advancement to TAC (contingent on technical valid.)
If accompanying PGRR filed, then ROS will be involved in review
ROS approval will be required for any PGRR(s).
Review/endorse combined NPRR/PGRR package for Board approval
Authorize implementation of Batch Zero by approval of NPRR/PGRRs
LLWG Feb 19
Workshop #3 Feb 26
TAC Vote 5/19-20
Close outstanding design and drafting issues, incorporate vetted stakeholder feedback, and finalize Revision Request language for committee approval
Target Board approval date
Board Meeting 4/20
Regular PRS 4/15
ROS Update 4/2
Monthly TAC updates
Workshop #7 Apr 9
Special PRS 4/22
Regular TAC 4/29
Special TAC 5/13
PRS Vote 5/6
4
Monthly LLWG updates
4/8 ERCOT files CLR/BYOG Revision Request(s)
ROS Update (special) 4/14
ROS Update (special) 4/23

## Slide 19: APPENDIX
Summary of Market Comments in following Slides

## Slide 20: Stakeholder feedback highlights: key themes across submissions
Source: ERCOT PGRR145 “Key Documents” section
Recurring feedback
Description
Treatment of advanced and legacy projects
Projects that have completed legacy LLIS processes (studies, IA execution, financial commitments, construction start) are viewed as already demonstrating firm readiness: re-assessment or reclassification at this stage raises concerns around investment certainty and financing risk
1
Timing framework and transition fairness
Current cutoff dates (e.g., March–July 2026 window) are perceived as creating inconsistent outcomes for projects with similar readiness, particularly where progress depends on ERCOT/TSP processing timelines: greater alignment between readiness and eligibility timing is sought
2
Eligibility and prioritization criteria
Preference for prioritization based on objective project maturity (studies, IA, financial commitment, construction) rather than timing metrics alone. RPG-backed projects are also viewed as valid pathways given their higher level of technical review, when combined with demonstrated readiness
3
Financial requirements and regulatory alignment
Concerns on potential duplication of financial obligations (e.g., CIAC vs. new security/fees), treatment of projects with no network upgrades, and alignment with ongoing PUCT rulemaking (Project No. 58481): request for mechanisms for crediting prior commitments and ensuring consistency with final rules
4
Process clarity, governance, and implementation
Feedback highlights the need for clearer definition of roles (ERCOT vs. TSP/DSP), standardized agreements and attestations, consistent modeling inputs, and greater transparency in study scope, assumptions, and outputs to support implementation
5
Note: based on list of comments submitted as of 3/23

## Slide 21: Stakeholder feedback concentrates on legacy project treatment and study validity in Batch Zero
Chart: 
 | 21 | 8 | 8 | 4 | 2 | 2 | 2 | 1 | 1
Comments received by section, # of comments1
Key takeaways
1. Each referenced section is counted once for each stakeholder; repeated mentions of the same section within a stakeholder’s comments are considered a single reference | Note: based on list of comments submitted as of 3/23
  Feedback is concentrated on treatment of legacy projects and prior study outcomes (Sections 9.2)
  Strong push to preserve investment-backed outcomes and avoid retroactive re-evaluation (e.g., executed IAs, completed studies, and committed capital should not be re-opened)
  Investment certainty is the central concern, particularly around re-studies, MW reallocation, and timing-based eligibility cutoffs
  Financial commitment requirements are comparatively less debated, with feedback primarily focused on implementation details (e.g., alignment with PUCT rules, avoiding duplication) rather than overall framework design
Detailed next
Main stakeholder feedback
  Eligibility and study framework (9.2)
  Cross-cutting
  Commitment criteria and agreements (9.7)
  Quarterly stability requirements (5.3)
  Energization and ongoing obligations (9.6)
  Batch study methodology (9.3)
  Ensure previously approved and mature projects are automatically recognized as Base Load (e.g., avoid re-evaluation, circular requirements, or exclusion of equivalent study pathways)
  Improve governance clarity and transparency across Batch Zero (e.g., clear roles ERCOT vs TSP/DSP, limit discretion, standardize processes, align with PUCT, enhance communication)
  Align financial requirements with PUCT and avoid duplicative obligations for legacy projects
  Consider chronological prioritization as an alternative to current allocation approach
  Align stability timelines with Batch Zero and clarify dynamic model responsibilities
  Ensure advanced projects continue without re-screening, delay, or reset
  Batch Zero refinement and transmission plan (9.5)
  Enhance TSP coordination, short circuit scope, and ensure upgrades support full load
  Load modeling and integration (6.6)
  Clarify modeling entry requirements and treatment of co-located or modified loads
  ILLE commitment and agreement execution (9.4)
  Extend commitment timelines and reduce risk from compressed agreement execution windows
Source: Batch Zero PGRR145 Stakeholder Comments

## Slide 22: Deep dive: Section 9.2 stakeholder feedback on eligibility and study validity
Chart: 
 | 16 | 11 | 4 | 3 | 2 | 1
Comments received by section, # of comments1
Main stakeholder feedback
  Study validity and ordering (9.2.1.4)
  Base load eligibility (9.2.1.1)
  Applicability framework (9.2.1)2
  Studied/allocated load (9.2.1.2)
  Commitment window (9.2.4)
  Submission requirements (9.2.2)
Key takeaways
  Section 9.2 dominates stakeholder concern, led by study validity and base load eligibility
  Protection for advanced projects is the clearest theme: stakeholders want safe harbor and no retroactive re-screening
  Eligibility is seen as too narrow and should recognize RPG, RTP, CLR/BYOG, and co-located generation pathways
  Process clarity remains a major issue, especially around timing, dynamic data, and ERCOT/TSP/DSP roles
Detailed next
  Expand safe harbor treatment for completed studies, executed agreements, financial commitment, and co-located/FIS-supported loads
  Clarify how Batch Zero applies to non-Batch projects and preserve parallel advancement pathways
  Broaden eligible pathways to include RPG-qualified, CLR/BYOG, and other substantively committed projects
  Clarify dynamic data standards and assign a consistent authority for impact determinations
  Extend the agreement-execution window and reduce pressure from compressed deadlines
1. Each referenced section is counted once for each stakeholder; repeated mentions of the same section within a stakeholder’s comments are considered a single reference | 2. Section 9.2.1 comments are cross-cutting comments addressing multiple sub-sections within 9.2.1 | Note: based on list of comments submitted as of 3/23
  Limit prior-study invalidation and use objective readiness and chronology, while recognizing valid RPG/RTP-backed projects
Source: Batch Zero PGRR145 Stakeholder Comments

## Slide 23: Study validity and re-evaluation (9.2.1.4): stakeholder feedback deep-dive
Source: Batch Zero PGRR145 (March 4) Stakeholder Comments
Protection of completed studies
Studies completed under Sections 9.4 and 9.5 should be treated as final and not subject to retroactive re-evaluation or re-determination, as this undermines investment certainty and reliance on prior approvals
Establish a safe harbor whereby completion of §§9.4 and 9.5 constitutes a complete and valid study, not subject to retroactive review under §9.2.1.4
Batch Zero should not re-order or invalidate advanced projects
Technically mature and financially committed projects should be treated as fixed base load inputs and not re-screened, re-prioritized, or displaced based on timing or interdependencies
Clarify that advanced-stage projects are preserved as base load and not subject to re-prioritization or displacement
Study validity should reflect project maturity (not timing alone)
Current proposals rely on proxies (e.g., RPG submission timing, ERCOT discretion) that do not reflect actual project maturity, risking exclusion of advanced projects
Base study validity and prioritization on completion of LLIS (or equivalent) and demonstrated commitment, rather than timing-based criteria
Main points
Description
Note: Comments reflect stakeholder feedback on both the March 4 PGRR draft and subsequent ERCOT comments issued on March 17
(Partially) Addressed by ERCOT comments on Mar 17
Stakeholder suggestion
Recognition of RPG/RTP-backed pathways
Projects supported by RPG or RTP processes are viewed as having undergone substantial technical review and should be recognized where combined with demonstrated readiness
Allow RPG/RTP-backed projects to qualify where technical review and project readiness requirements are met

## Slide 24: Base load eligibility criteria (9.2.1.1): stakeholder feedback deep-dive
Source: Batch Zero PGRR145 (March 4) Stakeholder Comments
Main points
Stakeholder suggestion
Protection of advanced projects from re-evaluation
Grant automatic Base Load classification to projects with completed studies, executed IA/FEA, and demonstrated commitment, without re-evaluation under §9.2.1.4
Recognition of equivalent study pathways (LLIS/FIS)
Allow completed FIS (incl. co-located load) to qualify as Base Load where requirements are met
Circularity and timing of attestation requirements
Description
Projects that completed LLIS (or equivalent FIS1) and demonstrated financial commitment should be treated as firm and not subject to re-evaluation or reclassification, as this undermines financing and reliance on prior approvals
FIS studies for co-located load should be explicitly recognized as equivalent to LLIS, ensuring otherwise qualified projects are not excluded from Base Load eligibility
Attestation requirements require capital commitment before Base Load status or MW allocation is confirmed, creating a circular and unworkable process
Confirm Base Load eligibility before requiring attestations or condition attestation requirements on confirmed eligibility
1. Full Interconnection Study (performed for a generation project)
Timing gap (“commit before certainty”)
Developers are required to make binding procurement and construction commitments before receiving confirmation of Base Load status, creating an “air gap” that introduces material investment risk
Align timing by confirming eligibility before requiring commitments, or remove requirements within the gap
Note: Comments reflect stakeholder feedback on both the March 4 PGRR draft and subsequent ERCOT comments issued on March 17
Eligibility should reflect demonstrated financial commitment
Financial commitment (e.g., CIAC, equipment procurement, capital deployment) is viewed as a primary indicator of project readiness and should be treated as equivalent to executed agreements for Base Load eligibility
Allow demonstrated financial commitment to qualify projects for Base Load eligibility, even where an IA has not yet been executed