## Slide 1
SCR820 – Real-Time Operator Communication System (RTOC)
Preethi Meher & Christelle Seri
Mar 26, 2026

## Slide 2: SCR820
Agenda
  Status updates
  Project timeline overview
  Testing Updates
  Primary Contacts

## Slide 3: Status Updates
Project updates
  ERCOT internal operator logging feature went live in Dec 2025
  Messaging feature deployed and under testing in staging
  MIS proxy setup to enable external user access
  EMS data interface development is complete
  Communication template creation screens are developed and testing is in progress
  Development updates
  Admin screens for internal use in progress
  SOL Exceedance data displays are being developed
  Default dashboard development will begin

## Slide 4: SCR820 – Project Timelines
Phase | Milestone | Target Date
Planning | Requirements & Design Finalized | Complete
Development | Development & Internal ERCOT Testing | Apr 2026
Testing | TOs/QSEs Testing | Mar 2026 – May 2026
Parallel Ops | Dual Operation Phase | June 2026
Go Live | Full Launch | July 2026
Project Timeline
Market Notice: M-A032326-01 Access and familiarization of the Real- Time Operation Communications (RTOC) tool

## Slide 5: Testing and Parallel Operations Timelines
Market Notice sent out on 03/23/2026:
M-A032326-01 Access and familiarization of the Real- Time Operation Communications (RTOC) tool

## Slide 6: Tool Access
Access control
  Application access will be granted via digital certificates
  New roles must be added to the certificate for authorization
    Operator (RTOC_M_OPERATOR)
    ReadOnly (RTOC_M_VIEW)
  Link will be available on mis.ercot.com application library (It will be enabled after the completion of testing)
Available to request

## Slide 7: Provide Primary Contact Information
We need your help to streamline communication for RTOC Market Testing.
Please share the following details for your organization:
Primary Contact Name
Email Address
Role/Designation
Why?
To provide testing-related communications
Share application URL, updates, and instructions promptly
How to Submit:
Email your details to: Preethi.MeherMalla@ercot.com, Sreenivas.Badri@ercot.com

## Slide 8: Key Highlights
What messages will RTOC handle?
Anything that requires a hotline call today
Examples include:
  Operational alerts
  Outage notifications
  System conditions
These same communications will now be delivered through RTOC for centralized access
How will notifications work?
Audible alerts for critical messages when logged in.
Visual notifications for operational updates.
API integration is under consideration
How Will RTOC Handle QSE Relationships?
Main QSE will have access to the tool
Main QSE should communicate on behalf of sub-QSEs

## Slide 9: SCR820
Thank you