## Slide 1: Project Prioritization Update Technical Advisory Committee (TAC) Troy Anderson ERCOT Portfolio Management April 29, 2026
Key Takeaways
10 High Priority RR projects tracked from Aug 2025 workshop
2026 Aging RR prioritization at PRS in June
Outline:
High Priority Revision Request Project Status
Other Revision Request Project Updates

## Slide 2: Aging Revision Request Project Status
10 Revision Request projects were deemed “High Priority” at August 2025 Prioritization Workshop
Status | High Priority Revision Request Projects | Additional Information
Complete | NPRR1234 – Interconnection Requirements for Large Loads and Modeling Standards for Loads >=25MW | System changes implemented in 3 phases Remaining gray box: Large Load Interconnection Study (LLIS) fee
 | NPRR1277 – Revisions to EAL Formula | Went live on 3/2/2026
In-Flight | NPRR1188 – Implement Nodal Dispatch and Energy Settlement for CLRs | January 2027 go-live target (w/NPR1244)
 | NPRR1198 – Congestion Mitigation Using Topology Reconfigurations | September 2026 go-live target
 | NPRR1238 – Registration of Loads with Curtailable Load Capabilities | Q4 2026 go-live target
 | NPRR1244 – Clarification of CLR Primary Frequency Response Responsibilities | January 2027 go-live target (w/NPR1188)
 | NPRR1281 – Improvements to Alternate FFSS Resource Designation | October 2026 go-live target
Pending Start Approval | NPRR1091 – Changes to Address Market Impacts of Additional Non-Spin Procurement | Expected to be part of Reliability Deployment Price Adder (RDPA) analysis
 | NPRR1004 – Load Distribution Factor Process Update | July 2026 start candidate
Workaround in Place | NPRR1216 – Implementation of Emergency Pricing Program | No action at this time
Key Takeaway: 10 High Priority RR projects tracked; 2 complete, 5 in-flight, 2 pending approval, 1 workaround

## Slide 3: Aging Revision Request Project Status
Updates on other Revision Request projects
Key Takeaway: 2026 Aging Revision Request project prioritization at PRS in June
Status | Revision Request | Additional Information
In-Flight | NPRR936 – CRR Account Holder Limits | Q4 2026 go-live target (w/NPR1288)
 | NPRR1201 – Limitations on Resettlement Timeline & Default Uplift Exposure Adjustments | Q4 2026 go-live target
 | NPRR1288 – Remove Multiple Month Transactions in CRR Auctions | Q4 2026 go-live target (w/NPR936)
 | NPRR1303 – Modernize Submission of Declarations of Natural Gas Pipeline Coordination | September 2026 go-live target
 | SCR820 – Operator Real-Time Messaging During Emergency (RTOC) | June 2026 go-live target
Not Started (starting soon) | NPRR1290 – Gap Resolutions and Clarifications for the Implementation of RTC+B | Go-live target TBD (w/NPRR1323)
 | NPRR1323 – Correction to Inadvertent Removal of Real-Time MCPC Capping for NPRR1290 Phase 2 | Go-live target TBD (w/NPRR1290)
 | SCR829 – API for the NDCRC Application | Go-live target TBD
Start Date Delay | SCR818 Ph2 – Changes to Incorporate GIC Modeling Data into Existing Modeling Apps | Resource constraints
 | SCR831 – Short Circuit Model Integration | Resource constraints

## Slide 4: Questions/Comments?
Troy.Anderson@ercot.com