| PGRR Number | 145 | PGRR Title | Batch Zero Process for Large Load Interconnections |
| --- | --- | --- | --- |
| Impact Analysis Date |  | May 18, 2026 |  |
| Estimated Cost/Budgetary Impact |  | PCLR: Between $300k and $400k See Comments. Batch Zero and WLPUN: Annual Recurring Operations and Maintenance (O&M) Budget Cost: $3.6M – $4.5M See ERCOT Staffing Impacts. |  |
| Estimated Time Requirements |  | PCLR: The timeline for implementing this Planning Guide Revision Request (PGRR) is dependent upon prioritization and Public Utility Commission of Texas (PUCT) approval. Estimated project duration: 8 to 12 months. Batch Zero and WLPUN: No project required. This Nodal Protocol Revision Request (NPRR) can take effect following Public Utility Commission of Texas (PUCT) approval. |  |
| ERCOT Staffing Impacts (across all areas) |  | Implementation Labor: 79% ERCOT; 21% Vendor There will be ongoing operational impacts to the following ERCOT departments totaling 18.0 Full-Time Employees (FTEs) to support this PGRR: • Grid Planning (9.0 FTEs Effort) • Dynamic Studies (7.5 FTEs Effort) • Planning Model Administration (1.0 FTE Effort) ERCOT has assessed its ability to absorb the ongoing efforts of this PGRR with current staff and concluded the need for 18 FTEs in the following departments: • Grid Planning (9.0 FTEs) • Dynamic Studies (8.0 FTEs) • Planning Model Administration (1.0 FTE) • Grid Planning - department requires nine additional FTE to support the following work: • Batch Zero (9 FTEs) o 16,740 hrs. to perform planning studies to support large load interconnection, develop Batch Zero power flow study cases, conduct steady-state to meet NERC & ERCOT planning criteria and collaborate with interconnection transmission service providers (TSPs) to identify necessary transmission upgrades, identify load allocation limits, complete the Batch Zero Refinement studies based on large load commitments, and recommendations and submit transmission projects to the Regional Planning Group (RPG). • Dynamic Studies - department requires eight additional FTEs to support the following work: • Batch Zero (7 FTEs) o 12,960 hrs. to support Batch Zero and refinement stability screening studies and detailed stability studies to meet NERC standard. • WLPUN (1 FTE) 900 hrs. to support additional maximum withdraw constraints calculation for WLPUN. • Planning Model Administration - department requires one additional FTE to support the following work: • Batch Zero (1 FTE) o 1,860 hrs. to support case building for the Batch Study by coordinating the transmission topology for the 15 cases. This FTE will also support the Batch Study as needed. The 2026-2027 ERCOT budget does not account for the FTEs needed to support this PGRR. |  |
| ERCOT Computer System Impacts |  | The following ERCOT systems would be impacted (primarily related to PCLR requirements): - Market Management System 30% - Energy Management System 19% - Data and Information Products 14% - Resource Integration and Ongoing Operations 12% - Data Management & Governance 10% - Enterprise Integration Nodal Services 8% - Registration 4% - Web Communications 2% |  |
| ERCOT Business Function Impacts |  | ERCOT will update business processes to implement this PGRR. |  |
| Grid Operations & Practices Impacts |  | ERCOT will update grid operations and practices to implement this PGRR. |  |

Evaluation of Interim Solutions or Alternatives for a More Efficient Implementation

None offered.

Comments

This Impact Analysis reflects the staffing and systems needed to achieve the Batch Zero functionality and to support the ongoing work in subsequent Batch Studies (to be further defined in the second half of 2026). The impacts for the subsequent Batch studies after Batch Zero are subject to further review and may result in changes in staffing and/or system costs to be defined later in 2026. ERCOT will develop the Control Room displays as necessary for monitoring the loads that leverage the PCLR and WLPUN designs.