## Slide 1: Batch Zero Timelines and Communications June 4, 2026
Disclaimer: This presentation is provided solely for informational and discussion purposes and does not constitute a binding interpretation of the ERCOT Protocols, Planning Guide, or any other governing authority. In the event of any conflict between this presentation and the ERCOT Protocols, Planning Guide, or other applicable governing documents, the governing documents shall prevail.

## Slide 2: Weekly Batch Zero Readiness Discussions (see ERCOT Meeting Calendar)
Also:
ERCOT is currently sending weekly emails to TSPs by end of day Tuesday on current LLIS Batch Zero status (final LLIS status is subject to PUCT approval of PGRR145 requirements, expected Jun 18)
ERCOT is developing an FAQ to assist with implementation questions
Wednesday
Friday
Thursday
Tuesday
Monday
5
12
19
LLWG/Batch Readiness
Time TBD
26
3
4
Batch Readiness Meeting 2-3PM
10
11
Batch Readiness Meeting 2-3PM
17
18
24
25
Batch Readiness Meeting 2-3PM
9
16
23
30
2
Board Meeting
8
15
22
29
1
Board Meeting
3
10
LLIS Submission
Process ends
17
24
TSP Due date for Batch Zero
1
Batch Readiness Meeting 2-3PM
2
8
9
Batch Readiness Meeting 2-3PM
15
16
22
23
7
14
21
28
6
13
20
27
June
July
29
30
31

## Slide 3: Batch Zero key submission deadlines and main responsibilities
Source: ERCOT discussions
ILLE
TSP/DSP
ERCOT
July 10
July 24
August 7
August 31
Detailed next
Deadline for ILLE to submit required Batch Zero eligibility materials to the Interconnecting TSP/DSP and, where required, directly to ERCOT (e.g., dynamic load models)
Deadline for TSPs/DSPs to submit complete Batch Zero eligibility packages and supporting materials to ERCOT
Deadline for ERCOT to notify TSPs/DSPs of Batch Zero classification results, including eligibility determinations and identified dynamic model or data deficiencies
Deadline for ILLEs to resolve identified dynamic model and technical data deficiencies and submit corrected materials
Last day ERCOT will review and approve LLIS studies under the legacy process
1
2
Note: timeline assumes PUCT approval on June 18th
Early submission encouraged prior to July 10: Interconnecting DSPs/TSPs and ILLEs are encouraged to begin submitting Batch Zero eligibility materials and supporting documentation as early as practicable in advance of the July 10, 2026 milestone. ERCOT may review submitted materials on a rolling basis and provide preliminary feedback regarding completeness, potential deficiencies, or additional information needs
X

## Slide 4
ILLE
TSP/DSP
ERCOT
  Coordinate review responsibilities between TSP and DSP, as applicable
  Begin preliminary review of submitted ILLE materials and supporting evidence
  Align on the designated entity responsible for final ERCOT package submission
  Finalize LLIS study review activities under the legacy process
  Working with the TSP/DSP, identify the applicable Batch Zero eligibility pathway within the LIF
  Prepare required attestations, technical documentation, and supporting evidence
  Submit dynamic load models and supporting technical materials to ERCOT and the Interconnecting TSP, where applicable
  Resolve known documentation or technical gaps prior to TSP/DSP validation review
July 10 Batch Zero milestone: activities required
1
  Lead role

## Slide 5
ILLE
TSP/DSP
ERCOT
  Complete review and validation of ILLE submission materials against applicable eligibility requirements
  Resolve outstanding package deficiencies and confirm submission completeness within the LIF
  Finalize the coordinated Batch Zero eligibility package and submit required materials to ERCOT
  Prepare for formal completeness, classification, and eligibility review of submitted Batch Zero packages
  Respond to TSP/DSP validation questions and resolve identified submission deficiencies, as applicable
  Provide supplemental technical materials or clarifications needed to support package completeness
July 24 Batch Zero milestone: activities required
2
  Lead role
  Clarification: the post–July 10 validation period is intended to address administrative corrections, clarification requests, and minor submission errors identified during TSP/DSP review (e.g., typos or incorrect references). It is not intended to allow submission of materially missing eligibility items or satisfaction of requirements that were not completed by the applicable July 10 deadline (e.g., posting financial security, executing required commitments, or completing required attestations)

## Slide 6: Batch Zero eligibility submission and validation process
Performed by ILLE
Performed by TSP/DSP
Performed by ERCOT
Source: ERCOT discussions
ILLUSTRATIVE
HIGHLY PRELIMINARY
Eligibility Path Identification
Working with TSP/DSP, ILLE uses the Load Information Form (LIF) to identify the applicable Batch Zero eligibility pathway and the associated submission requirements and documentation
1
Preparation of Submission Materials
ILLE executes the required attestations, and prepares technical documentation, forms, and supporting evidence applicable to the selected eligibility pathway
2
Submission of Materials
ILLE submits the applicable materials and supporting evidence to the Interconnecting TSP/DSP and, where required, directly to ERCOT (e.g., dynamic load models and supporting documentation)
3
Review Coordination
Interconnecting TSP/DSP coordinate responsibility for reviewing submission materials, determine the applicable Eligibility/Entry Path, and prepare the LCP2. Review responsibility and completion status are tracked within the LIF
4
Validation and Completeness Review
Interconnecting TSP/DSP, as applicable, review submitted materials, validate completeness against the applicable eligibility requirements, and document status/comments in the LIF
5
Final Package Assembly
Interconnecting TSP/DSP, as applicable, finalize the coordinated eligibility package and confirm all applicable items are complete within the LIF
7
Submission to ERCOT
Interconnecting TSP submits the final coordinated eligibility package to ERCOT via email with the Interconnecting DSP and ILLE copied, where applicable
8
ERCOT Initial Eligibility Assessment
ERCOT performs validation of the Batch Zero eligibility package, including attestations, TSP/DSP confirmations, and submission completeness
9
Until Jul 10
Jul 10- Jul 24
Jul 24-Aug 7
Aug 7-Aug 31
ILLE provides administrative corrections, clarifications, or non-material supplemental information to address issues identified during TSP/DSP review1
6
Package Reconciliation and Follow-up
ERCOT notifies ILLEs of identified dynamic model or data deficiencies. ILLEs submit corrected models, updated parameters, or supplemental technical information during the cure period
10
Dynamic Model Deficiency Resolution
ERCOT Final Eligibility Validation
ERCOT finalizes Batch Zero eligibility determinations following resolution of outstanding dynamic model and data deficiencies
11
1. The post–July 10 validation period is intended to address administrative corrections, clarification requests, and minor submission errors identified during TSP/DSP review (e.g., typos or incorrect references). It is not intended to allow submission of materially missing eligibility items or satisfaction of requirements that were not completed by the applicable July 10 deadline (e.g., posting financial security, executing required commitments, or completing required attestations) | 2. Including selection of the applicable Entry Path, incorporation of LLIS/RPG/PBRP study information, transmission upgrade and TPIT data, and calculation of the resulting modeled load schedule

## Slide 7: Batch Zero ERCOT communications and submission channels
LLWG_Feedback@ercot.com for General Batch Zero Questions
Channel for general implementation questions, stakeholder feedback, and process clarification requests related to the Batch Zero Large Load interconnection framework
Supporting materials and forms will be published on the Large Load Integration webpage
LargeLoadInterconnection@ercot.com for Existing LLIS Process Questions
Channel for questions related to the legacy LLIS process (e.g., ongoing study reviews, dynamic model submissions, and existing interconnection study coordination)
BatchZero@ercot.com (under development) for Formal Batch Zero Submissions
Channel for submission of completed Batch Zero eligibility packages by the designated Interconnecting TSP, with notification to the applicable DSP and ILLE through copied submission correspondence, as appropriate
NOTE: ERCOT plans to assign a new unique Batch Zero identifier (“BZ ID”) to each submitted Large Load project for Batch Zero intake and tracking purposes. These identifiers will serve as the primary reference number for Batch Zero implementation activities