## Sheet1
TDTMS Agile Enhancement List of Proposed Changes |  |  | rev 05042026
Date | System | Description of Issue /Suggestion | Submitted By | NOTES | Completed
2024-12-01 | ERCOT MIS - Find Transaction | Adding 'key dates' back which represent when the transaction was submitted | TDTMS | included in MIS Project
2024-12-01 | ERCOT MIS - Find Transaction | Providing a hyperlink to a list of reject codes | TDTMS | included in MIS Project
2024-12-01 | MarkeTrak | Addition of ESI within automated subject line of escalation email | TDTMS | Complete
2024-12-01 | MarkeTrak | alllow REPs to utilize the same Switch Hold removal reject codes as TDSPs yet not changing the workflow | TDTMS | Group for an SCR
2025-08-01 | MarkeTrak User's Guide | remove the reference to "waiting 5 days to submit" in section 4.3 - Usage & Billing - Dispute add the reference "waiting 5 days to submit" in section 4.2 Usage & Billing - Missing | Tomas Fernandez | Complete 2/23/26
2025-08-01 | MarkeTrak | Add validations to Usage & Billing - Missing submittals: invalid start/stop cycle date not scheduled | TDMTS - small group | LOE is estimated as high - project would be required - group for an SCR
2026-02-19 | MarkeTrak | Auto assign TDU for Usage & Billing MTs | Tomas Fernandez | Group for an SCR
2026-02-19 | MarkeTrak | Label "agree" button for IAG MT from Losing REP | TDTMS | LOE is low if text on a button is changing as opposed to new transition: WSDL change required: ACTION: Sheri to secure screenshot of 'button" where verbiage may change
2026-03-23 | MarkeTrak API | ability to upload file attachments and download reports via MT API | Tomas Fernandez | tabled with enterprise API project
2026-05-04 | ERCOT MIS - API | ability to utilize the */wildcard feature in Find ESI search similar to GUI | Sheri Wiegand | Dave Michelson will inquire