## Batch Zero FAQs
Batch Zero Readiness FAQs
Current as of June 11, 2026 (Version One)
Disclaimer: This question-and-answer document is provided solely for informational purposes. In the event of any conflict with the ERCOT Protocols or Planning Guide, those authorities shall govern. ERCOT may update or revise answers as it receives additional questions and information. Nothing in this document constitutes an interpretation or guidance by ERCOT, or is otherwise binding, in proceedings at the Public Utility Commission of Texas, including Project No. 58481, Rulemaking to Implement Large Load Interconnection Standards Under PURA § 37.0561. Unless otherwise noted, capitalized terms are defined consistent with the ERCOT Protocols.
Macro-topic | ID | Question | Answer
Batch Zero eligibility and qualifications | 1 | Do already energized loads automatically qualify for inclusion in Batch Zero? | Under Section 9.2.1.1(1)(a) and (b), already energized loads are included as base load subject to the Interconnecting Large Load Entity (ILLE) and applicable Interconnecting Transmission Service Provider (TSP) or Interconnecting Distribution Service Provider (DSP) providing necessary modeling and technical information. The ILLE and TSP or DSP should consult the Load Information Form to determine what additional information is required for modeling purposes.
| 2 | Does all long lead equipment mean the ILLE's substation equipment, all load facility equipment, or both? | All long lead equipment as used in Section 9.2.1.1(1)(e)(iii) includes the ILLE's interconnection equipment, e.g., transformers and breakers.
| 3 | What is the definition of an end-use customer in Section 9.2.1.1(1)(e)(v)? | The end-use customer is the customer that will take electric service at the site of the Large Load development. The ILLE must be able to demonstrate an existing legally binding connection linking itself, the Large Load development, and the ultimate retail customer.
| 4 | Is a purchase and sale agreement that includes a termination right, typically referred to as a due diligence period, valid for purposes of the site control criteria? | The inclusion of a right to terminate in a purchase and sale agreement remains a valid purchase and sale agreement for purposes of PGRR145.
| 5 | Can ERCOT provide confirmation that a Large Load meets the eligibility criteria for its selected inclusion path before August 7, 2026? | ERCOT will evaluate submitted information and notify Interconnecting DSPs and TSPs of each Large Load’s classification and Batch Zero inclusion status by August 7, 2026. However, ERCOT strongly encourages Interconnecting DSPs and TSPs to provide the documentation identified in PGRR145, NPRR1325, and the ERCOT Large Load Integration page as early as possible. ERCOT will endeavor to review submitted materials and provide prompt feedback on the submission.
Study process and timelines | 6 | What are the key deadlines for inclusion in Batch Zero? | The primary Batch Zero milestones are: *May 28, 2026 – Last date a study submitted to ERCOT is guaranteed review by July 10 *July 10, 2026 – Deadline for ILLEs seeking treatment as base load to have satisfied the applicable Batch Zero eligibility requirements, including submission of any required materials, including dynamic models and dynamic data packages where applicable *July 24, 2026 – Deadline for Interconnecting DSPs/TSPs to submit to ERCOT all required Batch Zero materials and for TSPs to submit stability-study impact determinations, if applicable *August 7, 2026 – ERCOT deadline by which it will notify TSPs/DSPs of Batch Zero inclusion and classification outcomes and dynamic model deficiencies *August 31, 2026 – Final deadline to resolve outstanding dynamic model/data deficiencies; Large Loads with unresolved issues are excluded from Batch Zero
| 7 | How should a Large Load proceed if its eligibility pathway changes near the July 10 deadline? | It depends. Section 9.3.1(2) permits an ILLE to reconcile its financial security if its classification changes from base load to studied load. Where additional financial security is required due to reclassification, the ILLE generally has seven Business Days to satisfy the applicable requirement. Failure to satisfy the required financial security obligations may result in exclusion from Batch Zero. There is not a reconciliation period that works in reverse. Therefore, an ILLE that is unsure whether it will qualify as base load or studied load should submit as if it will be base load, and take advantage of the reconciliation period should ERCOT classify it as studied load.
| 8 | Should outdated or no-longer-achievable Load Commissioning Plans (LCPs) be updated before submission? | The LCP should reflect the Large Load's current information at the time of submission. If the Large Load's schedule for connecting the Large Load in increments has changed, the LCP should be updated accordingly. ERCOT has indicated that it expects a practical and achievable LCP rather than a schedule that is known to be outdated or no longer attainable.
| 9 | If a Large Load has not yet started the scoping process, can it still realistically qualify for Batch Zero? | Large Loads that have not yet completed a kickoff meeting by May 21, 2026 face a highly compressed timeline to complete scoping, studies, ERCOT review, and any required restudies before the July 10, 2026 sunset. The current Planning Guide allows the TSP, ERCOT, and any directly affected TSPs up to 35 Business Days to approve a study scope after a kickoff meeting is held. ERCOT will make every effort to review study scopes through the July 10, 2026 sunset. Even so, Large Loads that have not had a kickoff meeting before May 21, 2026, may not get an approved scope prior to July 10, 2026.
| 10 | Will ERCOT continue conducting study reviews through July 10, 2026? | ERCOT is committed to continuing study reviews throguh the July 10, 2026 sunset date. However, ERCOT cannot guarantee that studies submitted after May 28, 2026 will be reviewed before July 10, 2026.
| 11 | Are Large Loads guaranteed approval if the Transmission Service Provider submits studies before the July 10 cutoff? | No. Studies submitted before July 10, 2026 are not guaranteed approval. ERCOT will continue reviewing studies under the current LLIS process through July 10, but submitted studies must still satisfy the applicable Planning Guide requirements. If ERCOT identifies deficiencies, incomplete information, or material changes to study assumptions, then clarification or restudy may be required. Additionally, ERCOT cannot guarantee that new or updated study reports submitted after May 28, 2026 will be reviewed by July 10, 2026.
| 12 | For base load, what information can be corrected after July 10 versus considered missing or incomplete? | ERCOT may allow cure of identified dynamic model deficiencies through August 31, 2026. In addition, ERCOT and the Interconnecting TSP/DSP may permit administrative corrections, clarification requests, or minor submission errors identified during the review process (e.g., typographical errors or incorrect references). However, the post–July 10 review period is not intended to allow submission of materially missing eligibility items or completion of requirements that were not satisfied by the applicable July 10 deadline (e.g., financial security, required commitments, or required attestations). Failure to resolve identified dynamic model deficiencies by August 31, 2026 results in removal from Batch Zero.
| 13 | How does ERCOT handle studies that become invalid because of other Large Loads meeting milestones ahead of the studied Large Load? | PGRR145 establishes a formal validation framework in Section 9.2.1.4. ERCOT will evaluate whether prior studies remain valid by assessing whether Large Loads with earlier approval dates were included within the applicable study area assumptions. Large Loads whose studies no longer reflect the evolving system conditions may be reclassified into the “load to be studied and allocated” category.
Commitment and notice requirements post-Batch Zero Interconnection Study | 14 | What is required to satisfy the commitment requirements under the Batch Zero Process? | Following completion of the Batch Zero Interconnection Study, an ILLE with studied load must execute an interconnection agreement meeting the requirements of P.U.C. SUBST. R. 25.194 and accept the allocated peak Demand and schedule reflected in the updated Load Commissioning Plan (LCP). The applicable Interconnecting DSP or TSP must then provide ERCOT a notarized attestation confirming the required commitments were satisfied by the applicable deadline. Additional requirements apply for projects electing PCLR or WLPUN treatment. Large Loads that fail to satisfy the applicable commitment requirements are excluded from the Batch Zero Refinement Study and are not eligible for Initial Energization unless included in a future batch process.
Dynamic model and technical submission requirements | 15 | What dynamic model information is required for Batch Zero participation? | By July 10, 2026, the ILLE must provide ERCOT and the Interconnecting TSP dynamic data, including the necessary models, parameters, and supporting technical documentation required for accurate representation of the Large Load. The data must be compatible with the version of the planning and operations model software specified in the Dynamics Working Group Procedure Manual in effect on March 4, 2026. If a prior dynamic stability study exists, the Interconnecting TSP must also provide ERCOT by July 24, 2026 a written determination regarding whether the submitted dynamic data is expected to adversely impact the prior study results. ERCOT has prepared a form Interconnecting TSPs must use to inform ERCOT whether a prior stability study was conducted, and if it was, whether the updated dynamic data adversely impacts the study results. ERCOT may notify the ILLE of any deficiencies by August 7, 2026, with a cure period extending through August 31, 2026.
| 16 | Will ERCOT provide confirmation when model submissions are received? | PGRR145 does not expressly require ERCOT to provide formal receipt confirmations for dynamic model submissions. ERCOT is currently developing the submission and communication process for Batch Zero implementation, including package tracking and confirmation procedures. Stakeholders should expect additional guidance as implementation activities progress.
| 17 | What happens if a Large Load changes its load technology, configuration, or operating characteristics after studies have been completed? | ERCOT may evaluate whether the change adversely impacts prior study assumptions, dynamic model performance, or eligibility determinations. Material changes may require additional review and could affect study validity or Batch Zero classification.
| 18 | For co-located load and generation projects, what should be included in the dynamic model submission? | For co-located projects, the submitted dynamic model should include sufficient information to accurately represent both the Large Load and the associated generation configuration, including all relevant operating characteristics necessary for ERCOT to evaluate stability and system impacts. Additional generation-related modeling requirements may also apply under Section 6.9 and the applicable FIS requirements.
| 19 | Who is responsible for submitting dynamic models to ERCOT — the ILLE or the TSP? | Under Section 9.2.2(3), the ILLE is responsible for providing the dynamic data, models, parameters, and supporting technical documentation to both ERCOT and the Interconnecting TSP by July 10, 2026. If a prior dynamic stability study exists, the Interconnecting TSP must also provide ERCOT by July 24, 2026 a written determination regarding whether the submitted dynamic data is expected to adversely impact the prior study results. ERCOT has prepared a form Interconnecting TSPs must use to inform ERCOT whether a prior stability study was conducted, and if it was, whether the updated dynamic data adversely impacts the study results.
| 20 | What happens if required dynamic model information is incomplete by the July 10 deadline? | Under Section 9.2.2(3)(a), if ERCOT determines that submitted dynamic data is deficient, ERCOT must notify the ILLE no later than August 7, 2026. The ILLE then has until August 31, 2026 to cure the deficiency. Failure to resolve the deficiency by August 31, 2026 results in removal of the associated Large Load from the Batch Zero Interconnection Study.
| 21 | Will a Large Computational Load's (LCL) allocation be impacted if the LCL is unable to update its model to show compliance with NOGRR282 prior to the end of Batch Zero? | NOGRR282 compliance is separate and distinct from Batch Zero timelines and eligibility. If NOGRR282 is approved by the PUCT, a LCL will be required to comply with the voltage and frequency ride-through requirements of NOGRR282 unless the LCL is entitled to an exemption as provided in the NOGRR. A LCL subject to study and allocation under Section 9.2.1.2 in Batch Zero that is not exempt from the ride-through requirements will need to submit models that demonstrate compliance with those requirements to qualify for a QSA after Batch Zero. A LCL that is included in Batch Zero as base load should review NOGRR282 and the QSA timelines to determine whether it is subject to NOGRR282 compliance. ERCOT is highlighting the NOGRR282 performance requirements to inform LCLs about the relevant timing; however, this does not affect the allocation process for Batch Zero.
Communications and process management | 22 | What email address or communication channel should stakeholders use for Batch Zero questions and submissions? | Interconnecting TSPs or DSPs and ILLEs should send Batch Zero-related questions and submissions to the following email addresses: -LLWG_Feedback@ercot.com for general Batch Zero implementation questions, stakeholder feedback, and process clarification requests (Interconnecting TSPs and DSPs should not use this email address for eligibility submission packages); - LargeLoadInterconnection@ercot.com for existing LLIS process questions, including ongoing study reviews, dynamic model submissions, and interconnection study coordination (will cease operation after July 10); and - BatchZero@ercot.com (under development) for formal Batch Zero eligibility submissions by the designated Interconnecting DSP or TSP, as applicable.
| 23 | How will ERCOT and TSPs standardize subjective validation criteria across Large Loads? | ERCOT, in consultation with Interconnecting DSPs and TSPs, is continuing to develop implementation guidance regarding validation standards and supporting documentation requirements. ERCOT may request supporting materials or perform additional verification. ERCOT has prepared attestation and Load Information Forms to standardize the intake of information.
| 24 | Should the Interconnecting TSP copy the ILLE on Batch Zero submission communications with ERCOT? | Copying the ILLE on submission-related communications would be considered good practice. Additional guidance regarding communication expectations between ERCOT, Interconnecting DSPs/TSPs, and ILLEs may be provided during implementation. However, ILLEs should not send attestations or other information directly to ERCOT. Information should be sent through the Interconnecting DSP and TSP, as applicable.
| 25 | Will ERCOT provide provisional feedback before PUCT approval of PGRR145? | ERCOT may review submitted materials and provide preliminary feedback regarding completeness, deficiencies, or additional information needs. However, final Batch Zero eligibility determinations and classification decisions are contingent upon the PUCT's approval of the revision requests and completion of ERCOT's validation process.
Financial security and cost responsibility | 26 | Is Batch Zero financial security refundable? | PGRR145 does not address refundability of financial security. For information about the timing and amount of refundable security, stakeholders should refer to proceedings at the Public Utility Commission of Texas, including Project Nos. 58481, Rulemaking to Implement Large Load Interconnection Standards Under PURA § 37.0561, and 59142, Review of ERCOT's Interconnection Processes for Large Loads.
| 27 | Who is responsible for facility studies, contribution in aid of construction (CIAC) calculations, and related upgrade cost estimates? | Interconnecting DSPs and TSPs are responsible for conducting any required facility studies, estimating direct interconnection costs and applicable CIAC obligations, and providing an estimate of upgrade costs. ERCOT will not perform facility studies as part of the Batch Zero Interconnection Study. ILLEs should coordinate directly with their Interconnecting DSP or TSP regarding facility study scope, timing, cost estimates, and financial obligations.