## Slide 1
Flight Testing Update
David Michelsen
Manager Retail Operations
Retail Market Subcommittee
06/25/2026

## Slide 2: Flight 0626 Preview
Market Notice for Flight 0626 was sent on 03/18/26
Market Notice first reminder for Flight 0626 was sent on 04/08/26
Market Notice final reminder for Flight 0626 was sent on 04/29/26
Flight 0626 application deadline was 04/15/26
Flight 0626 signup deadline was 05/06/26
Connectivity testing began on 05/13/26
Day 1 transactions began on 06/08/26
Flight 0626 was scheduled to complete on 06/22/26
Contingency period is scheduled to conclude 06/26/26
Retail Market Subcommittee
06/25/26

## Slide 3: Flight 0626 Details
As of 06/22/2026
12 New CRs are testing in Flight 0626 including 9 DUNS+4 CRs
Of the 3 New CRs, 1 of the New CRs have successfully completed testing and the 9 DUNS+4 CRs have successfully completed testing
6 Existing CRs are testing in Flight 0626 including 2 Service Provider changes and 4 adding territories
Of the 2 Existing CRs changing Service Providers, both have successfully completed testing and the 4 Existing CRs adding territories, all have successfully completed testing
Retail Market Subcommittee
06/25/26