## Sheet1
TDTMS Agile Enhancement List of Proposed Changes |  |  | rev 061826
Date | System | Description of Issue /Suggestion | Submitted By | NOTES | Completed
2024-12-01 | ERCOT MIS - Find Transaction | Adding 'key dates' back which represent when the transaction was submitted | TDTMS | included in MIS Project
2024-12-01 | ERCOT MIS - Find Transaction | Providing a hyperlink to a list of reject codes | TDTMS | included in MIS Project
2024-12-01 | MarkeTrak | Addition of ESI within automated subject line of escalation email | TDTMS | Complete
2024-12-01 | MarkeTrak | alllow REPs to utilize the same Switch Hold removal reject codes as TDSPs yet not changing the workflow | TDTMS | Group for an SCR
2025-08-01 | MarkeTrak User's Guide | remove the reference to "waiting 5 days to submit" in section 4.3 - Usage & Billing - Dispute add the reference "waiting 5 days to submit" in section 4.2 Usage & Billing - Missing | Tomas Fernandez | Complete 2/23/26
2025-08-01 | MarkeTrak | Add validations to Usage & Billing - Missing submittals: invalid start/stop cycle date not scheduled | TDMTS - small group | LOE is estimated as high - project would be required - group for an SCR
2026-02-19 | MarkeTrak | Auto assign TDU for Usage & Billing MTs | Tomas Fernandez | Group for an SCR
2026-02-19 | MarkeTrak | Label "agree" button for IAG MT from Losing REP | TDTMS | LOE is low if text on a button is changing as opposed to new transition: WSDL change required: ACTION: Sheri to secure screenshot of 'button" where verbiage may change
2026-03-23 | MarkeTrak API | ability to upload file attachments and download reports via MT API | Tomas Fernandez | tabled with enterprise API project
2026-05-04 | ERCOT MIS - API | ability to utilize the */wildcard feature in Find ESI search similar to GUI | Sheri Wiegand | Dave Michelson will inquire
2026-06-15 | MarkeTrak | AI feature within tool (i.e. co-pilot) to utilize for MarkeTrak reporting analysis | TDTMS small group
2026-06-08 | MarkeTrak - Usage & Billing Dispute | • Move the “Dispute Category” dropdown directly under “Original Tran ID” - ensures users select the primary driver of the dispute before entering dependent fields • Based on the selected Dispute Category, dynamically filter the “Tran Type” dropdown- only display valid transaction types applicable to that dispute category • When a Dispute Category is selected: Auto-populate the STARTTIME and STOPTIME fields with default values of 00:00:00 -- Allow users to adjust only when necessary | Edelmira Pena- Revolution Energy
2026-06-15 | MarkeTrak | ability to cleanse aged active MTs in mass | Jesse Macias - AEP
2026-05-25 | MarkeTrak | If the MVI is received on the same day the MVO is completed, and 867_03F with the new REF ID has been sent, ERCOT should allow the Siebel status of the MVO to be changed from "Completed" to "Cancelled" without CR approval. | CNP- Kimmy Ng | We currently need to create a Marketrak for Siebel status update, and some CRs may take days or weeks to respond.
2026-05-29 | MarkeTrak | Allow backgound reporting to include archive issues greater than 7 months when selecting live return data | CNP - Monica Jones
2026-06-01 | MarkeTrak | Allow issue visibilty of MarkeTrak issues for 12 months in the GUI | CNP - Monica Jones | Currently MarkeTrak issues greated than 7 months are not visible in the GUI
2026-06-01 | MarkeTrak | Update background report parameters to include total volume of data as submitted in the report parameters | CNP - Monica Jones | If report results returns a large volume of data the user is unable to view all the data at once.
2026-06-08 | MarkeTrak | Enhance/Improve and expand the Mass update process | CNP -Ester Floyd | Primarly the Bulk Insert process
2026-06-08 | MarkeTrak | Ability to include attachments via API | CNP - Karen Malkey | Primarly for the "Submits"
2026-06-08 | MarkeTrak | Include ability to escalation on the TDSP submit | CNP - Karen Malkey | When TDSP submits a MT to the CR there is escalation email sent to the CR for aged issues/ no updates received
2026-06-08 | MarkeTrak | If the current in-house API is replaced ensure the new solution is designed the same to avoid the need for having to add customized changes | CNP - David Fimble
2026-06-08 | MarkeTrak | Allow user capability to run reports and retrieve archived issues outside of background reporting | CNP - Karen Malkey
2026-06-08 | MarkeTrak | Improve process to retrieve large volume of MT data greater than 12 months | CNP - Karen Malkey | Current process is request submitted to ERCOT for data and ERCOT provides access to dsignated portal to retrive the requested data
2026-06-08 | MarkeTrak | More user defined reporting to elimate ERCOT faciliating the data | CNP - Kathy Scott
2026-06-08 | MarkeTrak | Access to Historical MT Issues/Bulid in a plan to access open MT issues | CNP -Karen Malkey/Kathy Scott | What is the transition plan and how does that work
2026-06-15 | MarkeTrak | Enhance the MT escalation contact list to display only active users | CNP - Chris Dominguez | Limit the escalation contact list to only show Issue Escalation "Enabled"