## Slide 1: Project Prioritization Update Technical Advisory Committee (TAC) Troy Anderson ERCOT Portfolio Management July 29, 2026
Key Takeaway
11 Revision Request projects were deemed Critical or High priority at June/July PRS meetings
Outline:
2026 Aging Revision Request Prioritization Update
  Items deemed Critical or High priority
Appendix
  Status of High Priority items from 2025
  Status of other Revision Request projects in-flight

## Slide 2: 2026 Aging Revision Request Project Prioritization – Stats
Tier | June 2026 | July 2026
1 – Critical | 3 | 3
2 – High Priority | 2 | 8
3 – Medium Priority | 1 | 38
4 – No Action | 9 | 13
5 – Candidate for Removal | 2 | 3
TBD | 50 | 0
Total | 67 | 65
Excel files posted to June and July PRS meeting pages
  Retained notes from prior year prioritization meetings
  Updated based on June PRS discussion
  Added submitter name
65 items on the list – changes from June to July:
  Dropped from list
    SCR829 (project started)
    NPRR1323 (added to in-flight NPRR1290 project)
    OBDRR055 (O&M effort went live)
  Added to list
    NPRR1326 IA completed
Ongoing Activity:
  ERCOT Portfolio Management is evaluating timeline options for the 11 Critical and High priority items
  Outreach on “No Action” and Removal candidates
  Reminder: “Removal” requires a new NPRR to strike existing gray boxes

## Slide 3: Aging Revision Request Project Status – 2026
11 Revision Request projects were deemed “Critical” or “High” at 2026 Prioritization discussion
Status | Revision Request | Additional Information
Critical | NPRR1309 – Board Priority - Dispatchable Reliability Reserve Service Ancillary Service | Project started on 7/22/2026
 | NPRR1328 – Establishment of Generation Firming Program | On July 2026 TAC agenda
 | PGRR145 – Batch Zero Process for Large Load Interconnections | 2027 project for PCLR portion
High | NPRR826 – Mitigated Offer Caps for RMR Resources | Bundle w/NPRR1342 (at WMS)
 | NPRR1004 – Mitigated Offer Caps for RMR Resources | Starting in next couple of weeks
 | NPRR1171 – Requirements for DGRs and DESRs on Circuits Subject to Load Shedding | Bundle w/NPRR1213
 | NPRR1213 – Allow DGRs & DESRs on Circuits Subject to Load Shed to Provide ECRS | Bundle w/NPRR1171
 | NPRR1214 – Reliability Deployment Price Adder Fix to Provide Locational Price Signals, Reduce Uplift and Risk | Tabled at PRS, pending completion of IA
 | NPRR1264 – Creation of a New Energy Attribute Certificate Program | Approved by PUCT on 7/9/2026
 | NPRR1296 – Residential Demand Response Program | Tabled at WMS and RMS
 | NPRR1307 – Revised Definition of Mitigation Plan | Approved by PUCT on 7/9/2026

## Slide 4: Appendix

## Slide 5: Aging Revision Request Project Status – 2025
10 Revision Request projects were deemed “High Priority” at August 2025 Prioritization Workshop
Status | High Priority Revision Request Projects | Additional Information
Complete | NPRR1234 – Interconnection Requirements for Large Loads and Modeling Standards for Loads >=25MW | System changes implemented in 3 phases Remaining gray box: Large Load Interconnection Study (LLIS) fee
 | NPRR1277 – Revisions to EAL Formula | Went live on 3/2/2026
In-Flight | NPRR1188 – Implement Nodal Dispatch and Energy Settlement for CLRs | January 2027 go-live target (w/NPR1244)
 | NPRR1198 – Congestion Mitigation Using Topology Reconfigurations | September 2026 go-live target
 | NPRR1238 – Registration of Loads with Curtailable Load Capabilities | Q4 2026 go-live target
 | NPRR1244 – Clarification of CLR Primary Frequency Response Responsibilities | January 2027 go-live target (w/NPR1188)
 | NPRR1281 – Improvements to Alternate FFSS Resource Designation | September 2026 go-live target
Pending Start Approval | NPRR1091 – Changes to Address Market Impacts of Additional Non-Spin Procurement | Expected to be part of Reliability Deployment Price Adder (RDPA) analysis
 | NPRR1004 – Load Distribution Factor Process Update | July 2026 project start
Workaround in Place | NPRR1216 – Implementation of Emergency Pricing Program | No action at this time
Key Takeaway: 10 High Priority RR projects tracked; 2 complete, 5 in-flight, 2 pending approval, 1 workaround

## Slide 6: Aging Revision Request Project Status
Updates on other Revision Request projects
Key Takeaway: Other Aging Revision Request projects are being actively worked
Status | Revision Request | Additional Information
In-Flight | NPRR936 – CRR Account Holder Limits | Q1 2027 go-live target (w/NPRR1288)
 | NPRR1201 – Limitations on Resettlement Timeline & Default Uplift Exposure Adjustments | December 2026 go-live target
 | NPRR1288 – Remove Multiple Month Transactions in CRR Auctions | Q1 2027 go-live target (w/NPRR936)
 | NPRR1290 – Gap Resolutions and Clarifications for the Implementation of RTC+B | August 2026 go-live target (w/NPRR1323)
 | NPRR1303 – Modernize Submission of Declarations of Natural Gas Pipeline Coordination | September 2026 go-live target
 | NPRR1323 – Correction to Inadvertent Removal of Real-Time MCPC Capping for NPRR1290 Phase 2 | August 2026 go-live target (w/NPRR1290)
 | PGRR127 – Addition of Proposed Generation to the Planning Models | Late Q3 / early Q4 go-live target
 | SCR820 – Operator Real-Time Messaging During Emergency (RTOC) | June 2026 software implementation 2027 effective date (NPRR pending)
 | SCR829 – API for the NDCRC Application | Go-live target TBD (maybe in late 2026)

## Slide 7: Questions/Comments?
Troy.Anderson@ercot.com