## Slide 1: Comprehensive Transmission Planning and Batch 1+
July 29, 2026
Program update and stakeholder engagement plan
Presentation to the Technical Advisory Committee

## Slide 2: ERCOT is pursuing an integrated Comprehensive Transmission Planning framework
TSP engagement
Stakeholder engagement and public comment (e.g., via monthly updates, to define stakeholder gates)
1. TPL and Alternative Project Analytics 2. Short circuit
RIOO
MOD, TPIT
Base Load Economic Forecast, TSP RFI
Batch study
Post commitment CTP Year N Model
Final model snapshot
Gen. data
Topology data
Remaining load data
(medium, economic)
Large load data (from TSPs)
ILLE submitting large load request
Commitment window
Actionable Transmission Plan
Endorsed Transmission Plan
TPL1
Dynamic
Economic
SC2
Single source of truth
Integrated batch study + CTP modeling / study
Data inputs
Batch study
CTP modeling & study
Endorsement
Streamlined endorsement
RPG-like analysis
Reliability assessment

## Slide 3: Batch 1+: Initial Batch 1+ Revision Requests priorities span four focus areas to continue advancing the Large Load framework
Initial ERCOT priorities for Revision Request development
Reconsider ERCOT–ILLE–TSP relationships for on-ramping Large Loads
Establish a framework for resubmitting unmet Large Load ramp requests across Batches
Define carry-forward treatment for non-committed Large Loads across Batch cycles
Establish a governance framework for post-study project changes (e.g., delayed in-service date or end-use technology changes)
Large Load Interconnection
Refine the financial security methodology for transmission upgrades and direct interconnection costs
Financial and reporting
Modernize Batch technical study scope, responsibilities, and model governance
    Short circuit studies
    SSO studies
    Dynamic model change evaluation
Technical study framework
Enhance Large Load reporting and confidentiality provisions
Enhance Bring Your Own Generation (BYOG) framework
Enhance the Provisional Controllable Load Resource (PCLR) framework
Market rules & operational enhancements

## Slide 4: CTP scope: CTP will integrate batch process, streamline modeling and planning processes, and define clear governance handoffs
Scope for Comprehensive Transmission Process development
Define the future role of Batch within the annual planning cycle
Determine the technical study required to support Large Load commitment decisions
Design the transition from Batch study outputs to the CTP planning process
Batch-CTP integration
Establish a planning-led source of truth for planning models and assumptions
Develop a standardized planning model framework and taxonomy
Standardize planning cases, assumptions, and study methodology
Clarify ERCOT and TSP responsibilities for case development, model conditioning, and study execution
Modeling and planning
Define the stakeholder engagement and endorsement process for CTP
Clarify ERCOT and TSP roles in project identification and solution development
Establish governance, milestones, and response timelines for transmission plan development
TSP/stakeholder process and governance

## Slide 5: Roadmap: Path to Batch 1+ and CTP Board approval by February 2027
Forums
ROS
2026
2027
Q3
Q4
Q1
Jul
Aug
Sep
Oct
Nov
Dec
Jan
PRS
Workshops and working groups
Formally present CTP and Batch 1 PGRRs/NPRRs for approval
ERCOT Board
Objective
Interview TSP planning staff on CTP scope
Engage with Protocol Revisions Subcommittee on NPRR(s)
Engage with Reliability and Operations Subcommittee engagement on PGRR(s)
TAC
Review/endorse combined NPRR/PGRR package for Board approval
Update to the Board 12/7-8
Presentation to the Board 2/8-9
TAC 10/28
TAC 11/18
TAC 1/20
ROS 10/1
ROS 11/5
ROS 12/3
PRS 10/14
PRS 11/11
PRS 12/9
PUCT OM
Provide updates to Commission on progress/emerging policy considerations (specific sessions to be selected)
OM 8/20
OM 9/11
OM 9/18
OM 10/1
OM 10/15
OM 11/5
OM 11/19
OM 12/3
OM 12/17
Conduct stakeholder workshops on CTP process design and Batch 1+
Stakeholder engagement
Update
Targeted endorsement date
July 16 – late August
Workshop 1 8/27
LLWG
Engage with Large Load Working Group on Batch 1+
LLWG 8/21
TAC 8/28
LLWG 9/17
LLWG 10/15
LLWG 11/19
LLWG 12/17
Workshop 2 9/10
Draft scope from ERCOT
Workshop 3 9/24
Workshop 5 10/29
Workshop 4 10/8
Further scoping details discussion
Details of design elements discussion (ahead of Oct 1 Revision Requests)
Review Revision Requests and market comments
2/8 Board approval
10/1 File initial Revision Requests
7/8 ERCOT market notice
Early Dec. Target RR approval
1/20 TAC approval
TAC 7/29