## Slide 1: Batch Zero Update TAC July 29, 2026

## Slide 2: Batch Zero: upcoming milestones
2026
Jul
Aug
July 10
July 10
  Last day ERCOT reviews studies under the Large Load Interconnection Study (LLIS) process; Large Loads without a qualifying study by the end of the day July 10 are not eligible for inclusion in Batch Zero, no extensions or cure period
  Interconnecting Large Load Entity (ILLE) dynamic model data due to ERCOT; ILLEs that did not submit a dynamic model for their Large Load are not eligible for Batch Zero
August 7
  ERCOT issues Batch Zero classifications no later than August 7
  Classification notices initiate the optional dispute period, if applicable
  ERCOT notifies ILLE of any deficient dynamic data
  Final Batch Zero eligibility package submission deadline; if not submitted, Load is not eligible for Batch Zero (Submissions may be made prior to July 24)
  Financial security posting confirmed by T(D)SP
  Begins when ERCOT notifies the T(D)SP that a Large Load has been reclassified from Base Load to Studied Load
  Up to 17 business days from ERCOT's classification notice:
    Notify. T(D)SP has 2 business days to notify the ILLE
    Dispute process (optional). ILLE has 3 business days to dispute the reclassification through its T(D)SP
    ERCOT, ILLE, and T(D)SP have 3 business days to resolve the dispute
  If unresolved, ERCOT's classification stands
  Reconcile Security. ILLE has 7 Business Days to post any shortfall needed to bring its financial security to $50,000/MW & T(D)SP must inform ERCOT within 2 Business Days
  ILLE coordinates with T(D)SP to resolve ERCOT-identified dynamic model data deficiencies only
  Corrected data due back by Aug 31, no extensions granted under PGRR 145; Large Loads with unresolved dynamic model deficiencies are not eligible for Batch Zero study
  No later than September 2, ERCOT begins Batch Zero interconnection study
  ERCOT requests supporting documentation from T(D)SP for select ILLEs and conducts verification
  Large Loads that fail to demonstrate eligibility may be disqualified from Batch Zero
  Planning Guide Revision Request 145 becomes effective
Description
July 11
Milestone
LLIS review2
ERCOT classification notices
Reclassification dispute window and reconciliation period
Dynamic model data
Eligibility evidence review
PGRR145 becomes effective
T(D)SP package
  July 10, 2026 – April 9, 2027
Milestone
  Period/window
Timeline break
Eligibility gate1
2027
Apr
Projects that fail to submit required materials, resolve identified deficiencies, or demonstrate eligibility by the applicable eligibility gate may be removed or disqualified from Batch Zero
Loads that are already energized or included in a QSA remain eligible for Batch Zero without submitting a dynamic model
  August 7 – 31
Sept
  July 24
  August 7 – September 1

## Slide 3: Preliminary Overview of Batch Zero Eligibility
Key Takeaways
Approximately 205 GW of Large Load is eligible for inclusion in Batch Zero based on existing studies
ERCOT will make final determinations of which loads are included in the study on or before August 7 and communicate the results by September 2
Chart: Large Load Requests (GW)
| Sum of Max MW
Eligible for inclusion as base load | 65.4101
Eligible for inclusion in Batch Zero. Base/studied load classification under ERCOT review. | 25.4849
Eligible for inclusion as studied load | 114.0348
Not eligible for inclusion in Batch Zero - dynamic model not received | 20.4566
Not eligible for inclusion in Batch Zero - no qualifying study | 274.3624
Not Included In Batch Zero – No Qualifying Study (315 Projects): These loads did not have an existing study that qualified them for inclusion in Batch Zero.
Not Included In Batch Zero – No Dynamic Model (47): These loads had one or more studies that made them eligible for inclusion but were removed when no dynamic model was submitted to ERCOT by July 10.
Eligible for Inclusion as Allocated Load (127): These loads have existing studies that make them eligible for inclusion as allocated load and submitted the required dynamic model data to ERCOT by July 10.
Eligible for Inclusion, Base or Allocated Load to be Determined (49): These loads have existing studies that make them eligible for inclusion in Batch Zero and submitted the required dynamic model data to ERCOT by July 10. ERCOT will review the studies according to Planning Guide 9.2.1.4(4) by August 7 to determine if the load will be treated as base load or allocated load.
Eligible for Inclusion as Base Load (150): These loads have existing studies that make them eligible for inclusion as base load and submitted the required dynamic model data to ERCOT by July 10.
Data as of July 28, 2026
NOTE: The following data is preliminary and only reflects eligibility for inclusion in Batch Zero. ERCOT will review all application materials and make final determinations of which loads are included in the study on or before August 7. ERCOT will communicate the results by September 2.