## Slide 1
Modeling Upgrade to CIM16: Application and Data Products
Joel Koepke
Aug 2026

## Slide 2: Overview – Upgrading from CIM10 to CIM16
ERCOT produces Network Models following CIM standards and in an XML format
  Since 2010, the Network Model Management System (NMMS) has produced models using the CIM10 schema (with customizations)
  In 2021, a process was developed to translate CIM10 models into CIM16 allowing for downstream systems to upgrade their importers
ERCOT has begun a project to enhance NMMS to natively produce CIM16 model files
  Reduces the need for ERCOT-specific legacy code in vendor applications
  Officially started execution in August 2024
  Project completion is scheduled for Q1/Q2 2027
ERCOT will no longer produce CIM10 models after project completion

## Slide 3: CIM-Related Inputs/Outputs of NMMS

## Slide 4: Who/What is Affected?
Any processes utilizing files directly created from NMMS will need to prepare for an updated schema
Files include:
  MIS Secure:
    Redacted CIM Network Model - EMIL ID: NP3-450-SG
  MIS Certified:
    TSP Version of the CIM Network Model XMLs (via Citrix)
    Incremental CIM Change Requests XMLs (via Citrix/NMMS)

## Slide 5: Status Update and Key Events
Recently Completed:
  CIM10→CIM16 migration script
    Converts database structure from CIM10 to CIM16 format
  Testing of SCR813 “NMMS Jointly-Rated Equipment Coordination Confirmation”
      Brings additional awareness to model submissions that affect jointly-rated equipment
Now:
  Updating model redaction process for CIM16
  Updating internal tools and reports
Q4/Q1:
  Transition NMMS MOTE system to CIM16
  Provide TSP training on new system

## Slide 6: ERCOT CIM16 Project – Test Models
“Representative” previews of CIM16 models are posted ~quarterly to the MIS
  “Preview of Modified Redacted CIM Network Model” EMIL NP3-451-SG
  Created by converting a CIM10 XML file to a CIM16 XML file
  The final CIM16 schema will differ from the representative models
“Native” CIM16 models will be provided in Q3/Q4 2026
  To be created with CIM16 modeling application using migrated database
  First TDSP model will be provided by end of August
  First redacted model to be provided by end of September