## Slide 1: Project Update Troy Anderson ERCOT Portfolio Management August 12, 2026
Key Takeaways
Monthly project status update for ERCOT Portfolio Management presented to PRS on August 12, 2026
Covers 2026 release highlights, project updates, priority/rank recommendations, TWG update, and project planning
Outline:
Recent / Upcoming Project Highlights
2026 Release Targets
Other Project Updates
Priority / Rank Recommendations
Technology Working Group (TWG)
Aging Revision Request Prioritization

## Slide 2: Project Update Agenda
Recent / Upcoming Project Highlights
2026 Release Targets
Other Project Updates
Priority/Rank Recommendations for Revision Requests with Impacts
    NPRR1214 – Reliability Deployment Price Adder Fix to Provide Locational Price Signals, Reduce Uplift and Risk
    NPRR1329 – Resource Entity Requirements for Self-Limiting Facilities
    NPRR1338 – Restructure Long-Term Auction Sequence Auctions to Six Monthly Optimizations
Technology Working Group (TWG)
  Next meeting is 8/20/2026
Aging Revision Request Review and Prioritization
  Limited discussion this month
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Notes: Delete this slide before presenting

## Slide 3: Recent / Upcoming Project Highlights
2026 July Release – 7/29/2026-7/30/2026 Complete
  4 data products added to ERCOT Data Portal for public API access
    See 7/27/2026 market notice for details
2026 August Release – 8/26/2026-8/27/2026 In Flight
  NPRR1290 – Gap Resolutions and Clarifications for the Implementation of RTC+B
  NPRR1323 – Correction to Inadvertent Removal of Real-Time MCPC Capping for NPRR1290 Phase 2
2026 September Release – 9/30/2026-10/1/2026 In Flight
  NPRR1281 – Improvements to Alternate FFSS Resource Designation
  NPRR1303 – Modernize Submission of Declarations of Natural Gas Pipeline Coordination
2026 October Release – 10/28/2026-10/29/2026 In Flight
  NPRR1198 – Congestion Mitigation Using Topology Reconfigurations
  PGRR127 – Addition of Proposed Generation to the Planning Models
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2026 Release Targets - Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/28-1/29 | February 2/25-2/26 | March 3/25-3/26 | April 4/29-4/30 | May 5/27-5/28 | June 6/24-6/25
NPRR1234(c) PGRR131 NPRR1283 NPRR1285 NPRR1299 | NPRR1266 NPRR1277 | NPRR1287 Add’l Public Data Products in ERCOT Data Portal | CRR Historical Data Removal | NPRR1265 OBDRR055 | SCR820 PGRR145 NPRR1325
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R4
R5
R6
July 7/29-7/30 | August 8/26-8/27 | September 9/30-10/1 | October 10/28-10/29 |  | December 12/16-12/17
 | NPRR1290 NPRR1323 | NPRR1198 NPRR1281 NPRR1303 | NPRR1198 PGRR127 |  | NPRR1201
R7
R8
R10
R11
R3
R9
RTC+B Stabilization
NPRR1234(c) – RIOO changes for End-Use
Industry Classification to Loads
1/1
ü
ü
ü
ü
ü
2/1
SCR820 TO/QSE Testing (see TWG meetings)
3/2
E
E
ü
ü
3/1
ü
ü
Cipher Security Upgrades (see TWG meetings)
4/24
6/1
ü
ü
ü
E
E
NS
7/11
ü
ü
ü
E
NS

## Slide 5: Other Project Updates
NPRR936 – CRR Account Holder Limits – and –
NPRR1288 – Remove Multiple Month Transactions in CRR Auctions
  Go-live target = 2027 R2 (February)
  Gated to Execution in late July
NPRR1188 – Implement Nodal Dispatch and Energy Settlement for Controllable Load Resources – and – NPRR1244 – Clarification of Controllable Load Resource Primary Frequency Response Responsibilities
  Go-live target = 2027 R1 (January)
NPRR1238 – Voluntary Registration of Loads with Curtailable Load Capabilities
  Part of Large Load Curtailment Manager project
  Initial implementation in June 2026, full scope by end of 2026
  NPRR1238 portion expected to go-live late in 2026
NPRR1309 – Board Priority - Dispatchable Reliability Reserve Service Ancillary Service (DRRS)
  PUCT approved on 7/9/2026
  Project started in July 2026
NPRR1328 – Establishment of Generation Firming Program
  Pending Board approval in September
  Project began administrative activities in July 2026 – necessary to meet December 2027 go-live requirement
SCR829 – API for the NDCRC Application
  Project in Planning – likely early 2027 go-live

## Slide 6: Priority / Rank Recommendations for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1214 | Reliability Deployment Price Adder Fix to Provide Locational Price Signals, Reduce Uplift and Risk | 2027 | 4940 | $900k-$1.2M, 12-18 months Impacted Systems: MMS, S&B, Data Management, Registration
NPRR1329 | Resource Entity Requirements for Self-Limiting Facilities | 2028 | 5110 | $150k-$250k, 7-11 months Impacted Systems: RIOO, Registration, NMMS, MMS, Data Management, EMS
NPRR1338 | Restructure Long-Term Auction Sequence Auctions to Six Monthly Optimizations | 2027 | 4930 | $750k-$1.25M, 12-16 months Impacted Systems: CRR, Data Management ERCOT recommends bundling with NPRR1292
Recommendations for…
PPL Rank Information
Next 2026 Rank in Business Strategy = 4830 Next 2029 Rank in Business Strategy = 5300
Next 2027 Rank in Business Strategy = 4940 Next Rank in Regulatory = 450
Next 2028 Rank in Business Strategy = 5110

## Slide 7: Technology Working Group (TWG) - 7/23/2026 Meeting
Next TWG scheduled for 8/20/2026

## Slide 8: 2026 Project Planning
ERCOT understands that Market Participants need lead time to implement changes in their systems for many Revision Requests
Approved Revision Request Project Starts
  NPRR936 – CRR Account Holder Limits
  NPRR1188 – Implement Nodal Dispatch and Energy Settlement for Controllable Load Resources
  NPRR1198 – Congestion Mitigation Using Topology Reconfigurations
  NPRR1201 – Limitations on Resettlement Timeline & Default Uplift Exposure Adj
  NPRR1238 – Voluntary Registration of Loads with Curtailable Load Capabilities
  NPRR1244 – Clarification of CLR Primary Frequency Response Responsibilities
  NPRR1277 – Revisions to EAL Formula
  NPRR1281 – Improvements to Alternate FFSS Resource Designation
  NPRR1288 – Remove Multiple Month Transactions in CRR Auctions
  NPRR1290 Phase 2 – Gap Resolutions and Clarifications for RTC+B + NPRR1323
  NPRR1309 – Board Priority - Dispatchable Reliability Reserve Service Ancillary Service (DRRS)
  NPRR1323 – Correction to Inadvertent Removal of Real-Time MCPC Capping for NPRR1290 Phase 2
  SCR829 – API for the NDCRC Application
Revision Request Projects with Starts Delayed to Early 2027
  SCR818 Phase 2 – Changes to Incorporate GIC Modeling Data into Existing Modeling Applications
  SCR831 – Short Circuit Model Integration
Other priority Review Request projects may start in 2026 with a future year Go-Live
  Residential Demand (NPRR1296), Establishment of Generation Firming Program (NPRR1328)
Green Text: Deemed “High Priority” at 2025 Prioritization Workshop

## Slide 9: Aging Revision Request Project Prioritization Approach – Stats
Tier | June 2026 | July 2026 | Aug 2026
1 – Critical | 3 | 3 | 1
2 – High Priority | 2 | 8 | 7
3 – Medium Priority | 1 | 37 | 39
4 – No Action | 9 | 13 | 13
5 – Candidate for Removal | 2 | 3 | 3
TBD | 50 | 1 | 0
Total | 67 | 65 | 63
Posted Excel file details
  August v1 posted with latest updates
List will not be reviewed this month
Changes since July:
  Dropped from prioritization list
    NPRR1309 (project started)
    NPRR1328 (project started)
    NPRR1004 (project started)
  Added to list
    NPRR1338 IA completed
      Suggest “Medium” priority as are other projects in the CRR queue
  Moved items previously noted as “No Graybox” to the “No Action” category

## Slide 10: Aging Revision Request Project Prioritization Approach
Categorize RRs into “Tiers”
  Tier 1 Critical Must-have items (PUCT/Board directives, etc.)
  Tier 2 High Priority Highest priority after Tier 1
  Tier 3 Medium Priority Fit in without impacting Tier 1 and 2 projects
  Tier 4 No Action Not ready for immediate action
  Tier 5 Candidate for Removal New Revision Request required to strike gray boxes
Important Point
  Some aging RRs are expected to require language changes to bring them up to current market or system constructs
    Language updates would be made with a new RR
    ERCOT suggests this analysis be limited to aging items that are prioritized high enough to be queued for implementation

## Slide 11: Questions/Comments?
Troy.Anderson@ercot.com