## Slide 1: SCR820 – Real-Time Operator Communications System (RTOC) Bharati Nepal Christelle Seri August 20, 2026
Key Takeaways
RTOC project and market testing updates
Outline:
Status updates
Market Testing Updates
Recap Tool Access
Primary Contacts

## Slide 2: Status Updates
Market testing is underway while production capabilities continue to expand.
PROJECT UPDATES
Testing & operating readiness
✓
QSE testing underway
Primary contact information is being gathered.
✓
Parallel communications planned
Control Room Operations plans to use the RTOC tool alongside hotline calls for routine testing.
✓
Protocol update in discussion
Internal discussions are underway to draft an NPRR enabling Control Room use of the tool in addition to the current Hotline Call.
DEVELOPMENT UPDATES
Production capabilities
•
SOL Exceedance displays
First version developed and deployed to Production.
•
SOL Exceedance History
History tab has been rolled out.
•
Default dashboard
Provides a quick activity overview.
•
Emergency conditions
Development in progress on new screen to manage emergency condition
RTOC Market Testing | Project and development status

## Slide 3
RTOC Tool – Project Timelines
KEY TAKEAWAY
QSE market testing is now included in the project timeline. Please note that certain dates are subject to change pending the implementation of a nodal protocol revision request (NPRR)
PROJECT TIMELINE
Complete
Planning
Requirements & design finalized
Apr 2026
Development
Development & internal ERCOT testing
Apr–Jun 2026
TO Market Testing
Market testing with Transmission Operators
Jun–Aug 2026
QSE Market Testing
Market testing with Qualified Scheduling Entities
Q4 2026–Q1 2027*
Parallel Operation
TOs/QSEs Parallel Operation
Q1–Q2 2027*
Go-Live
TOs/QSEs Go Live
PROTOCOL DEPENDENCY
Parallel Operations and Go-Live dates depend on implementation and final approval of the NPRR protocol changes.
01 Protocol update
ERCOT is developing a draft NPRR to update protocols so RTOC can be used in addition to the current Hotline Call.
02 Parallel Operations
ERCOT and TO/QSE primary contacts will test and verify RTOC messages alongside Hotline Calls and routine communication tests. RTOC will NOT be a designated communication medium for control rooms. Hotline and voice communication will be the primary medium for Realtime system activities
03 Go-Live
RTOC is introduced into control rooms as a monitored 24×7 communication tool for normal and emergency operations.
During Parallel Operations, Hotline and voice communications remain the primary medium for real-time system activities.
* Coordinated with final approval of NPRR changes. Revised dates will be communicated through an updated market notice.
Reference: M-A032326-01A — Access and familiarization of the Real-Time Operation Communications (RTOC) tool

## Slide 4: Market Testing Updates
RTOC market testing readiness, engagement, and next steps
TRANSMISSION OPERATORS
22
124 total users
QUALIFIED SCHEDULING ENTITIES
26
97 total users
QSE TEST WINDOW
6/29–8/21
Active market testing
1
Access & onboarding
22 TOs and 26 QSEs successfully logged in and navigated all application displays.
Only main QSEs are requested to log in; they may acknowledge messages on behalf of sub-QSEs.
2
Contact readiness
ERCOT Control Room / Project team completed primary contact collection for TO control rooms.
QSE primary contact collection is currently in progress.
TO contacts complete • QSE contacts in progress
3
Testing & participation
Communications testing will occur twice weekly to confirm users can read, respond to, and acknowledge messages.
40%
TO online participation
Weekly RTOC hotline testing
20%
QSE online participation
Weekly RTOC hotline testing
Focus: increase live participation and response rates during recurring tests.
MARKET NOTICE
QSE access & familiarization
M-A062326-01
Access and familiarization of the Real-Time Operation Communications (RTOC) Tool — Qualified Scheduling Entities (QSE)
Support
ERCOTRTOCSupport@ercot.com

## Slide 5: RTOC Tool Access
Digital certificate • role-based authorization • MIS Application Library
01
CERTIFICATE
Access is granted through an approved digital certificate.
02
ROLE
Add the appropriate RTOC role to authorize the user.
03
LAUNCH
Open RTOC from the MIS Application Library when enabled.
Available roles
Operator
RTOC_M_OPERATOR
REQUEST
Read-only
RTOC_M_VIEW
VIEW
Where users will launch RTOC
MIS link will be enabled after market testing is complete.
Action: confirm certificate + required role before launch.

## Slide 6: Provide Primary Contact Information
Help us keep RTOC Market Testing communications timely and targeted.
WHAT TO PROVIDE
One primary contact for your organization
01
Primary contact name
02
Email address
03
Role / designation
WHY WE NEED IT
A clear contact path keeps testing moving.
• Receive testing-related communications • Get the application URL, updates, and instructions promptly
HOW TO SUBMIT
Email your contact details to
ERCOTRTOCSupport@ercot.com
Primary contact name • Email address • Role / designation

## Slide 7
RTOC enhancements
1
SOL Exceedance History
RTCA DISPLAY
• Addition of 1-hour and 24-hour history views for SOL exceedances history data
2
Default Dashboard
• Provides an overview of the new communications, GMD updates, and system conditions.
7
New Features Rolled Out

## Slide 8: August Release (R8): What’s New
RELEASE DATE
August 27, 2026
R8 enters RTOC Production and becomes available for Market Testing the same day.
ENHANCEMENT
Application performance
RTOC-206 • Communication
Improve application performance
1 enhancement included
DEFECTS
6 fixes
Communication
RTOC-156
Communication - No indication of failed message
RTOC-228
Communication - Message sent with sticky checked are not going through
RTOC-234
Communication - Read and ack % are not getting update
Dashboard
RTOC-233
Dashboard - User connection monitor - is not getting updated to reflect the number of active users
RTOC-232
Dashboard - Pop ups open in same window
RTOC-235
Dashboard - Active Alerts & Acknowledgements - is not displaying SOL Exceedances

## Slide 9: RTOC Emergency Page

## Slide 10: Questions/Comments?