## Slide 1: Comprehensive Transmission Planning and Batch 1+
August 26, 2026
Program update and stakeholder engagement plan
Presentation to TAC

## Slide 2: ERCOT continues to evolve the high-level process design
TPL and Alternative Project Analytics
Short circuit
Single source of truth
Integrated batch process
Consolidated modeling and reliability study
Streamlined endorsement
Stakeholder engagement and public comment (e.g., via monthly updates, to define stakeholder gates)
RIOO
MOD, TPIT
Base Load Economic Forecast, TSP RFI
Batch model build
Post commitment CTP Year N Model
Final model snapshot
Gen. data
Topology data
Remaining load data
(medium, economic)
Large load data (from TSPs)
ILLE submitting large load request
Commit-ment window
Actionable Trans. Plan
Endorsed Trans. Plan
Data inputs
Batch study
Modeling
Endorsement
TPL1
Dynamic
Economic
SC2
RPG-like analysis
Reliability study
CTP assessment
Batch study
TSP engagement

## Slide 3: Overall CTP scope: CTP will integrate batch process, streamline modeling and planning processes, and define clear governance handoffs
Scope for Comprehensive Transmission Process development
Define the future role of Batch within the annual planning cycle
Determine the technical study required to support Large Load commitment decisions
Design the transition from Batch study outputs to the CTP planning process
Batch-CTP integration
Establish a planning-led source of truth for planning models and assumptions
Develop a standardized planning model framework and taxonomy
Standardize planning cases, assumptions, and study methodology
Clarify ERCOT and TSP responsibilities for case development, model conditioning, and study execution
Modeling and planning
Define the stakeholder engagement and endorsement process for CTP
Clarify ERCOT and TSP roles in project identification and solution development
Establish governance, milestones, and response timelines for transmission plan development
TSP/stakeholder process and governance

## Slide 4: Batch 1+: Initial Batch 1+ Revision Requests priorities span four focus areas to continue advancing the Large Load framework
Initial ERCOT priorities for Revision Request development
Develop ILLE-TSP-ERCOT interaction process for Batch Studies
Establish a framework for resubmitting unmet Large Load ramp requests across Batches
Define carry-forward treatment for non-committed Large Loads across Batch cycles
Establish a governance framework for post-study project changes (e.g., delayed in-service date or end-use technology changes)
Large Load Interconnection
Refine the financial security methodology for transmission upgrades and direct interconnection costs to align with PUCT changes in 58481.
Financial and reporting
Modernize Batch technical study scope, responsibilities, and model governance
    Short circuit studies
    SSO studies
    Dynamic model change evaluation
Technical study framework
Enhance Large Load reporting and confidentiality provisions
Enhance Bring Your Own Generation (BYOG) framework
Enhance the Provisional Controllable Load Resource (PCLR) framework
Market rules & operational enhancements

## Slide 5: Stakeholder roadmap: Path to Batch 1+ and CTP Board approval
Forums
ROS
2026
2027
Q3
Q4
Q1
Jul
Aug
Sep
Oct
Nov
Dec
Jan
PRS
Workshops and working groups
Formally present CTP and Batch 1 PGRRs/NPRRs for approval
ERCOT Board
Objective
Interview TSP planning staff on CTP scope
Engage with Protocol Revisions Subcommittee on NPRR(s)
Engage with Reliability and Operations Subcommittee engagement on PGRR(s)
TAC
Review/endorse combined NPRR/PGRR package for Board approval
ROS 11/5
ROS 12/3
PUCT OM
Provide updates to Commission on progress/emerging policy considerations
Conduct stakeholder workshops on CTP process design and Batch 1+
Stakeholder engagement
Meeting
Targeted date
July 16 – late August
Workshop 1 8/31
LLWG
Engage with Large Load Working Group on Batch 1+
LLWG 8/21
LLWG 9/17
LLWG 11/19
LLWG 12/17
Workshop 2 9/24
Draft scope from ERCOT
Workshop 3 10/14
Workshop 5 12/2
Workshop 4 11/9
Further scoping details discussion
Details of design elements discussion
Review Revision Requests and market comments
April Board approval
11/1 File initial Revision Requests
7/8 ERCOT market notice
March TAC approval
Feb
Mar
Apr
Q2
ROS 1/7
ROS 2/4
ROS 3/4
ROS 4/8
ROS 10/1
Board 12/7-8
Board 2/8-9
Board 4/12-13
PRS 10/14
PRS 11/11
PRS 12/9
PRS 1/12
PRS 2/16
PRS 3/10
PRS 4/14
LLWG 10/15
TAC 10/28
TAC 11/18
TAC 1/20
TAC 8/28
TAC 7/29
TAC 2/24
TAC 3/24
TAC 4/28
As needed
Specific sessions to be selected for updates