## Slide 1: SCR820 – Real-Time Operator Communications System (RTOC) Preethi Meher Christelle Seri Sep 24, 2026
Key Takeaways
RTOC project and market testing updates
Outline:
Status updates
Market Testing Updates
Next release Updates
Primary Contacts

## Slide 2: Status Updates
Market testing is underway while production capabilities continue to expand.
PROJECT UPDATES
Testing & operating readiness
✓
QSE testing underway
Primary contact information is being gathered.
✓
Parallel communications planned
Control Room Operations plans to use the RTOC tool alongside hotline calls for routine testing.
✓
Protocol update in discussion
Internal discussions are underway to draft an NPRR enabling Control Room use of the tool in addition to the current Hotline Call.
DEVELOPMENT UPDATES
Production capabilities
•
•
SOL Exceedance History
History tab has been rolled out.
•
Default dashboard
Provides a quick activity overview.
•
Emergency Conditions
Being tested in staging environment
RTOC Market Testing | Project and development status
Load Shed Instructions
Currently, in development

## Slide 3
RTOC Tool – Project Timelines
KEY TAKEAWAY
QSE market testing is now included in the project timeline. Please note that certain dates are subject to change pending the implementation of a nodal protocol revision request (NPRR)
PROJECT TIMELINE
Complete
Planning
Requirements & design finalized
Apr 2026
Development
Development & internal ERCOT testing
Apr–Jun 2026
TO Market Testing
Market testing with Transmission Operators
Jun–Oct 2026
QSE Market Testing
Market testing with Qualified Scheduling Entities
Nov 2026–Q1 2027*
Parallel Operation
TOs/QSEs Parallel Operation
Q1–Q2 2027*
Go-Live
TOs/QSEs Go Live
PROTOCOL DEPENDENCY
Parallel Operations and Go-Live dates depend on implementation and final approval of the NPRR protocol changes.
01 Protocol update
ERCOT is developing a draft NPRR to update protocols so RTOC can be used in addition to the current Hotline Call.
02 Parallel Operations
ERCOT and TO/QSE primary contacts will test and verify RTOC messages alongside Hotline Calls and routine communication tests. RTOC will NOT be a designated communication medium for control rooms. Hotline and voice communication will be the primary medium for Realtime system activities
03 Go-Live
RTOC is introduced into control rooms as a monitored 24×7 communication tool for normal and emergency operations.
During Parallel Operations, Hotline and voice communications remain the primary medium for real-time system activities.
* Coordinated with final approval of NPRR changes. Revised dates will be communicated through an updated market notice.
Reference: M-A032326-01A — Access and familiarization of the Real-Time Operation Communications (RTOC) tool

## Slide 4: Market Testing Updates
RTOC market testing readiness, engagement, and next steps
TRANSMISSION OPERATORS
23
173 total users
QUALIFIED SCHEDULING ENTITIES
46
166 total users
QSE TEST WINDOW
6/29–10/30
Active market testing
1
Access & onboarding
23 TOs and 46 QSEs successfully logged in and navigated all application displays.
Only main QSEs are requested to log in; they may acknowledge messages on behalf of sub-QSEs.
2
Contact readiness
ERCOT Control Room / Project team completed primary contact collection for TO control rooms.
QSE primary contact collection almost done.
TO contacts complete • QSE contacts in progress
3
Testing & participation
Communications testing will occur twice weekly to confirm users can read, respond to, and acknowledge messages.
61%
TO online participation
Weekly RTOC hotline testing
32%
QSE online participation
Weekly RTOC hotline testing
Focus: increase live participation and response rates during recurring tests.
MARKET NOTICE
QSE access & familiarization
M-A062326-01
Access and familiarization of the Real-Time Operation Communications (RTOC) Tool — Qualified Scheduling Entities (QSE)
Support
ERCOTRTOCSupport@ercot.com

## Slide 5: RTOC Tool Access
Digital certificate • role-based authorization • MIS Application Library
01
CERTIFICATE
Access is granted through an approved digital certificate.
02
ROLE
Add the appropriate RTOC role to authorize the user.
03
LAUNCH
Open RTOC from the MIS Application Library when enabled.
Available roles
Operator
RTOC_M_OPERATOR
REQUEST
Read-only
RTOC_M_VIEW
VIEW
Where users will launch RTOC
MIS link will be enabled after market testing is complete.
Action: confirm certificate + required role before launch.

## Slide 6: Provide Primary Contact Information
Help us keep RTOC Market Testing communications timely and targeted.
WHAT TO PROVIDE
One primary contact for your organization
01
Primary contact name
02
Email address
03
Role / designation
WHY WE NEED IT
A clear contact path keeps testing moving.
• Receive testing-related communications • Get the application URL, updates, and instructions promptly
HOW TO SUBMIT
Email your contact details to
ERCOTRTOCSupport@ercot.com
Primary contact name • Email address • Role / designation

## Slide 7: October Release: What’s New
RELEASE DATE
Oct 29, 2026
R10 enters RTOC Production and becomes available for Market Testing the same day.
ENHANCEMENT
New Display
RTOC-247 • Emergency Communication
Communication during emergencies
1 enhancement included
DEFECTS
4 fixes
Communication
RTOC-275
Communication – Sticky Messages Timestamps
RTOC-277
Communication – removing label throws an error
RTOC-144
Communication – Add unique audio alarm for new messages
RTOC-187
Communication – Display acknowledged by username and timestamp for receiving company
RTOC-193 • User Experience – Replace developer style alerts with styled popups
Enhancement

## Slide 8: RTOC Load Shed Page

## Slide 9: Questions/Comments?