## Slide 1: An Open Season Batch Integration for Large Load Interconnection
A market-based framework for proactively planned transmission
ERCOT Stakeholder Discussion
September 24, 2026

## Slide 2: The Current Path Can Invite Logjam
The Large Load Interconnection Queue reflects significantly higher interest from Large Load customers than the current ERCOT all-time peak.
Large load interconnection is handled reactively, so network upgrades are identified assuming all requests will proceed.
Commitments come only after the work is done which results in overburdened study and unpredictable costs.
  This creates uncertainty for both new and existing customers, and other Market Participants.
Long-term planning is essential, but 10–20-year forecasts make consensus difficult to reach.
ERCOT’s single-regulator structure positions it well to test a nearer-term, commitment-based augmentations.

## Slide 3: How an Open Season Would Work
Identify. ERCOT uses Batch/Comprehensive Transmission Planning (CTP) processes to pinpoint transmission upgrades deliverable within about five years.
Offer. ERCOT offers the planned transmission capability and posts the rules by which bids will be evaluated.
Bid. Large Load customers make financially binding bids.
Select. ERCOT awards capability to the configuration of bids returning the highest value per MW, up to the capacity planned. Batch allocations and commitments with interconnecting utilities commence.
Build. ERCOT proceeds with the upgrades; committed loads retain a defined right to withdraw energy at the point of interconnection.
Proven precedent: natural gas pipeline open seasons, FERC merchant transmission policy, and Bonneville Power Administration’s 2008 Network Open Season, which drew 153 requests for 6,410 MW.

## Slide 4: ERCOT: Future Process - Initial view on scope and potential high-level CTP design Batch 1+ and Comprehensive Transmission Planning Workshop #1 (August 31, 2027)
TPL and Alternative Project Analytics
Short circuit
Single source of truth
Integrated batch process
Consolidated modeling and reliability study
Streamlined endorsement
Stakeholder engagement and public comment (e.g., via monthly updates, to define stakeholder gates)
RIOO
MOD, TPIT
Base Load Economic Forecast, TSP RFI
Batch model build
Post commitment & CTP Year N Model
Final model snapshot
Gen. data
Topology data
Remaining load data
(medium, economic)
Large load data (from TSPs)
ILLE large load data
Commit-ment window
Actionable Trans. Plan
Endorsed Trans. Plan
Data inputs
Batch study
Modeling
Endorsement
TPL1
Dynamic
Economic
SC2
RPG-like analysis
Reliability study
CTP assessment
Batch study
TSP engagement
Key Design Change:
Post-commitment in Batch Zero proceeds to Batch Refinement Study/RPG
Post commitment in Batch 1+ feeds into full Planning Studies
Open season runs here

## Slide 5: Adding an Open Season Complements the Commitment Window
The concept runs as a market test prior to the point in the CTP batch process where developers commit today.
Data inputs
Batch model build
Batch study
Open season
Commitment window
Modelling, reliability study and endorsement
1. Open
When the window opens, ERCOT posts the transmission capability the batch study found deliverable with scoring rules for bids.
2. Bid
Large loads bid for defined withdrawal capability instead of simply electing to meet the commitment requirement on the Batch allocation. Bids are binding and backed by financial security.
3. Award
At close, capability is awarded to the configuration of bids returning the highest value per MW, up to the Batch planned capacity.
No major deviation from the current envisioned process. Awards feed the commitment window and the same downstream path – refinement study, RPG-like review and endorsement – but on committed MW that have cleared a market test.

## Slide 6: Benefits & Open Questions
Expected Benefits
  The open season itself is the market test- it uses competitive market to allocate a scarce resource (and self corrects if it is no longer scarce)
  Provides a faster, firmer path to service for loads that are ready to commit
  Potential for fewer allocations below requested MW (or lower reductions from requested load to allocated load)
  It helps to reduce logjam by filtering prior to commitment window, and possibly into the Batch study itself
  Increases confidence in the load forecast
Bid revenue opens policy questions
  Flow back to load (similar to CARD Revenue, or some other allocation mechanism)?
  Offset System Admin Fee?
  Customer bill payment assistance funding?
  Credit against TCOS revenue requirements?
  Pay down securitization costs?
  Others?