## Wind Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 18INR0073 | Sweetwater 1 repower | Nolan | 2024-11-30 | 2002-10-23 | Wind | WT | 3 | 2024 | No
[7 empty] | 22INR0301 | Fortuna Wind | Jack | 2026-07-01 | 2024-08-08 | Wind | WT | 295.3 | 2026 | No
[7 empty] | 16INR0112 | Loma Pinta Wind | La Salle | 2026-12-31 | 2017-12-13 | Wind | WT | 197.01 | 2026 | No
[7 empty] | 26INR0622 | Buffalo Gap 1 Wind Repower | Taylor | 2027-02-01 | 2005-02-28 | Wind | WT | 120.23 | 2027 | Yes
[7 empty] | 26INR0625 | Buffalo Gap 2 Wind Repower | Nolan | 2027-02-01 | 2005-02-28 | Wind | WT | 231.49 | 2027 | Yes
[7 empty] | 26INR0626 | Buffalo Gap 3 Wind Repower | Taylor | 2027-02-01 | 2005-02-28 | Wind | WT | 168.45 | 2027 | Yes
[7 empty] | 27INR0367 | Goat Mountain Wind-Repower | Sterling | 2027-03-01 | 2026-02-20 | Wind | WT | 303.2 | 2027 | Yes
[7 empty] | 25INR0018 | Yellow Cat Wind | Navarro | 2027-03-05 | 2024-07-09 | Wind | WT | 262 | 2027 | Yes
[7 empty] | 26INR0647 | Wake Wind Energy Repower | Crosby | 2027-06-04 | 2014-02-28 | Wind | WT | 252.5 | 2027 | No
[7 empty] | 23INR0637 | Goodnight Wind II | Armstrong | 2027-06-06 | 2019-08-18 | Wind | WT | 261.1 | 2027 | Yes
[7 empty] | 24INR0291 | Rubicon Alpha Wind | Haskell | 2027-07-31 | 2024-05-08 | Wind | WT | 222.6 | 2027 | Yes
[7 empty] | 21INR0263 | Monarch Creek Wind | Throckmorton | 2027-09-17 | 2020-08-24 | Wind | WT | 283.4 | 2027 | Yes
[7 empty] | 25INR0494 | Willow Beach Wind | Brazoria | 2027-10-01 | 2025-06-16 | Wind | WT | 202.33 | 2027 | No
[7 empty] | 23INR0561 | Cascabel Wind 2 | Zapata | 2027-12-01 | 2025-05-23 | Wind | WT | 197.75 | 2027 | Yes
[7 empty] | 24INR0424 | Cascabel Wind 1 | Zapata | 2027-12-01 | 2025-05-23 | Wind | WT | 197.75 | 2027 | Yes
[7 empty] | 24INR0505 | Corralitos Wind 1 | Zapata | 2027-12-01 | 2025-06-19 | Wind | WT | 196.1 | 2027 | Yes
[7 empty] | 20INR0247 | Water Valley Wind Energy | Tom Green | 2027-12-15 | 2025-03-17 | Wind | WT | 180 | 2027 | Yes
[7 empty] | 24INR0506 | Corralitos Wind 2 | Zapata | 2027-12-31 | 2025-06-19 | Wind | WT | 195.4 | 2027 | Yes
[7 empty] | 27INR0004 | Dundee West Wind | Wilbarger | 2027-12-31 | 2025-02-21 | Wind | WT | 146.49 | 2027 | Yes
[7 empty] | 27INR0005 | Dundee East A Wind | Baylor | 2027-12-31 | 2025-02-21 | Wind | WT | 524 | 2027 | Yes
[7 empty] | 27INR0011 | Dundee East B Wind | Baylor | 2027-12-31 | 2025-02-21 | Wind | WT | 261.45 | 2027 | Yes
[7 empty] | 27INR0056 | Laurel Wind Energy Center | Pecos | 2027-12-31 | 2024-10-25 | Wind | WT | 306.6 | 2027 | Yes
[7 empty] | 26INR0021 | Crossroads Wind | Victoria | 2028-02-28 | 2024-07-24 | Wind | WT | 277.38 | 2028 | Yes
[7 empty] | 26INR0113 | Meitner Wind | Gray | 2028-05-24 | 2024-04-19 | Wind | WT | 709 | 2028 | No
[7 empty] | 27INR0510 | Pecos Wind | Pecos | 2028-05-30 | 2026-03-18 | Wind | WT | 193.8 | 2028 | No
[7 empty] | 28INR0037 | Bullring Wind 1 | Starr | 2028-06-30 | 2025-11-03 | Wind | WT | 303.5 | 2028 | Yes
[7 empty] | 28INR0038 | Bullring Wind 2 | Starr | 2028-06-30 | 2025-11-03 | Wind | WT | 303.8 | 2028 | Yes
[7 empty] | 28INR0039 | Bullring Wind 3 | Starr | 2028-06-30 | 2025-11-03 | Wind | WT | 190.4 | 2028 | Yes
[7 empty] | 29INR0004 | Aurelius Wind | Deaf Smith | 2028-06-30 | 2025-10-09 | Wind | WT | 621.6 | 2028 | Yes
[7 empty] | 27INR0076 | Bob Creek Wind | Sterling | 2028-07-01 | 2025-06-06 | Wind | WT | 239.47 | 2028 | Yes
[7 empty] | 29INR0025 | Skyrider Wind | Pecos | 2028-07-01 | 2025-12-23 | Wind | WT | 370 | 2028 | Yes
[7 empty] | 28INR0072 | Mirando Valley Wind | Jim Hogg | 2028-07-06 | 2025-12-31 | Wind | WT | 478.74 | 2028 | Yes
[7 empty] | 28INR0434 | Viento Bravo Wind | Jim Hogg | 2028-07-06 | 2025-12-31 | Wind | WT | 366.51 | 2028 | Yes
[7 empty] | 25INR0247 | Bluebonnet Prairie Wind | Navarro | 2028-07-15 | 2025-07-03 | Wind | WT | 180 | 2028 | Yes
[7 empty] | 23INR0441 | Bug Tussle Wind Project | Lamar | 2028-09-18 | 2024-07-10 | Wind | WT | 396.8 | 2028 | No
[7 empty] | 27INR0108 | Paint Rock Wind | Concho | 2028-10-01 | 2026-08-24 | Wind | WT | 379.18 | 2028 | No
[7 empty] | 26INR0530 | Longview Wind | Dawson | 2028-12-01 | 2025-12-16 | Wind | WT | 352.6 | 2028 | Yes
[7 empty] | 19INR0023 | Monte Alto 2 Wind | Willacy | 2028-12-31 | 2022-03-22 | Wind | WT | 199.2 | 2028 | Yes
[7 empty] | 19INR0055 | Monte Cristo II Wind | Hidalgo | 2028-12-31 | 2025-12-19 | Wind | WT | 233.9 | 2028 | Yes
[7 empty] | 27INR0383 | Windjammer Windpower | Glasscock | 2028-12-31 | 2025-12-03 | Wind | WT | 244.06 | 2028 | Yes
[7 empty] | 29INR0040 | Gusty Windpower | Glasscock | 2028-12-31 | 2025-12-03 | Wind | WT | 248.9 | 2028 | Yes
[7 empty] | 20INR0047 | Siete | Webb | 2029-03-31 | 2022-06-30 | Wind | WT | 492.8 | 2029 | Yes
[7 empty] | 28INR0169 | Sanders Hollow Energy Center | Dickens | 2029-06-23 | 2026-06-09 | Wind | WT | 292.6 | 2029 | No
[7 empty] | 29INR0042 | Slager Lake Wind | Reagan | 2029-07-01 | 2025-12-23 | Wind | WT | 310.2 | 2029 | No
[7 empty] | 27INR0132 | Palo Verde Wind | San Patricio | 2029-07-22 | 2025-12-19 | Wind | WT | 297.5 | 2029 | No
[7 empty] | 26INR0531 | West Munday Wind | Knox | 2029-08-31 | 2025-07-21 | Wind | WT | 351.91 | 2029 | Yes
[7 empty] | 27INR0140 | Kingsmill Wind SLF | Carson | 2029-09-01 | 2025-12-18 | Wind | WT | 606.3 | 2029 | No
[7 empty] | 30INR0018 | Big Canyon Wind | Pecos | 2030-07-01 | 2025-12-24 | Wind | WT | 1500 | 2030 | Yes
Year | Cumulative Operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | Small Generator
2000 | 160.37 | 160.37 | 0 | 0 | 0 | 0
2001 | 887.97 | 887.97 | 0 | 0 | 0 | 0
2002 | 1058.22 | 1058.22 | 0 | 0 | 0 | 0
2003 | 1260.72 | 1260.72 | 0 | 0 | 0 | 0
2004 | 1377.82 | 1377.82 | 0 | 0 | 0 | 0
2005 | 1990.42 | 1990.42 | 0 | 0 | 0 | 0
2006 | 2726.72 | 2726.72 | 0 | 0 | 0 | 0
2007 | 4306.44 | 4306.44 | 0 | 0 | 0 | 0
2008 | 8190.64 | 8190.64 | 0 | 0 | 0 | 0
2009 | 9116.66 | 9116.66 | 0 | 0 | 0 | 0
2010 | 9575.04 | 9575.04 | 0 | 0 | 0 | 0
2011 | 9707.04 | 9707.04 | 0 | 0 | 0 | 0
2012 | 11181 | 11181 | 0 | 0 | 0 | 0
2013 | 11329.6 | 11329.6 | 0 | 0 | 0 | 0
2014 | 13222.18 | 13222.18 | 0 | 0 | 0 | 0
2015 | 16430.92 | 16430.92 | 0 | 0 | 0 | 0
2016 | 19056.24 | 19056.24 | 0 | 0 | 0 | 0
2017 | 21302.98 | 21302.98 | 0 | 0 | 0 | 0
2018 | 22686.68 | 22686.68 | 0 | 0 | 0 | 0
2019 | 27272.33 | 27272.33 | 0 | 0 | 0 | 0
2020 | 31180.3 | 31180.3 | 0 | 0 | 0 | 0
2021 | 33981.9 | 33981.9 | 0 | 0 | 0 | 0
2022 | 36947.92 | 36947.92 | 0 | 0 | 0 | 0
2023 | 38730.81 | 38730.81 | 0 | 0 | 0 | 0
2024 | 39491.03 | 39491.03 | 0 | 0 | 0 | 0
2025 | 40738.65 | 40738.65 | 0 | 0 | 0 | 0
2026 | 41703.36 | 41208.05 | 0 | 495.31 | 0 | 0
2027 | 46216.2 | 41208.05 | 4058.01 | 950.14 | 0 | 0
2028 | 52505.04 | 41208.05 | 8668.07 | 2628.92 | 0 | 0
2029 | 54856.35 | 41208.05 | 9512.78 | 4135.52 | 0 | 0
2030 | 56356.35 | 41208.05 | 11012.78 | 4135.52 | 0 | 0

## Solar Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 23INR0487 | Brightside Solar Alt POI | Live Oak | 2026-08-14 | 2020-06-11 | Solar | PV | 50 | 2026 | Yes
[7 empty] | 19INR0103 | Rodeo Solar | Andrews | 2026-11-30 | 2019-08-20 | Solar | PV | 200 | 2026 | Yes
[7 empty] | 21INR0334 | Nightfall Solar | Uvalde | 2026-12-31 | 2023-10-26 | Solar | PV | 180.87 | 2026 | Yes
[7 empty] | 21INR0421 | Armadillo Solar | Navarro | 2026-12-31 | 2021-02-02 | Solar | PV | 150.48 | 2026 | Yes
[7 empty] | 22INR0262 | Sequoia II Solar | Callahan | 2027-01-28 | 2023-08-29 | Solar | PV | 417.47 | 2027 | Yes
[7 empty] | 21INR0362 | Oystercatcher Solar | Ellis | 2027-01-29 | 2021-08-20 | Solar | PV | 198.43 | 2027 | No
[7 empty] | 23INR0244 | Tiger Solar | Jones | 2027-02-26 | 2024-10-30 | Solar | PV | 250.9 | 2027 | Yes
[7 empty] | 29INR0015 | Funston Solar | Jones | 2027-02-26 | 2024-10-23 | Solar | PV | 351.1 | 2027 | Yes
[7 empty] | 22INR0559 | Honeycomb Solar SLF | Bee | 2027-02-27 | 2023-05-01 | Solar | PV | 61.4 | 2027 | Yes
[7 empty] | 21INR0253 | Ulysses Solar | Coke | 2027-03-17 | 2022-10-03 | Solar | PV | 151.2 | 2027 | Yes
[7 empty] | 24INR0137 | Eagle Springs Solar | Delta | 2027-03-29 | 2024-04-17 | Solar | PV | 77.21 | 2027 | Yes
[7 empty] | 22INR0437 | TORMES SOLAR | Navarro | 2027-03-31 | 2024-04-10 | Solar | PV | 356.6 | 2027 | Yes
[7 empty] | 24INR0154 | Lupinus Solar 2 | Franklin | 2027-04-03 | 2025-03-04 | Solar | PV | 242.31 | 2027 | Yes
[7 empty] | 25INR0199 | Bonham Solar SLF | Limestone | 2027-04-06 | 2024-08-07 | Solar | PV | 138.4 | 2027 | Yes
[7 empty] | 23INR0235 | Hoyte Solar | Milam | 2027-04-15 | 2022-10-14 | Solar | PV | 206.75 | 2027 | Yes
[7 empty] | 25INR0232 | Isaac Solar | Matagorda | 2027-04-15 | 2023-10-18 | Solar | PV | 50.73 | 2027 | Yes
[7 empty] | 23INR0027 | Clear Fork Creek Solar | Wilson | 2027-04-29 | 2021-11-23 | Solar | PV | 602.02 | 2027 | Yes
[7 empty] | 23INR0207 | El Patrimonio Solar | Bexar | 2027-04-29 | 2023-12-11 | Solar | PV | 152.32 | 2027 | Yes
[7 empty] | 21INR0371 | Pecan Prairie South | Leon | 2027-05-01 | 2021-02-21 | Solar | PV | 132.98 | 2027 | Yes
[7 empty] | 21INR0428 | Pecan Prairie North | Leon | 2027-05-01 | 2021-02-26 | Solar | PV | 324.11 | 2027 | Yes
[7 empty] | 22INR0454 | Wallace Solar | Culberson | 2027-05-14 | 2022-02-07 | Solar | PV | 36 | 2027 | Yes
[7 empty] | 24INR0188 | Tehuacana Creek Solar | Navarro | 2027-05-18 | 2024-11-25 | Solar | PV | 505.43 | 2027 | Yes
[7 empty] | 21INR0341 | Space City Solar | Wharton | 2027-06-01 | 2025-12-11 | Solar | PV | 366 | 2027 | Yes
[7 empty] | 25INR0102 | Austin Bayou Solar | Brazoria | 2027-06-01 | 2023-11-15 | Solar | PV | 502.48 | 2027 | Yes
[7 empty] | 23INR0045 | Caney Creek Solar | Van Zandt | 2027-06-21 | 2021-12-29 | Solar | PV | 121.04 | 2027 | Yes
[7 empty] | 26INR0524 | Fagus Solar Park 3 SLF | Childress | 2027-06-28 | 2019-02-21 | Solar | PV | 169.59 | 2027 | Yes
[7 empty] | 23INR0289 | Skull Creek Solar | Anderson | 2027-06-30 | 2024-05-20 | Solar | PV | 136.98 | 2027 | No
[7 empty] | 25INR0225 | Lucy Solar | Concho | 2027-06-30 | 2024-05-29 | Solar | PV | 352.21 | 2027 | Yes
[7 empty] | 25INR0368 | Echols Grove Solar | Lamar | 2027-06-30 | 2024-07-06 | Solar | PV | 201.56 | 2027 | Yes
[7 empty] | 23INR0231 | Hoke Solar | Gonzales | 2027-07-05 | 2022-04-25 | Solar | PV | 95.29 | 2027 | Yes
[7 empty] | 26INR0269 | Moccasin Solar | Stonewall | 2027-07-06 | 2024-09-04 | Solar | PV | 603.59 | 2027 | Yes
[7 empty] | 25INR0081 | SanPat Solar I | San Patricio | 2027-07-08 | 2023-10-18 | Solar | PV | 308.88 | 2027 | Yes
[7 empty] | 25INR0164 | Star Dairy Solar | Lamar | 2027-07-12 | 2024-12-09 | Solar | PV | 115.61 | 2027 | No
[7 empty] | 21INR0520 | Yellow Viking Solar | Somervell | 2027-07-13 | 2022-10-25 | Solar | PV | 171.13 | 2027 | Yes
[7 empty] | 25INR0052 | SanPat Solar II | San Patricio | 2027-07-22 | 2023-10-18 | Solar | PV | 256.23 | 2027 | Yes
[7 empty] | 26INR0155 | Ross Solar | Refugio | 2027-07-31 | 2024-06-27 | Solar | PV | 1025.57 | 2027 | No
[7 empty] | 25INR0382 | HappyDogSolar | Milam | 2027-08-04 | 2024-12-16 | Solar | PV | 85.54 | 2027 | No
[7 empty] | 23INR0086 | Hanson Solar | Coleman | 2027-08-17 | 2023-09-20 | Solar | PV | 398.83 | 2027 | Yes
[7 empty] | 26INR0718 | PHOTON SOLAR REPOWERING | Wharton | 2027-08-17 | 2021-02-25 | Solar | PV | 0 | 2027 | No
[7 empty] | 22INR0342 | Matagorda Solar | Matagorda | 2027-08-25 | 2022-06-08 | Solar | PV | 101 | 2027 | Yes
[7 empty] | 23INR0349 | Tokio Solar | McLennan | 2027-08-25 | 2023-11-06 | Solar | PV | 170.45 | 2027 | Yes
[7 empty] | 24INR0106 | Payne Battlecreek | Hill | 2027-08-25 | 2024-02-23 | Solar | PV | 84.99 | 2027 | No
[7 empty] | 23INR0040 | Dori BQ Solar | Harris | 2027-08-30 | 2022-12-01 | Solar | PV | 50.42 | 2027 | No
[7 empty] | 16INR0049 | Nazareth Solar | Castro | 2027-08-31 | 2026-03-05 | Solar | PV | 203 | 2027 | Yes
[7 empty] | 21INR0210 | Adamstown Solar | Wilbarger | 2027-08-31 | 2024-12-04 | Solar | PV | 250.88 | 2027 | Yes
[7 empty] | 22INR0605 | Camino Santiago Solar | Milam | 2027-09-01 | 2024-12-06 | Solar | PV | 196.3 | 2027 | Yes
[7 empty] | 24INR0150 | Lupinus Solar 1 | Franklin | 2027-09-13 | 2025-06-26 | Solar | PV | 162.31 | 2027 | Yes
[7 empty] | 27INR0434 | Lyra Solar | Borden | 2027-09-15 | 2025-07-01 | Solar | PV | 500 | 2027 | Yes
[7 empty] | 21INR0031 | Indigo Solar | Fisher | 2027-09-17 | 2020-09-15 | Solar | PV | 150 | 2027 | Yes
[7 empty] | 23INR0150 | Cradle Solar | Brazoria | 2027-09-17 | 2023-03-15 | Solar | PV | 200.85 | 2027 | Yes
[7 empty] | 25INR0204 | Cedar Range Solar | Hopkins | 2027-09-17 | 2025-07-02 | Solar | PV | 150.64 | 2027 | No
[7 empty] | 26INR0380 | Pepper Solar Farm | McLennan | 2027-09-20 | 2025-06-23 | Solar | PV | 120.72 | 2027 | Yes
[7 empty] | 26INR0409 | Lucky 7 Solar | Hopkins | 2027-09-20 | 2025-08-13 | Solar | PV | 101.35 | 2027 | Yes
[7 empty] | 27INR0049 | Darkwood Solar | Comanche | 2027-09-20 | 2025-11-05 | Solar | PV | 152.02 | 2027 | Yes
[7 empty] | 21INR0391 | Grandslam Solar | Atascosa | 2027-10-01 | 2021-01-29 | Solar | PV | 121.89 | 2027 | No
[7 empty] | 24INR0167 | OCI SunRoper | Wharton | 2027-10-01 | 2025-07-10 | Solar | PV | 265.1 | 2027 | Yes
[7 empty] | 24INR0326 | Blarney Solar | Hopkins | 2027-10-01 | 2024-04-22 | Solar | PV | 81.46 | 2027 | No
Year | Cumulative Operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | Small Generator | 27INR0438 | Wisdom Solar SLF | Pecos | 2027-10-06 | 2026-03-18 | Solar | PV | 299.37 | 2027 | No
2010 | 14.9 | 14.9 | 0 | 0 | 0 | 0 | 23INR0056 | Caliche Mound Solar | Deaf Smith | 2027-10-26 | 2023-10-12 | Solar | PV | 406.6 | 2027 | Yes
2011 | 41.6 | 41.6 | 0 | 0 | 0 | 0 | 26INR0241 | Sol Marina SLF Energy Center | Ellis | 2027-10-29 | 2025-04-25 | Solar | PV | 171.09 | 2027 | Yes
2012 | 72 | 72 | 0 | 0 | 0 | 0 | 26INR0130 | Elm Flats Solar SLF | Navarro | 2027-11-01 | 2025-11-21 | Solar | PV | 125.84 | 2027 | Yes
2013 | 121.18 | 121.18 | 0 | 0 | 0 | 0 | 27INR0198 | Musgravite Solar | Henderson | 2027-11-01 | 2025-05-20 | Solar | PV | 100.6 | 2027 | Yes
2014 | 190.7 | 190.7 | 0 | 0 | 0 | 0 | 22INR0220 | Lamkin Solar | Comanche | 2027-11-08 | 2025-03-06 | Solar | PV | 101.5 | 2027 | Yes
2015 | 301.71 | 301.71 | 0 | 0 | 0 | 0 | 25INR0281 | Cosper Solar | Bell | 2027-11-12 | 2025-07-31 | Solar | PV | 148.16 | 2027 | Yes
2016 | 698.22 | 698.22 | 0 | 0 | 0 | 0 | 26INR0621 | Juno 3 Solar | Borden | 2027-11-30 | 2025-07-01 | Solar | PV | 500 | 2027 | Yes
2017 | 1140.12 | 1140.12 | 0 | 0 | 0 | 0 | 27INR0500 | Antila Solar | Borden | 2027-11-30 | 2025-08-13 | Solar | PV | 500 | 2027 | Yes
2018 | 1909.16 | 1909.16 | 0 | 0 | 0 | 0 | 25INR0422 | Waterloo Solar 1 | Bastrop | 2027-12-01 | 2024-09-04 | Solar | PV | 200.64 | 2027 | No
2019 | 2605.35 | 2605.35 | 0 | 0 | 0 | 0 | 24INR0161 | Miranda Solar Project | McMullen | 2027-12-06 | 2024-07-16 | Solar | PV | 261.67 | 2027 | Yes
2020 | 6034.64 | 6034.64 | 0 | 0 | 0 | 0 | 24INR0298 | Leighton Solar | Limestone | 2027-12-06 | 2024-05-28 | Solar | PV | 181 | 2027 | Yes
2021 | 10038.12 | 10038.12 | 0 | 0 | 0 | 0 | 24INR0038 | Jaguar Solar | McLennan | 2027-12-11 | 2022-09-12 | Solar | PV | 300.87 | 2027 | Yes
2022 | 14818.22 | 14818.22 | 0 | 0 | 0 | 0 | 24INR0201 | Short Creek Solar | Wichita | 2027-12-17 | 2024-10-02 | Solar | PV | 627.81 | 2027 | Yes
2023 | 22153.33 | 22153.33 | 0 | 0 | 0 | 0 | 24INR0186 | Rowdy Creek Solar | Lamar | 2027-12-29 | 2025-05-02 | Solar | PV | 351.78 | 2027 | Yes
2024 | 29344.07 | 29344.07 | 0 | 0 | 0 | 0 | 27INR0313 | Spindletop Solar | Nacogdoches | 2027-12-29 | 2025-12-29 | Solar | PV | 286.4 | 2027 | Yes
2025 | 37442.74 | 37442.74 | 0 | 0 | 0 | 0 | 25INR0304 | Flying Kite Solar | Zavala | 2027-12-30 | 2024-10-02 | Solar | PV | 80.38 | 2027 | No
2026 | 42507.34 | 41925.99 | 581.35 | 0 | 0 | 0 | 22INR0455 | Blue Sky Sol | Crockett | 2027-12-31 | 2022-02-01 | Solar | PV | 101.2 | 2027 | Yes
2027 | 61204.78 | 41925.99 | 16138.87 | 3139.92 | 0 | 0 | 23INR0057 | Duffy Solar | Matagorda | 2027-12-31 | 2023-04-12 | Solar | PV | 502.46 | 2027 | Yes
2028 | 84788.76 | 41925.99 | 32097.74 | 10765.03 | 0 | 0 | 24INR0404 | Tres Rios Ranch Solar | Upton | 2027-12-31 | 2025-12-30 | Solar | PV | 508 | 2027 | No
2029 | 92047.69 | 41925.99 | 36003.84 | 14117.86 | 0 | 0 | 25INR0229 | OCI Cobb Creek Solar | Hill | 2027-12-31 | 2024-07-24 | Solar | PV | 203.1 | 2027 | Yes
2030 | 93181.41 | 41925.99 | 37006.84 | 14248.58 | 0 | 0 | 25INR0482 | Vault Solar | Palo Pinto | 2027-12-31 | 2026-06-30 | Solar | PV | 108.5 | 2027 | Yes
2031 | 94185.51 | 41925.99 | 37006.84 | 15252.68 | 0 | 0 | 27INR0127 | Bigway Solar I | King | 2027-12-31 | 2025-02-15 | Solar | PV | 195.2 | 2027 | Yes
2032 | 94370.06 | 41925.99 | 37006.84 | 15437.23 | 0 | 0 | 27INR0128 | Bigway Solar II | King | 2027-12-31 | 2025-02-15 | Solar | PV | 206 | 2027 | Yes
[7 empty] | 25INR0430 | Hackberry Creek Solar | Mitchell | 2028-01-01 | 2025-12-02 | Solar | PV | 175.51 | 2028 | Yes
[7 empty] | 25INR0174 | Concho Pearl Solar | Concho | 2028-01-09 | 2024-07-22 | Solar | PV | 171.9 | 2028 | No
[7 empty] | 20INR0255 | Renegade Project | Deaf Smith | 2028-01-15 | 2021-01-04 | Solar | PV | 515.66 | 2028 | Yes
[7 empty] | 23INR0091 | Cascade Solar | Brazoria | 2028-01-15 | 2023-04-17 | Solar | PV | 171 | 2028 | Yes
[7 empty] | 24INR0440 | Starling Solar | Gonzales | 2028-01-28 | 2026-02-17 | Solar | PV | 144.6 | 2028 | No
[7 empty] | 20INR0086 | Arroyo Solar | Cameron | 2028-02-22 | 2021-09-28 | Solar | PV | 100 | 2028 | Yes
[7 empty] | 25INR0170 | Pinewood Solar | Brazoria | 2028-02-29 | 2025-05-08 | Solar | PV | 150.68 | 2028 | No
[7 empty] | 24INR0065 | Keys Hollow Solar Phase II SLF | Goliad | 2028-03-10 | 2024-10-29 | Solar | PV | 200.85 | 2028 | Yes
[7 empty] | 24INR0067 | KEYS HOLLOW SOLAR SLF | Goliad | 2028-03-10 | 2024-10-29 | Solar | PV | 200.85 | 2028 | Yes
[7 empty] | 25INR0319 | Northington Solar | Wharton | 2028-03-14 | 2024-10-02 | Solar | PV | 125.9 | 2028 | Yes
[7 empty] | 24INR0206 | Glasgow Solar | Navarro | 2028-03-16 | 2023-11-08 | Solar | PV | 203.5 | 2028 | Yes
[7 empty] | 24INR0339 | Mystic Springs Renewable Energy Solar SLF | Kaufman | 2028-03-31 | 2025-10-30 | Solar | PV | 258.83 | 2028 | No
[7 empty] | 26INR0452 | Cannibal Draw Solar | Glasscock | 2028-04-10 | 2025-01-17 | Solar | PV | 149.5 | 2028 | Yes
[7 empty] | 23INR0059 | Briggs Solar | Haskell | 2028-04-15 | 2025-03-15 | Solar | PV | 323.7 | 2028 | Yes
[7 empty] | 26INR0098 | Douie Solar | Freestone | 2028-04-18 | 2026-03-08 | Solar | PV | 221.2 | 2028 | Yes
[7 empty] | 22INR0426 | LUBIO SOLAR | Kaufman | 2028-04-20 | 2024-11-08 | Solar | PV | 54.71 | 2028 | No
[7 empty] | 23INR0061 | Noria Solar DCC | Nueces | 2028-04-21 | 2022-10-12 | Solar | PV | 145 | 2028 | Yes
[7 empty] | 20INR0162 | Diamondback solar | Starr | 2028-04-29 | 2024-06-14 | Solar | PV | 200.5 | 2028 | Yes
[7 empty] | 24INR0124 | High Noon Solar | Hill | 2028-05-09 | 2024-05-03 | Solar | PV | 182 | 2028 | Yes
[7 empty] | 24INR0117 | Utley Solar | Freestone | 2028-05-11 | 2025-12-18 | Solar | PV | 221.78 | 2028 | Yes
[7 empty] | 23INR0367 | Fewell Solar | Limestone | 2028-05-15 | 2023-08-18 | Solar | PV | 203.5 | 2028 | Yes
[7 empty] | 26INR0147 | Seven Springs Solar | Lampasas | 2028-05-26 | 2025-08-28 | Solar | PV | 145 | 2028 | Yes
[7 empty] | 26INR0290 | Cold Creek Solar 2 | Schleicher | 2028-05-28 | 2025-04-23 | Solar | PV | 431.87 | 2028 | No
[7 empty] | 26INR0431 | Big Rooter West Solar | Robertson | 2028-05-31 | 2025-02-18 | Solar | PV | 403.2 | 2028 | No
[7 empty] | 22INR0257 | Corazon Solar Phase II | Webb | 2028-06-01 | 2020-08-04 | Solar | PV | 203.9 | 2028 | No
[7 empty] | 27INR0355 | Gardner Draw Solar | Glasscock | 2028-06-01 | 2025-08-07 | Solar | PV | 309.5 | 2028 | Yes
[7 empty] | 25INR0080 | Meitner Solar | Gray | 2028-06-08 | 2024-01-31 | Solar | PV | 702.64 | 2028 | No
[7 empty] | 22INR0251 | Shaula I Solar | DeWitt | 2028-06-15 | 2022-02-16 | Solar | PV | 205.2 | 2028 | Yes
[7 empty] | 22INR0267 | Shaula II Solar | DeWitt | 2028-06-15 | 2022-04-27 | Solar | PV | 205.2 | 2028 | Yes
[7 empty] | 24INR0118 | Possum Kingdom Solar | Jack | 2028-06-21 | 2025-07-25 | Solar | PV | 262.22 | 2028 | Yes
[7 empty] | 24INR0287 | Rockridge Solar | Guadalupe | 2028-06-27 | 2025-03-14 | Solar | PV | 211.2 | 2028 | No
[7 empty] | 25INR0112 | August Draw Solar | Reeves | 2028-06-27 | 2025-09-12 | Solar | PV | 250 | 2028 | Yes
[7 empty] | 26INR0440 | Hamby Solar | Jones | 2028-06-27 | 2025-12-31 | Solar | PV | 205.8 | 2028 | Yes
[7 empty] | 24INR0258 | Zeissel Solar | Knox | 2028-06-30 | 2024-02-24 | Solar | PV | 451.52 | 2028 | Yes
[7 empty] | 24INR0422 | Hollow Branch Creek Solar | Leon | 2028-06-30 | 2024-10-22 | Solar | PV | 460 | 2028 | Yes
[7 empty] | 25INR0060 | Argenta Solar | Bee | 2028-06-30 | 2024-04-05 | Solar | PV | 310 | 2028 | Yes
[7 empty] | 29INR0003 | Aurelius Solar | Deaf Smith | 2028-06-30 | 2025-10-09 | Solar | PV | 1124.24 | 2028 | Yes
[7 empty] | 22INR0279 | Clutch City Solar Phase I | Brazoria | 2028-07-01 | 2022-09-30 | Solar | PV | 200.75 | 2028 | No
[7 empty] | 23INR0116 | Cantaloupe Solar | Reeves | 2028-07-01 | 2024-04-23 | Solar | PV | 307 | 2028 | Yes
[7 empty] | 25INR0154 | Nymphaea Solar | Wichita | 2028-07-01 | 2026-05-18 | Solar | PV | 120.9 | 2028 | Yes
[7 empty] | 25INR0330 | Clutch City Solar Phase II | Brazoria | 2028-07-01 | 2025-02-11 | Solar | PV | 251.27 | 2028 | No
[7 empty] | 26INR0600 | Crocus Solar | Stephens | 2028-07-01 | 2026-08-04 | Solar | PV | 102 | 2028 | No
[7 empty] | 28INR0185 | San Gabriel Solar | Milam | 2028-07-01 | 2026-08-06 | Solar | PV | 255 | 2028 | No
[7 empty] | 24INR0337 | Eldora Solar | Matagorda | 2028-07-02 | 2023-11-15 | Solar | PV | 200.94 | 2028 | Yes
[7 empty] | 26INR0470 | Roxton Solar | Lamar | 2028-07-21 | 2026-09-03 | Solar | PV | 116.8 | 2028 | Yes
[7 empty] | 25INR0282 | Hornet Solar II SLF | Swisher | 2028-07-31 | 2024-08-21 | Solar | PV | 201.49 | 2028 | Yes
[7 empty] | 24INR0356 | Cibeles Solar | McLennan | 2028-08-15 | 2025-02-25 | Solar | PV | 252.3 | 2028 | Yes
[7 empty] | 25INR0172 | Wolf Spring Solar | Dickens | 2028-08-25 | 2024-08-14 | Solar | PV | 195.8 | 2028 | No
[7 empty] | 26INR0359 | Uva Creek Solar | Borden | 2028-08-25 | 2024-10-30 | Solar | PV | 302.16 | 2028 | Yes
[7 empty] | 28INR0176 | Gail Mountain Solar | Borden | 2028-08-25 | 2025-12-30 | Solar | PV | 244.4 | 2028 | Yes
[7 empty] | 27INR0124 | RedSun Solar | Burnet | 2028-08-28 | 2025-09-25 | Solar | PV | 82.55 | 2028 | No
[7 empty] | 29INR0147 | Selenite Springs Solar | Pecos | 2028-08-30 | 2025-12-24 | Solar | PV | 253 | 2028 | Yes
[7 empty] | 30INR0058 | Springfield Solar | Pecos | 2028-08-30 | 2025-12-24 | Solar | PV | 400 | 2028 | Yes
[7 empty] | 26INR0088 | La Salle Solar | La Salle | 2028-09-13 | 2025-11-03 | Solar | PV | 512.6 | 2028 | Yes
[7 empty] | 25INR0227 | SERENGETI SOLAR | Delta | 2028-09-18 | 2025-12-30 | Solar | PV | 76.18 | 2028 | Yes
[7 empty] | 27INR0389 | Sugaree Solar | Maverick | 2028-09-21 | 2025-09-29 | Solar | PV | 251.4 | 2028 | Yes
[7 empty] | 25INR0246 | VALDIVIAN SOLAR | Hunt | 2028-09-22 | 2026-09-03 | Solar | PV | 74.9 | 2028 | Yes
[7 empty] | 21INR0265 | Sisters Solar | Ector | 2028-09-23 | 2025-07-01 | Solar | PV | 100.51 | 2028 | Yes
[7 empty] | 25INR0400 | Maldives Solar | Scurry | 2028-09-25 | 2023-12-01 | Solar | PV | 181.3 | 2028 | Yes
[7 empty] | 28INR0223 | Bayou Creek Solar | San Patricio | 2028-09-25 | 2026-06-02 | Solar | PV | 256.9 | 2028 | Yes
[7 empty] | 26INR0074 | Anila Solar | Wilson | 2028-09-30 | 2025-03-06 | Solar | PV | 200.8 | 2028 | Yes
[7 empty] | 29INR0009 | Aurelius 2 Solar | Deaf Smith | 2028-09-30 | 2026-07-10 | Solar | PV | 445.4 | 2028 | Yes
[7 empty] | 27INR0288 | Rain Lily Solar 1 | Hood | 2028-10-15 | 2026-09-16 | Solar | PV | 147.76 | 2028 | Yes
[7 empty] | 26INR0211 | Titus Low Carbon Ventures Solar 1 | San Patricio | 2028-10-16 | 2026-05-26 | Solar | PV | 338.04 | 2028 | No
[7 empty] | 20INR0143 | Tri-X Solar 1 SLF | Crane | 2028-10-30 | 2026-08-21 | Solar | PV | 201.5 | 2028 | No
[7 empty] | 23INR0080 | Soda Lake Solar 2 SLF | Crane | 2028-10-30 | 2022-03-23 | Solar | PV | 201.74 | 2028 | No
[7 empty] | 27INR0047 | Sunscape Renewable Energy Solar SLF | Nueces | 2028-10-31 | 2024-07-18 | Solar | PV | 522.75 | 2028 | Yes
[7 empty] | 23INR0089 | Donegal Solar | Dickens | 2028-11-01 | 2022-07-25 | Solar | PV | 201.57 | 2028 | Yes
[7 empty] | 27INR0126 | Corvus Solar | Webb | 2028-11-12 | 2025-07-31 | Solar | PV | 201.5 | 2028 | Yes
[7 empty] | 28INR0486 | Spectra Solar | Scurry | 2028-11-16 | 2025-12-29 | Solar | PV | 1200 | 2028 | Yes
[7 empty] | 24INR0412 | Camino Ranch Solar SLF | Houston | 2028-12-09 | 2025-12-31 | Solar | PV | 296.42 | 2028 | No
[7 empty] | 26INR0256 | Camino Ranch Solar 2 SLF | Houston | 2028-12-09 | 2025-12-31 | Solar | PV | 237.21 | 2028 | No
[7 empty] | 24INR0059 | Cuchillas Solar | Webb | 2028-12-15 | 2023-06-20 | Solar | PV | 305.6 | 2028 | Yes
[7 empty] | 24INR0075 | Blue Bird Solar | Johnson | 2028-12-15 | 2024-01-18 | Solar | PV | 425.97 | 2028 | No
[7 empty] | 26INR0176 | Dionysus Solar | Houston | 2028-12-15 | 2026-07-31 | Solar | PV | 153.26 | 2028 | No
[7 empty] | 25INR0353 | Marshall Spring Solar | Gillespie | 2028-12-20 | 2025-12-26 | Solar | PV | 150 | 2028 | No
[7 empty] | 25INR0097 | Soleil Solar | Clay | 2028-12-28 | 2025-05-09 | Solar | PV | 451.69 | 2028 | Yes
[7 empty] | 24INR0172 | Smith Lake Solar DC | Grimes | 2028-12-29 | 2025-12-30 | Solar | PV | 402 | 2028 | No
[7 empty] | 28INR0008 | Oriole Solar | Knox | 2028-12-29 | 2025-12-08 | Solar | PV | 503.91 | 2028 | No
[7 empty] | 29INR0192 | Spurland Solar I | Dickens | 2028-12-30 | 2026-08-06 | Solar | PV | 302.1 | 2028 | Yes
[7 empty] | 29INR0195 | Spurland Solar II | Dickens | 2028-12-30 | 2026-08-06 | Solar | PV | 201.6 | 2028 | No
[7 empty] | 21INR0220 | Maleza Solar | Wharton | 2028-12-31 | 2021-01-13 | Solar | PV | 254.94 | 2028 | Yes
[7 empty] | 22INR0209 | Felix North Solar | Wilbarger | 2028-12-31 | 2025-02-21 | Solar | PV | 200.98 | 2028 | Yes
[7 empty] | 24INR0452 | Longfellow Solar I | Pecos | 2028-12-31 | 2025-04-15 | Solar | PV | 178.2 | 2028 | No
[7 empty] | 24INR0454 | Longfellow Solar II | Pecos | 2028-12-31 | 2025-04-15 | Solar | PV | 207.36 | 2028 | No
[7 empty] | 27INR0007 | Felix East Solar | Wilbarger | 2028-12-31 | 2025-02-21 | Solar | PV | 200.92 | 2028 | Yes
[7 empty] | 27INR0012 | Felix West Solar | Wilbarger | 2028-12-31 | 2025-02-21 | Solar | PV | 200.95 | 2028 | Yes
[7 empty] | 29INR0013 | Cattle Drive Solar | Crane | 2028-12-31 | 2025-12-29 | Solar | PV | 307 | 2028 | No
[7 empty] | 23INR0202 | Erath County Solar | Erath | 2029-01-31 | 2023-06-01 | Solar | PV | 207.4 | 2029 | Yes
[7 empty] | 23INR0090 | Iguala Solar | Victoria | 2029-02-01 | 2025-07-29 | Solar | PV | 250 | 2029 | No
[7 empty] | 26INR0425 | Twinwood Solar 1 | Waller | 2029-02-01 | 2025-11-07 | Solar | PV | 358.06 | 2029 | Yes
[7 empty] | 27INR0435 | Clairemont Solar 1 | Kent | 2029-02-13 | 2025-11-24 | Solar | PV | 251.75 | 2029 | Yes
[7 empty] | 27INR0234 | Lima Solar Project | Grayson | 2029-03-01 | 2026-09-02 | Solar | PV | 101.3 | 2029 | No
[7 empty] | 22INR0374 | Inertia Solar | Haskell | 2029-03-31 | 2023-05-10 | Solar | PV | 202.39 | 2029 | Yes
[7 empty] | 24INR0156 | Moonstone Solar Project | Wilson | 2029-03-31 | 2025-02-17 | Solar | PV | 174.97 | 2029 | No
[7 empty] | 26INR0311 | Senator Aggreko Solar | Maverick | 2029-03-31 | 2025-12-31 | Solar | PV | 258.91 | 2029 | No
[7 empty] | 24INR0407 | Mercury Solar III | Hill | 2029-04-01 | 2025-12-12 | Solar | PV | 203.5 | 2029 | Yes
[7 empty] | 26INR0255 | Operation Sunshine | Concho | 2029-04-01 | 2025-08-27 | Solar | PV | 603.2 | 2029 | Yes
[7 empty] | 28INR0013 | Varadero Solar | Limestone | 2029-04-01 | 2025-12-12 | Solar | PV | 206 | 2029 | Yes
[7 empty] | 20INR0050 | Castro Solar | Castro | 2029-04-18 | 2020-11-30 | Solar | PV | 224.67 | 2029 | No
[7 empty] | 24INR0269 | Bar Candela Solar SLF | Freestone | 2029-05-16 | 2025-05-06 | Solar | PV | 200.3 | 2029 | No
[7 empty] | 26INR0143 | Santa Garcias Solar | Kleberg | 2029-05-30 | 2025-12-31 | Solar | PV | 265 | 2029 | No
[7 empty] | 29INR0017 | Big Rooter East Solar | Robertson | 2029-05-31 | 2025-06-01 | Solar | PV | 554.7 | 2029 | No
[7 empty] | 23INR0088 | Nockenut Springs Solar 1 | Guadalupe | 2029-06-05 | 2023-11-17 | Solar | PV | 203.17 | 2029 | Yes
[7 empty] | 24INR0007 | Nockenut Springs Solar 2 | Guadalupe | 2029-06-05 | 2023-11-17 | Solar | PV | 203.26 | 2029 | Yes
[7 empty] | 27INR0372 | Abeja Solar Farm | Bee | 2029-06-07 | 2025-12-16 | Solar | PV | 200.84 | 2029 | No
[7 empty] | 24INR0160 | Huisache Solar | Wilson | 2029-06-30 | 2025-08-12 | Solar | PV | 125.59 | 2029 | Yes
[7 empty] | 25INR0512 | Monument Hill Solar | Fayette | 2029-06-30 | 2025-12-22 | Solar | PV | 200 | 2029 | No
[7 empty] | 28INR0127 | Half Moon Solar | Starr | 2029-07-01 | 2025-09-08 | Solar | PV | 512.5 | 2029 | Yes
[7 empty] | 28INR0305 | Iron Cowboy Solar | San Patricio | 2029-07-10 | 2026-08-10 | Solar | PV | 144.59 | 2029 | Yes
[7 empty] | 22INR0281 | Pink Solar SLF | Hunt | 2029-07-31 | 2022-08-30 | Solar | PV | 152.41 | 2029 | No
[7 empty] | 28INR0297 | Magnet Solar | Borden | 2029-09-29 | 2025-12-11 | Solar | PV | 503.09 | 2029 | Yes
[7 empty] | 21INR0022 | Red Holly Solar | Dawson | 2029-09-30 | 2020-10-19 | Solar | PV | 260 | 2029 | No
[7 empty] | 29INR0131 | Caesar Solar | Borden | 2029-11-26 | 2026-09-15 | Solar | PV | 181.6 | 2029 | Yes
[7 empty] | 23INR0058 | Erin Solar | Wharton | 2029-12-31 | 2023-03-22 | Solar | PV | 208.34 | 2029 | No
[7 empty] | 29INR0219 | Cenizo Solar | Webb | 2029-12-31 | 2026-09-28 | Solar | PV | 301.39 | 2029 | No
[7 empty] | 27INR0105 | Starlight Solar | Mills | 2030-05-09 | 2025-12-31 | Solar | PV | 130.72 | 2030 | No
[7 empty] | 28INR0114 | Elk Ridge Solar | Pecos | 2030-07-01 | 2026-09-22 | Solar | PV | 503 | 2030 | Yes
[7 empty] | 30INR0053 | MRR Solar | Pecos | 2030-07-01 | 2026-09-15 | Solar | PV | 500 | 2030 | Yes
[7 empty] | 27INR0022 | Panhandle Flagship Solar 1 | Carson | 2031-06-30 | 2025-08-28 | Solar | PV | 439.4 | 2031 | No
[7 empty] | 27INR0023 | Panhandle Flagship Solar 2 | Hutchinson | 2031-06-30 | 2025-08-28 | Solar | PV | 304.4 | 2031 | No
[7 empty] | 27INR0024 | Panhandle Flagship Solar 3 | Hutchinson | 2031-06-30 | 2025-08-28 | Solar | PV | 260.3 | 2031 | No
[7 empty] | 27INR0111 | Malachite Solar | Wharton | 2032-04-30 | 2025-12-26 | Solar | PV | 184.55 | 2032 | No

## Battery Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 25INR0688 | Giga Texas Data Center | Travis | 2025-12-15 | 2025-04-30 | Battery | BA | 133 | 2025 | No
[7 empty] | 22INR0504 | Barton Branch IA | Robertson | 2026-10-01 | 2025-06-18 | Battery | BA | 203.62 | 2026 | Yes
[7 empty] | 25INR0231 | Apache Hill BESS | Hood | 2026-10-31 | 2024-06-26 | Battery | BA | 201.15 | 2026 | Yes
[7 empty] | 26INR0636 | Lyra Storage | Borden | 2026-11-12 | 2025-08-13 | Battery | BA | 500 | 2026 | No
[7 empty] | 25INR0133 | Rose Quartz BESS | Dimmit | 2026-12-01 | 2026-07-28 | Battery | BA | 101.41 | 2026 | No
[7 empty] | 26INR0375 | Avalon BESS | Fort Bend | 2026-12-01 | 2024-12-17 | Battery | BA | 522.12 | 2026 | No
[7 empty] | 22INR0503 | Tidwell Prairie II Batt | Robertson | 2026-12-03 | 2025-01-13 | Battery | BA | 203.62 | 2026 | Yes
[7 empty] | 20INR0246 | Ryan Energy Storage | Coryell | 2026-12-12 | 2021-02-18 | Battery | BA | 51.6 | 2026 | Yes
[7 empty] | 22INR0558 | Callisto II Energy Center | Harris | 2026-12-17 | 2023-12-11 | Battery | BA | 203.2 | 2026 | Yes
[7 empty] | 28INR0154 | Pamela Heights I | Harris | 2026-12-18 | 2025-10-07 | Battery | BA | 101.65 | 2026 | Yes
[7 empty] | 26INR0250 | Duffy BESS | Matagorda | 2026-12-31 | 2025-07-28 | Battery | BA | 241.05 | 2026 | Yes
[7 empty] | 25INR0101 | Drake BESS | Collin | 2027-01-29 | 2025-05-06 | Battery | BA | 257.3 | 2027 | Yes
[7 empty] | 24INR0210 | Raven Storage | Wharton | 2027-02-01 | 2024-06-04 | Battery | BA | 103.53 | 2027 | Yes
[7 empty] | 24INR0274 | Bufflehead BESS | Collin | 2027-02-15 | 2024-04-10 | Battery | BA | 153.77 | 2027 | No
[7 empty] | 25INR0271 | City Breeze BESS | Matagorda | 2027-03-18 | 2024-05-15 | Battery | BA | 143.1 | 2027 | Yes
[7 empty] | 26INR0201 | Rock Rose BESS | Fort Bend | 2027-03-19 | 2024-06-15 | Battery | BA | 208.5 | 2027 | Yes
[7 empty] | 24INR0136 | Eagle Springs Storage | Delta | 2027-03-29 | 2024-04-17 | Battery | BA | 33.94 | 2027 | Yes
[7 empty] | 24INR0155 | Lupinus Storage 2 | Franklin | 2027-04-03 | 2025-03-04 | Battery | BA | 124.55 | 2027 | Yes
[7 empty] | 24INR0472 | Amador Storage | Van Zandt | 2027-04-08 | 2023-11-02 | Battery | BA | 102.41 | 2027 | Yes
[7 empty] | 25INR0616 | Bobcat Bluff Storage SLF | Archer | 2027-04-15 | 2026-01-12 | Battery | BA | 0 | 2027 | No
[7 empty] | 26INR0296 | Sherbino II BESS SLF | Pecos | 2027-04-19 | 2024-08-01 | Battery | BA | 77.37 | 2027 | Yes
[7 empty] | 23INR0331 | Orange Grove BESS | Jim Wells | 2027-04-30 | 2022-11-30 | Battery | BA | 61.39 | 2027 | Yes
[7 empty] | 25INR0432 | Brotherton Storage | Anderson | 2027-05-01 | 2024-08-06 | Battery | BA | 176.13 | 2027 | Yes
[7 empty] | 23INR0392 | Honeycomb Storage SLF | Bee | 2027-05-11 | 2023-05-01 | Battery | BA | 0 | 2027 | Yes
[7 empty] | 25INR0301 | Van Zandt Energy Storage | Ector | 2027-05-15 | 2025-03-03 | Battery | BA | 256 | 2027 | No
[7 empty] | 26INR0340 | SOUTHERN SELECT ENERGY STORAGE | Galveston | 2027-05-24 | 2025-05-09 | Battery | BA | 204.85 | 2027 | Yes
[7 empty] | 25INR0189 | Staccato BESS | Fayette | 2027-05-28 | 2024-08-27 | Battery | BA | 201.8 | 2027 | Yes
[7 empty] | 22INR0239 | Rockefeller Storage | Schleicher | 2027-06-01 | 2024-09-23 | Battery | BA | 206.8 | 2027 | Yes
[7 empty] | 23INR0421 | Bee Branch IA | Robertson | 2027-06-01 | 2026-03-13 | Battery | BA | 203.75 | 2027 | Yes
[7 empty] | 25INR0235 | Austin Bayou Storage I | Brazoria | 2027-06-01 | 2025-02-14 | Battery | BA | 150.68 | 2027 | No
[7 empty] | 25INR0236 | Austin Bayou Storage II | Brazoria | 2027-06-01 | 2025-02-14 | Battery | BA | 156.6 | 2027 | No
[7 empty] | 25INR0237 | Austin Bayou Storage III | Brazoria | 2027-06-01 | 2025-02-14 | Battery | BA | 156.6 | 2027 | No
[7 empty] | 24INR0355 | Anatole Renewable Energy Storage | Henderson | 2027-06-30 | 2024-05-10 | Battery | BA | 207.82 | 2027 | Yes
[7 empty] | 26INR0385 | Nanulak BESS | Reeves | 2027-06-30 | 2025-11-19 | Battery | BA | 181.54 | 2027 | No
[7 empty] | 22INR0552 | Sowers Storage | Kaufman | 2027-07-01 | 2022-04-22 | Battery | BA | 208.89 | 2027 | Yes
[7 empty] | 26INR0034 | Bracero Pecan Storage | Reeves | 2027-07-01 | 2024-06-27 | Battery | BA | 238.21 | 2027 | Yes
[7 empty] | 23INR0232 | Hoke Storage | Gonzales | 2027-07-05 | 2022-04-25 | Battery | BA | 33.17 | 2027 | Yes
[7 empty] | 25INR0473 | Crowded Star I BESS | Jones | 2027-07-09 | 2025-12-01 | Battery | BA | 202.69 | 2027 | Yes
[7 empty] | 25INR0334 | Star Dairy Storage | Lamar | 2027-07-12 | 2024-12-09 | Battery | BA | 205.24 | 2027 | No
[7 empty] | 25INR0417 | Mesa View Storage | Upton | 2027-07-15 | 2024-09-09 | Battery | BA | 254.88 | 2027 | Yes
[7 empty] | 25INR0131 | SOSA Storage | Madison | 2027-07-20 | 2023-12-05 | Battery | BA | 154.63 | 2027 | Yes
[7 empty] | 24INR0386 | Black & Gold Energy Storage | Menard | 2027-07-30 | 2024-08-14 | Battery | BA | 203.8 | 2027 | Yes
[7 empty] | 25INR0253 | Whiskey BESS | Van Zandt | 2027-07-31 | 2025-03-28 | Battery | BA | 153.72 | 2027 | No
[7 empty] | 26INR0156 | Ross Storage | Refugio | 2027-07-31 | 2024-06-27 | Battery | BA | 510.99 | 2027 | No
[7 empty] | 25INR0442 | Happy Dog Storage | Milam | 2027-08-04 | 2024-12-16 | Battery | BA | 104.52 | 2027 | No
[7 empty] | 24INR0196 | Dori BQ BESS | Harris | 2027-08-30 | 2023-05-31 | Battery | BA | 154 | 2027 | No
[7 empty] | 25INR0384 | Zorro BESS | Van Zandt | 2027-08-31 | 2025-03-28 | Battery | BA | 153.69 | 2027 | No
[7 empty] | 23INR0342 | Brizo BESS | Victoria | 2027-09-01 | 2025-03-27 | Battery | BA | 144.22 | 2027 | No
[7 empty] | 27INR0173 | Trenno BESS | Johnson | 2027-09-13 | 2025-08-18 | Battery | BA | 202.56 | 2027 | No
[7 empty] | 25INR0122 | Vial BESS | Hill | 2027-09-15 | 2025-08-04 | Battery | BA | 135.18 | 2027 | Yes
[7 empty] | 24INR0496 | Indigo Storage | Fisher | 2027-09-17 | 2026-03-27 | Battery | BA | 60 | 2027 | Yes
[7 empty] | 25INR0528 | Indigo Storage 2 | Fisher | 2027-09-17 | 2026-03-27 | Battery | BA | 60 | 2027 | Yes
[7 empty] | 25INR0529 | Indigo Storage 3 | Fisher | 2027-09-17 | 2026-03-27 | Battery | BA | 60 | 2027 | Yes
[7 empty] | 25INR0530 | Indigo Storage 4 | Fisher | 2027-09-17 | 2026-03-27 | Battery | BA | 60 | 2027 | Yes
[7 empty] | 26INR0330 | Alamo City BESS | Bexar | 2027-09-21 | 2025-05-22 | Battery | BA | 128.2 | 2027 | No
[7 empty] | 26INR0033 | Fairway Storage | Freestone | 2027-09-24 | 2025-08-11 | Battery | BA | 120.3 | 2027 | Yes
[7 empty] | 23INR0140 | Seine BESS | Foard | 2027-10-01 | 2024-12-01 | Battery | BA | 308.88 | 2027 | Yes
[7 empty] | 24INR0392 | Riverwalk BESS | Bexar | 2027-10-01 | 2026-08-18 | Battery | BA | 120 | 2027 | No
Year | Cumulative Operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | Small Generator | 27INR0440 | Wisdom BESS SLF | Pecos | 2027-10-06 | 2026-03-18 | Battery | BA | 102.88 | 2027 | No
2012 | 36 | 36 | 0 | 0 | 0 | 0 | 25INR0480 | Bell Creek BESS | Brazoria | 2027-10-30 | 2024-11-14 | Battery | BA | 200.9 | 2027 | No
2013 | 36 | 36 | 0 | 0 | 0 | 0 | 26INR0314 | Brazos River BESS | Brazoria | 2027-10-30 | 2025-05-24 | Battery | BA | 180.36 | 2027 | No
2014 | 36 | 36 | 0 | 0 | 0 | 0 | 26INR0131 | Elm Flats Storage SLF | Navarro | 2027-11-01 | 2025-11-21 | Battery | BA | 0 | 2027 | Yes
2015 | 38 | 38 | 0 | 0 | 0 | 0 | 26INR0226 | First Capitol BESS | Brazoria | 2027-11-01 | 2025-05-15 | Battery | BA | 257.48 | 2027 | Yes
2016 | 39 | 39 | 0 | 0 | 0 | 0 | 25INR0375 | NavBoot BESS | Nueces | 2027-11-11 | 2025-10-20 | Battery | BA | 303.7 | 2027 | No
2017 | 92.3 | 92.3 | 0 | 0 | 0 | 0 | 24INR0281 | Red Egret BESS | Galveston | 2027-11-17 | 2023-06-07 | Battery | BA | 310.58 | 2027 | Yes
2018 | 103.7 | 103.7 | 0 | 0 | 0 | 0 | 22INR0457 | Anson BAT | Jones | 2027-12-01 | 2024-08-15 | Battery | BA | 153.55 | 2027 | Yes
2019 | 153.3 | 153.3 | 0 | 0 | 0 | 0 | 23INR0290 | Zeya BESS | Galveston | 2027-12-01 | 2023-01-20 | Battery | BA | 255.33 | 2027 | Yes
2020 | 275.4 | 275.4 | 0 | 0 | 0 | 0 | 25INR0169 | Piedra BESS | Freestone | 2027-12-01 | 2024-07-02 | Battery | BA | 103.65 | 2027 | Yes
2021 | 1306.53 | 1306.53 | 0 | 0 | 0 | 0 | 26INR0474 | Sorghum BESS | Wharton | 2027-12-01 | 2025-01-08 | Battery | BA | 208.9 | 2027 | No
2022 | 2776.96 | 2776.96 | 0 | 0 | 0 | 0 | 27INR0485 | Blackland Prairie 1 Energy Storage | Travis | 2027-12-01 | 2026-04-10 | Battery | BA | 102.1 | 2027 | No
2023 | 5090.12 | 5090.12 | 0 | 0 | 0 | 0 | 25INR0230 | Great Rock BESS | Leon | 2027-12-20 | 2024-08-23 | Battery | BA | 300.9 | 2027 | No
2024 | 10014.66 | 10014.66 | 0 | 0 | 0 | 0 | 21INR0444 | Long Point Storage | Brazoria | 2027-12-30 | 2023-08-28 | Battery | BA | 100.62 | 2027 | No
2025 | 16655.8 | 16655.8 | 0 | 0 | 0 | 0 | 23INR0216 | Venus Mill Storage | Ellis | 2027-12-31 | 2025-12-24 | Battery | BA | 100.8 | 2027 | No
2026 | 24057.78 | 21536.67 | 1205.89 | 1256.53 | 0 | 58.69 | 25INR0371 | McMurtre Storage | Hunt | 2027-12-31 | 2025-09-17 | Battery | BA | 176.13 | 2027 | Yes
2027 | 34818.2 | 21536.67 | 7077.56 | 6080.02 | 0 | 123.95 | 25INR0441 | Dios BESS | Jackson | 2027-12-31 | 2025-04-03 | Battery | BA | 201.08 | 2027 | Yes
2028 | 50441.53 | 21536.67 | 17668.2 | 11112.71 | 0 | 123.95 | 25INR0451 | Tres Rios Ranch BESS | Upton | 2027-12-31 | 2025-12-30 | Battery | BA | 290 | 2027 | No
2029 | 55942.48 | 21536.67 | 19975.1 | 14306.76 | 0 | 123.95 | 24INR0178 | Cumulus Grid BESS | Ellis | 2028-01-01 | 2025-06-03 | Battery | BA | 210.74 | 2028 | Yes
2030 | 56760.77 | 21536.67 | 20123.71 | 14976.44 | 0 | 123.95 | 26INR0417 | GAMAY ENERGY STORAGE | Brazoria | 2028-01-01 | 2025-05-27 | Battery | BA | 418.6 | 2028 | No
2031 | 57132.47 | 21536.67 | 20123.71 | 15348.14 | 0 | 123.95 | 25INR0175 | Concho Pearl Storage | Concho | 2028-01-09 | 2024-07-22 | Battery | BA | 162.4 | 2028 | No
2032 | 57323.59 | 21536.67 | 20123.71 | 15539.26 | 0 | 123.95 | 23INR0137 | Diran BESS | Wharton | 2028-01-31 | 2025-01-07 | Battery | BA | 103 | 2028 | Yes
[7 empty] | 25INR0391 | Purple Sage BESS 1 | Collin | 2028-02-12 | 2024-10-11 | Battery | BA | 156 | 2028 | Yes
[7 empty] | 25INR0392 | Purple Sage BESS 2 | Collin | 2028-02-12 | 2024-10-11 | Battery | BA | 156 | 2028 | Yes
[7 empty] | 26INR0551 | Hastings Park BESS | Brazoria | 2028-02-27 | 2025-08-13 | Battery | BA | 256.34 | 2028 | No
[7 empty] | 23INR0425 | Coneflower Storage Project | Chambers | 2028-02-28 | 2024-03-25 | Battery | BA | 170.85 | 2028 | Yes
[7 empty] | 26INR0189 | Skipjack Energy Storage | Brazoria | 2028-02-28 | 2024-08-13 | Battery | BA | 150.6 | 2028 | Yes
[7 empty] | 24INR0425 | Two Brothers ESS | Victoria | 2028-02-29 | 2024-04-22 | Battery | BA | 154.65 | 2028 | Yes
[7 empty] | 25INR0421 | Aldrin 138 BESS | Brazoria | 2028-03-01 | 2024-04-18 | Battery | BA | 207 | 2028 | Yes
[7 empty] | 25INR0425 | Aldrin 345 BESS | Brazoria | 2028-03-01 | 2024-06-15 | Battery | BA | 362 | 2028 | Yes
[7 empty] | 24INR0066 | Keys Hollow Storage Phase II SLF | Goliad | 2028-03-10 | 2024-10-29 | Battery | BA | 0 | 2028 | Yes
[7 empty] | 24INR0068 | KEYS HOLLOW STORAGE SLF | Goliad | 2028-03-10 | 2024-10-29 | Battery | BA | 0 | 2028 | Yes
[7 empty] | 26INR0116 | Falcon Zapata Storage 138 | Zapata | 2028-03-11 | 2026-02-03 | Battery | BA | 200.79 | 2028 | Yes
[7 empty] | 23INR0200 | Paradiso BESS | Atascosa | 2028-03-15 | 2025-04-18 | Battery | BA | 102.3 | 2028 | Yes
[7 empty] | 24INR0207 | Glasgow Storage | Navarro | 2028-03-16 | 2023-11-08 | Battery | BA | 101 | 2028 | Yes
[7 empty] | 25INR0202 | East West BESS | Kerr | 2028-03-17 | 2024-07-12 | Battery | BA | 122.6 | 2028 | No
[7 empty] | 24INR0453 | Longfellow BESS I | Pecos | 2028-03-30 | 2025-04-15 | Battery | BA | 54.99 | 2028 | Yes
[7 empty] | 24INR0455 | Longfellow BESS II | Pecos | 2028-03-30 | 2025-04-15 | Battery | BA | 105.75 | 2028 | Yes
[7 empty] | 25INR0557 | McCamey's Castle Battery | Upton | 2028-03-30 | 2025-03-20 | Battery | BA | 409.6 | 2028 | Yes
[7 empty] | 24INR0485 | Rutile BESS | Runnels | 2028-03-31 | 2025-07-17 | Battery | BA | 100.65 | 2028 | Yes
[7 empty] | 25INR0138 | Champaign BESS | Glasscock | 2028-03-31 | 2025-07-31 | Battery | BA | 201.13 | 2028 | Yes
[7 empty] | 27INR0085 | Eagle Claw Energy Center | Grimes | 2028-03-31 | 2025-09-15 | Battery | BA | 204.58 | 2028 | Yes
[7 empty] | 25INR0046 | Blue Skies BESS | Hill | 2028-04-01 | 2024-06-20 | Battery | BA | 306.26 | 2028 | Yes
[7 empty] | 26INR0453 | Cannibal Draw Storage | Glasscock | 2028-04-10 | 2025-01-17 | Battery | BA | 98.6 | 2028 | Yes
[7 empty] | 24INR0058 | Briggs Storage | Haskell | 2028-04-15 | 2025-03-15 | Battery | BA | 336 | 2028 | Yes
[7 empty] | 23INR0502 | Adelite Storage | Milam | 2028-04-20 | 2024-08-27 | Battery | BA | 231.88 | 2028 | Yes
[7 empty] | 23INR0062 | Noria Storage | Nueces | 2028-04-21 | 2022-10-12 | Battery | BA | 75 | 2028 | Yes
[7 empty] | 25INR0657 | O'Bannion Energy Storage | Jack | 2028-04-21 | 2025-12-05 | Battery | BA | 306.4 | 2028 | Yes
[7 empty] | 26INR0252 | Neutron Storage | McLennan | 2028-04-29 | 2025-12-05 | Battery | BA | 104.5 | 2028 | Yes
[7 empty] | 24INR0126 | High Noon Storage | Hill | 2028-05-09 | 2024-05-08 | Battery | BA | 94 | 2028 | Yes
[7 empty] | 24INR0275 | Picadillo BESS | Martin | 2028-05-15 | 2024-01-23 | Battery | BA | 100.83 | 2028 | No
[7 empty] | 25INR0100 | Goldeneye BESS | Bell | 2028-05-15 | 2024-02-26 | Battery | BA | 201.6 | 2028 | No
[7 empty] | 24INR0528 | Blanquilla BESS | Nueces | 2028-05-19 | 2024-09-05 | Battery | BA | 200.78 | 2028 | Yes
[7 empty] | 26INR0291 | Cold Creek Storage 2 | Schleicher | 2028-05-28 | 2025-04-23 | Battery | BA | 171.75 | 2028 | No
[7 empty] | 21INR0029 | Red Holly Storage 1 | Dawson | 2028-05-30 | 2020-10-19 | Battery | BA | 50 | 2028 | No
[7 empty] | 21INR0033 | Red Holly Storage | Dawson | 2028-05-30 | 2020-10-19 | Battery | BA | 50 | 2028 | No
[7 empty] | 25INR0370 | Willis Storage | Rains | 2028-05-31 | 2025-04-07 | Battery | BA | 176.13 | 2028 | Yes
[7 empty] | 25INR0402 | Driet BESS | Colorado | 2028-06-20 | 2025-12-23 | Battery | BA | 150.52 | 2028 | No
[7 empty] | 24INR0442 | Midnight Sun Energy Storage | Crockett | 2028-06-29 | 2025-07-14 | Battery | BA | 523.86 | 2028 | Yes
[7 empty] | 21INR0505 | Ramsey Storage | Wharton | 2028-06-30 | 2022-08-11 | Battery | BA | 500 | 2028 | Yes
[7 empty] | 24INR0282 | Royal River BESS | Brazoria | 2028-06-30 | 2023-12-15 | Battery | BA | 310.7 | 2028 | Yes
[7 empty] | 25INR0061 | Argenta Storage | Bee | 2028-06-30 | 2024-04-05 | Battery | BA | 192 | 2028 | Yes
[7 empty] | 25INR0262 | Shepard Energy Storage | Galveston | 2028-06-30 | 2024-01-17 | Battery | BA | 256.79 | 2028 | Yes
[7 empty] | 24INR0169 | Yaupon Storage SLF | Milam | 2028-07-01 | 2023-09-28 | Battery | BA | 0 | 2028 | Yes
[7 empty] | 25INR0155 | Nymphaea Storage | Wichita | 2028-07-01 | 2026-05-18 | Battery | BA | 61 | 2028 | Yes
[7 empty] | 26INR0601 | Crocus Storage | Stephens | 2028-07-01 | 2026-08-04 | Battery | BA | 51 | 2028 | No
[7 empty] | 27INR0050 | Darkwood BESS | Comanche | 2028-07-01 | 2025-11-05 | Battery | BA | 150.5 | 2028 | Yes
[7 empty] | 28INR0191 | San Gabriel Storage | Milam | 2028-07-01 | 2026-08-06 | Battery | BA | 127.5 | 2028 | No
[7 empty] | 24INR0338 | Eldora BESS | Matagorda | 2028-07-02 | 2023-11-15 | Battery | BA | 201.31 | 2028 | Yes
[7 empty] | 26INR0285 | Hill Valley BESS | Grimes | 2028-07-15 | 2026-04-21 | Battery | BA | 245.8 | 2028 | No
[7 empty] | 26INR0324 | Misty Hollow BESS | Grimes | 2028-07-15 | 2025-12-04 | Battery | BA | 245.8 | 2028 | No
[7 empty] | 26INR0469 | Roxton Storage | Lamar | 2028-07-21 | 2026-09-03 | Battery | BA | 102 | 2028 | Yes
[7 empty] | 25INR0283 | Hornet Storage II SLF | Swisher | 2028-07-31 | 2024-08-21 | Battery | BA | 0 | 2028 | Yes
[7 empty] | 23INR0478 | Rhoda Storage | Milam | 2028-08-01 | 2025-12-31 | Battery | BA | 141.23 | 2028 | No
[7 empty] | 24INR0198 | Two Forks BESS | Cooke | 2028-08-01 | 2024-05-03 | Battery | BA | 309.8 | 2028 | Yes
[7 empty] | 25INR0173 | Wolf Spring Storage | Dickens | 2028-08-25 | 2024-08-14 | Battery | BA | 202.7 | 2028 | No
[7 empty] | 26INR0555 | Desert Palm BESS | Dimmit | 2028-09-01 | 2026-07-24 | Battery | BA | 201.3 | 2028 | No
[7 empty] | 22INR0443 | Bowstring BESS | San Patricio | 2028-09-18 | 2025-09-09 | Battery | BA | 155 | 2028 | Yes
[7 empty] | 28INR0094 | Pham BESS | Anderson | 2028-09-18 | 2026-07-31 | Battery | BA | 132.98 | 2028 | Yes
[7 empty] | 27INR0399 | Resaca Oasis Storage | Cameron | 2028-09-20 | 2025-05-22 | Battery | BA | 200.7 | 2028 | Yes
[7 empty] | 27INR0465 | Althea Storage | Maverick | 2028-09-21 | 2025-09-29 | Battery | BA | 251.3 | 2028 | Yes
[7 empty] | 25INR0661 | McCrae Energy Storage | Erath | 2028-09-25 | 2025-12-30 | Battery | BA | 306.35 | 2028 | No
[7 empty] | 26INR0077 | Anila BESS | Wilson | 2028-09-30 | 2025-03-06 | Battery | BA | 209 | 2028 | Yes
[7 empty] | 27INR0392 | Cernan BESS | Wharton | 2028-10-02 | 2025-12-30 | Battery | BA | 10.04 | 2028 | No
[7 empty] | 25INR0144 | Jasper BESS | Midland | 2028-10-11 | 2026-07-27 | Battery | BA | 201.13 | 2028 | Yes
[7 empty] | 25INR0146 | Blue Heron BESS | Reeves | 2028-10-11 | 2026-07-27 | Battery | BA | 201.13 | 2028 | Yes
[7 empty] | 27INR0285 | Rain Lily Storage 1 | Hood | 2028-10-15 | 2026-09-16 | Battery | BA | 105.6 | 2028 | Yes
[7 empty] | 26INR0428 | Diamond Cowboy Storage | San Patricio | 2028-10-16 | 2026-05-26 | Battery | BA | 103.5 | 2028 | Yes
[7 empty] | 24INR0375 | Possum Kingdom BESS | Jack | 2028-10-29 | 2025-07-30 | Battery | BA | 200.86 | 2028 | Yes
[7 empty] | 24INR0383 | Soda Lake BESS 2 SLF | Crane | 2028-10-30 | 2026-08-21 | Battery | BA | 205.35 | 2028 | No
[7 empty] | 28INR0389 | Tri-X BESS 1 SLF | Crane | 2028-10-30 | 2026-08-21 | Battery | BA | 205.3 | 2028 | No
[7 empty] | 27INR0048 | Sunscape Renewable Energy Storage SLF | Nueces | 2028-10-31 | 2024-07-18 | Battery | BA | 0 | 2028 | Yes
[7 empty] | 23INR0354 | Bordertown BESS | Starr | 2028-12-01 | 2022-10-12 | Battery | BA | 100 | 2028 | Yes
[7 empty] | 24INR0420 | Camino Ranch Storage SLF | Houston | 2028-12-09 | 2025-12-31 | Battery | BA | 298.06 | 2028 | No
[7 empty] | 26INR0257 | Camino Ranch Storage 2 SLF | Houston | 2028-12-09 | 2025-12-31 | Battery | BA | 238.45 | 2028 | No
[7 empty] | 21INR0492 | Stockyard Grid Batt | Tarrant | 2028-12-14 | 2022-10-26 | Battery | BA | 150.6 | 2028 | Yes
[7 empty] | 23INR0361 | Third Coast BESS | Jackson | 2028-12-15 | 2023-05-17 | Battery | BA | 102.82 | 2028 | Yes
[7 empty] | 23INR0469 | Big Elm Storage | Bell | 2028-12-15 | 2024-05-10 | Battery | BA | 120 | 2028 | Yes
[7 empty] | 25INR0447 | Waterloo BESS 1 | Bastrop | 2028-12-15 | 2024-09-04 | Battery | BA | 120 | 2028 | No
[7 empty] | 26INR0177 | Dionysus Storage | Houston | 2028-12-15 | 2026-07-31 | Battery | BA | 77.28 | 2028 | No
[7 empty] | 25INR0354 | Marshall Spring Storage | Gillespie | 2028-12-20 | 2025-12-26 | Battery | BA | 150 | 2028 | No
[7 empty] | 25INR0045 | Smith Lake Storage DC | Grimes | 2028-12-28 | 2025-12-30 | Battery | BA | 65 | 2028 | No
[7 empty] | 23INR0248 | Limewood Storage | Bell | 2028-12-29 | 2023-02-22 | Battery | BA | 50 | 2028 | Yes
[7 empty] | 28INR0009 | Oriole BES | Knox | 2028-12-29 | 2025-12-08 | Battery | BA | 150.39 | 2028 | No
[7 empty] | 25INR0071 | Albatross BESS | McLennan | 2028-12-30 | 2026-09-02 | Battery | BA | 50.4 | 2028 | Yes
[7 empty] | 25INR0579 | Albatross BESS 2 | McLennan | 2028-12-30 | 2026-09-02 | Battery | BA | 159.6 | 2028 | Yes
[7 empty] | 25INR0103 | Elio BESS | Brazoria | 2028-12-31 | 2024-09-15 | Battery | BA | 205.28 | 2028 | Yes
[7 empty] | 25INR0233 | OCI Cobb Creek ESS | Hill | 2028-12-31 | 2024-07-24 | Battery | BA | 201.6 | 2028 | Yes
[7 empty] | 25INR0293 | TOCE BESS 1 | Wharton | 2028-12-31 | 2024-12-30 | Battery | BA | 205.2 | 2028 | No
[7 empty] | 26INR0341 | Megamouth Energy Storage | Harris | 2028-12-31 | 2025-11-18 | Battery | BA | 101.3 | 2028 | No
[7 empty] | 27INR0109 | Two Barbaras BESS | Montgomery | 2029-01-04 | 2025-10-01 | Battery | BA | 217.16 | 2029 | Yes
[7 empty] | 26INR0426 | Maderagemela BESS1 | Waller | 2029-02-01 | 2025-11-07 | Battery | BA | 153.96 | 2029 | Yes
[7 empty] | 27INR0245 | Pez Rojo BESS | Harris | 2029-02-01 | 2026-05-01 | Battery | BA | 217.23 | 2029 | No
[7 empty] | 25INR0554 | Dan Kearney BESS | Brazoria | 2029-02-28 | 2024-10-18 | Battery | BA | 204.38 | 2029 | No
[7 empty] | 27INR0224 | Leopard BESS | Victoria | 2029-02-28 | 2025-06-09 | Battery | BA | 264.24 | 2029 | Yes
[7 empty] | 24INR0108 | Louisa Energy Storage | Bexar | 2029-03-12 | 2025-02-27 | Battery | BA | 102.77 | 2029 | Yes
[7 empty] | 22INR0387 | Val Vista Grid BESS 1 | Hidalgo | 2029-03-30 | 2025-12-31 | Battery | BA | 209.32 | 2029 | No
[7 empty] | 24INR0102 | Val Vista Grid BESS 2 | Hidalgo | 2029-03-30 | 2025-12-31 | Battery | BA | 210.56 | 2029 | No
[7 empty] | 25INR0143 | Ariji BESS | Howard | 2029-03-31 | 2025-08-01 | Battery | BA | 100.32 | 2029 | Yes
[7 empty] | 26INR0312 | Senator Aggreko Storage | Maverick | 2029-03-31 | 2025-12-31 | Battery | BA | 147.63 | 2029 | No
[7 empty] | 26INR0357 | Operation Sunshine Storage | Concho | 2029-04-01 | 2025-08-27 | Battery | BA | 409.8 | 2029 | Yes
[7 empty] | 28INR0295 | Margay Energy Storage | Brazoria | 2029-04-10 | 2025-12-26 | Battery | BA | 101.3 | 2029 | No
[7 empty] | 25INR0460 | Acker BESS | Castro | 2029-04-17 | 2025-04-21 | Battery | BA | 301.04 | 2029 | No
[7 empty] | 24INR0543 | Thomas Cameron BESS | Lampasas | 2029-04-28 | 2024-10-30 | Battery | BA | 205.5 | 2029 | Yes
[7 empty] | 22INR0401 | Eval Storage | Cameron | 2029-04-30 | 2022-02-03 | Battery | BA | 251.85 | 2029 | Yes
[7 empty] | 27INR0365 | Comanche BESS | Comanche | 2029-05-07 | 2026-03-20 | Battery | BA | 614.4 | 2029 | No
[7 empty] | 24INR0271 | Bar Candela Storage SLF | Freestone | 2029-05-16 | 2025-05-06 | Battery | BA | 0 | 2029 | No
[7 empty] | 23INR0479 | Taormina Storage | Bexar | 2029-05-26 | 2025-04-14 | Battery | BA | 231.86 | 2029 | Yes
[7 empty] | 28INR0288 | Outrider BESS | Dickens | 2029-06-26 | 2026-06-09 | Battery | BA | 302 | 2029 | No
[7 empty] | 24INR0376 | Huisache BESS | Wilson | 2029-06-30 | 2025-08-12 | Battery | BA | 100.67 | 2029 | Yes
[7 empty] | 28INR0306 | Iron Cowboy Storage | San Patricio | 2029-07-10 | 2026-08-10 | Battery | BA | 63.27 | 2029 | Yes
[7 empty] | 26INR0411 | Tex-Bar ESS | Madison | 2029-09-08 | 2025-12-26 | Battery | BA | 201.5 | 2029 | No
[7 empty] | 23INR0467 | Lavender Storage Project | Bexar | 2029-09-13 | 2025-06-23 | Battery | BA | 231.9 | 2029 | No
[7 empty] | 24INR0285 | APV Plumwood Storage | Chambers | 2029-10-01 | 2024-09-03 | Battery | BA | 200.82 | 2029 | No
[7 empty] | 23INR0324 | Lumberjack Storage | Cherokee | 2029-11-01 | 2024-03-20 | Battery | BA | 50.94 | 2029 | No
[7 empty] | 29INR0132 | Caesar Storage | Borden | 2029-11-26 | 2026-09-15 | Battery | BA | 205.5 | 2029 | Yes
[7 empty] | 29INR0018 | Big Rooter East Storage | Robertson | 2029-12-31 | 2025-06-01 | Battery | BA | 201.03 | 2029 | No
[7 empty] | 26INR0180 | Cape Rich BESS | Navarro | 2030-04-18 | 2025-02-03 | Battery | BA | 150.52 | 2030 | No
[7 empty] | 27INR0107 | Starlight Storage | Mills | 2030-05-09 | 2025-12-31 | Battery | BA | 208.96 | 2030 | No
[7 empty] | 24INR0514 | Rogers Draw BESS | Gillespie | 2030-07-31 | 2024-02-28 | Battery | BA | 148.61 | 2030 | Yes
[7 empty] | 27INR0091 | Oak Tree Energy Storage | Lavaca | 2030-09-20 | 2026-05-26 | Battery | BA | 310.2 | 2030 | No
[7 empty] | 27INR0025 | Panhandle Flagship Storage | Carson | 2031-06-30 | 2025-08-28 | Battery | BA | 371.7 | 2031 | No
[7 empty] | 27INR0112 | Malachite BESS | Wharton | 2032-04-30 | 2025-12-26 | Battery | BA | 191.12 | 2032 | No
Small Generators
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 25INR0601 | East Bernard BESS | Wharton | 2026-11-04 | 2024-04-29 | Battery | BA | 9.5 | 2026 | Yes
[7 empty] | 25INR0604 | Pledger BESS | Matagorda | 2026-11-04 | 2024-04-29 | Battery | BA | 9.5 | 2026 | Yes
[7 empty] | 25INR0768 | Stafford Hill BESS | Colorado | 2026-11-14 | 2026-05-28 | Battery | BA | 9.9 | 2026 | Yes
[7 empty] | 26INR0574 | Apple BESS | Ector | 2026-11-27 | 2025-04-03 | Battery | BA | 9.9 | 2026 | Yes
[7 empty] | 25INR0769 | Kleimann BESS | Colorado | 2026-12-08 | 2025-03-31 | Battery | BA | 9.9 | 2026 | Yes
[7 empty] | 26INR0714 | Pavlov BESS2 | Matagorda | 2026-12-13 | 2025-06-18 | Battery | BA | 9.99 | 2026 | Yes
[7 empty] | 24INR0712 | Byrd Ranch Repower | Brazoria | 2027-01-22 | 2020-12-14 | Battery | BA | 5.5 | 2027 | No
[7 empty] | 26INR0702 | Bexar Martinez BESS | Bexar | 2027-01-23 | 2026-02-03 | Battery | BA | 9.99 | 2027 | Yes
[7 empty] | 26INR0773 | Seaway BESS | Waller | 2027-02-22 | 2024-12-11 | Battery | BA | 9.9 | 2027 | Yes
[7 empty] | 26INR0774 | Wallis BESS2 | Austin | 2027-02-22 | 2024-12-11 | Battery | BA | 9.9 | 2027 | Yes
[7 empty] | 25INR0602 | Hockley BESS | Harris | 2027-03-01 | 2024-04-29 | Battery | BA | 9.99 | 2027 | Yes
[7 empty] | 26INR0734 | Alamo Street BESS2 | Pecos | 2027-03-30 | 2023-02-01 | Battery | BA | 9.99 | 2027 | Yes
[7 empty] | 23INR0603 | Damon BESS 2 | Brazoria | 2027-08-21 | 2023-10-06 | Battery | BA | 9.99 | 2027 | Yes
[7 empty] | 22INR0596 | Grizzly Ridge BESS SLF | Hamilton | 2030-07-01 | 2021-10-18 | Battery | BA | 0 | 2030 | Yes

## Gas-Combined Cycle Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 20INR0286 | Wise County Power Repower (CT1, CT2) | Wise | 2026-12-19 | 2001-03-19 | Gas | CC | 21 | 2026 | Yes
[7 empty] | 25INR0008 | BasRanch (TEF - Due Diligence) | Ward | 2028-12-01 | 2025-07-16 | Gas | CC | 1350 | 2028 | Yes
[7 empty] | 27INR0581 | Limitless Energy Hub I | Wilbarger | 2028-12-01 | 2025-12-31 | Gas | CC | 1238.25 | 2028 | No
[7 empty] | 27INR0582 | Limitless Energy Hub II | Wilbarger | 2028-12-01 | 2025-12-31 | Gas | CC | 1238.25 | 2028 | Yes
[7 empty] | 29INR0068 | Gregory Power Development SLF | San Patricio | 2028-12-19 | 2026-07-01 | Gas | CC | 469.9 | 2028 | No
[7 empty] | 29INR0150 | Jewett Energy Center 1 Gas | Freestone | 2029-11-01 | 2026-07-15 | Gas | CC | 1274 | 2029 | No
[7 empty] | 30INR0051 | Sim Gideon Combined Cycle | Bastrop | 2030-12-15 | 2025-12-19 | Gas | CC | 880 | 2030 | No
[7 empty] | 30INR0054 | SCHNEIDER COMBINED CYCLE | Caldwell | 2033-05-10 | 2025-12-19 | Gas | CC | 880 | 2033 | No
[7 empty] | 30INR0052 | Lost Pines Power Park | Bastrop | 2033-06-01 | 2025-12-26 | Gas | CC | 880 | 2033 | No
Year | Cumulative Operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | Small Generator
1999 | 7072.189 | 7072.189 | 0 | 0 | 0 | 0
2000 | 12056.519 | 12056.519 | 0 | 0 | 0 | 0
2001 | 18869.659 | 18869.659 | 0 | 0 | 0 | 0
2002 | 25147.899 | 25147.899 | 0 | 0 | 0 | 0
2003 | 30930.999 | 30930.999 | 0 | 0 | 0 | 0
2004 | 32961.519 | 32961.519 | 0 | 0 | 0 | 0
2005 | 32940.619 | 32940.619 | 0 | 0 | 0 | 0
2006 | 33644.819 | 33644.819 | 0 | 0 | 0 | 0
2007 | 34202.119 | 34202.119 | 0 | 0 | 0 | 0
2008 | 34763.219 | 34763.219 | 0 | 0 | 0 | 0
2009 | 35946.599 | 35946.599 | 0 | 0 | 0 | 0
2010 | 37406.799 | 37406.799 | 0 | 0 | 0 | 0
2011 | 38125.199 | 38125.199 | 0 | 0 | 0 | 0
2012 | 38125.199 | 38125.199 | 0 | 0 | 0 | 0
2013 | 38175.199 | 38175.199 | 0 | 0 | 0 | 0
2014 | 40906.999 | 40906.999 | 0 | 0 | 0 | 0
2015 | 41724.099 | 41724.099 | 0 | 0 | 0 | 0
2016 | 41325.109 | 41325.109 | 0 | 0 | 0 | 0
2017 | 43477.609 | 43477.609 | 0 | 0 | 0 | 0
2018 | 43477.609 | 43477.609 | 0 | 0 | 0 | 0
2019 | 43718.009 | 43718.009 | 0 | 0 | 0 | 0
2020 | 43718.009 | 43718.009 | 0 | 0 | 0 | 0
2021 | 43718.009 | 43718.009 | 0 | 0 | 0 | 0
2022 | 43718.009 | 43718.009 | 0 | 0 | 0 | 0
2023 | 44168.609 | 44168.609 | 0 | 0 | 0 | 0
2024 | 44162.609 | 44162.609 | 0 | 0 | 0 | 0
2025 | 44100.609 | 44100.609 | 0 | 0 | 0 | 0
2026 | 44046.609 | 44025.609 | 21 | 0 | 0 | 0
2027 | 44046.609 | 44025.609 | 21 | 0 | 0 | 0
2028 | 48343.009 | 44025.609 | 2609.25 | 1708.15 | 0 | 0
2029 | 49617.009 | 44025.609 | 2609.25 | 2982.15 | 0 | 0
2030 | 50497.009 | 44025.609 | 2609.25 | 3862.15 | 0 | 0
2031 | 50497.009 | 44025.609 | 2609.25 | 3862.15 | 0 | 0
2032 | 50497.009 | 44025.609 | 2609.25 | 3862.15 | 0 | 0
2033 | 52257.009 | 44025.609 | 2609.25 | 5622.15 | 0 | 0

## Gas-Other Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 26INR0111 | Graphic Packaging Gas | McLennan | 2027-02-15 | 2026-07-30 | Gas | GT | 43.36 | 2027 | Yes
[7 empty] | 27INR0181 | Elk Unit 4 | Hale | 2027-02-28 | 2025-12-30 | Gas | GT | 210 | 2027 | Yes
[7 empty] | 26INR0261 | Bastrop Peaking Generators (TEF-Due Diligence) | Bastrop | 2027-12-07 | 2025-12-19 | Gas | GT | 1104 | 2027 | No
[7 empty] | 28INR0089 | EmberYork | Austin | 2028-01-01 | 2025-12-12 | Gas | GT | 900 | 2028 | No
[7 empty] | 28INR0090 | EmberGreen | Wharton | 2028-01-01 | 2026-08-04 | Gas | GT | 1036 | 2028 | No
[7 empty] | 28INR0108 | RAYBURN ENERGY STATION II Gas (TEF-Due Diligence) | Grayson | 2028-02-26 | 2025-12-22 | Gas | GT | 570 | 2028 | Yes
[7 empty] | 23INR0029 | Cedar Bayou 5 (TEF - Due Diligence) | Chambers | 2028-03-31 | 2022-01-10 | Gas | GT | 697 | 2028 | Yes
[7 empty] | 24INR0410 | NRG Greens Bayou 6 (TEF-Due Diligence) | Harris | 2028-05-01 | 2025-02-07 | Gas | GT | 445 | 2028 | Yes
[7 empty] | 28INR0105 | Vast Sands Power I (TEF -Due Diligence) | Ward | 2028-05-01 | 2025-10-31 | Gas | GT | 440 | 2028 | Yes
[7 empty] | 28INR0109 | Vast Sands Power II (TEF-Due Diligence) | Ward | 2028-06-30 | 2025-10-31 | Gas | GT | 440 | 2028 | Yes
[7 empty] | 26INR0408 | Liatris Flexible Gas | Brazoria | 2029-02-01 | 2025-11-01 | Gas | GT | 204.71 | 2029 | Yes
[7 empty] | 30INR0077 | Moon Hammer | Wheeler | 2030-11-30 | 2025-12-19 | Gas | GT | 1300 | 2030 | No
Year | Cumulative Operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | Small Generator
1999 | 34896.87 | 34896.87 | 0 | 0 | 0 | 0
2000 | 35054.48 | 35054.48 | 0 | 0 | 0 | 0
2001 | 35768.14 | 35768.14 | 0 | 0 | 0 | 0
2002 | 35768.14 | 35768.14 | 0 | 0 | 0 | 0
2003 | 35716.14 | 35716.14 | 0 | 0 | 0 | 0
2004 | 34378.24 | 34378.24 | 0 | 0 | 0 | 0
2005 | 32480.04 | 32480.04 | 0 | 0 | 0 | 0
2006 | 32062.14 | 32062.14 | 0 | 0 | 0 | 0
2007 | 30336.14 | 30336.14 | 0 | 0 | 0 | 0
2008 | 29968.94 | 29968.94 | 0 | 0 | 0 | 0
2009 | 25446.37 | 25446.37 | 0 | 0 | 0 | 0
2010 | 22779.25 | 22779.25 | 0 | 0 | 0 | 0
2011 | 22422.55 | 22422.55 | 0 | 0 | 0 | 0
2012 | 22684.75 | 22684.75 | 0 | 0 | 0 | 0
2013 | 22241.91 | 22241.91 | 0 | 0 | 0 | 0
2014 | 22132.91 | 22132.91 | 0 | 0 | 0 | 0
2015 | 20754.11 | 20754.11 | 0 | 0 | 0 | 0
2016 | 21794.49 | 21794.49 | 0 | 0 | 0 | 0
2017 | 21489.63 | 21489.63 | 0 | 0 | 0 | 0
2018 | 21918.79 | 21918.79 | 0 | 0 | 0 | 0
2019 | 21813.49 | 21813.49 | 0 | 0 | 0 | 0
2020 | 21800.49 | 21800.49 | 0 | 0 | 0 | 0
2021 | 22672.39 | 22672.39 | 0 | 0 | 0 | 0
2022 | 23304.54 | 23304.54 | 0 | 0 | 0 | 0
2023 | 23859.74 | 23859.74 | 0 | 0 | 0 | 0
2024 | 24603.84 | 24603.84 | 0 | 0 | 0 | 0
2025 | 24523.63 | 24523.63 | 0 | 0 | 0 | 0
2026 | 25391.35 | 25333.96 | 0 | 0 | 57.39 | 0
2027 | 26778.68 | 25333.96 | 253.36 | 1104 | 87.36 | 0
2028 | 31306.68 | 25333.96 | 2845.36 | 3040 | 87.36 | 0
2029 | 31511.39 | 25333.96 | 3050.07 | 3040 | 87.36 | 0
2030 | 32819.19 | 25333.96 | 3050.07 | 4340 | 95.16 | 0